## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 01/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-01
Name of the builder group |  |  |  |  | M/s.Prithvi Anand Housing And Land Developers
Name of the builder company |  |  |  |  | M/s.Prithvi Anand Housing And Land Developers
Name of the Project |  |  |  |  | Prithvi Anand Kuber Complex
Contact Details ( Name & Contact No.) |  |  |  |  | 2228701266
Name / No of the Building |  |  |  |  | Prithvi Anand Nav - Bldg No.1(Type A, B) Prithvi Anand Hans - Bldg No.2(Type C,D) Prithvi Anand Pati - Bldg No.3 (Type E, F) Bldg No. 4 (Type G)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA Name & No. |  |  |  |  | P99000025647
Project location details |  | Prithvi Anand Kuber Complex, Survey No.54/2, Palghar - Manor Road, Vevoor, Palghar.
Survey No |  | 54/2
Road |  | Palghar - Manor Road |  |  | Locality/Village |  | Vevoor
City |  | Palghar East |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401404
Near by Landmark |  | St. John College of Engineering and Management |  |  | Distance from city centre: |  | About 3.1Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Open Plot |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.704111,72.783417
Location Link |  | https://goo.gl/maps/1Kz8N4Jn3uLGjG1j7
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 10967.68
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.0015821
Total FSI availaible for the project |  |  |  |  | 1.1016
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 12081.8
Total number of Buildings |  |  |  |  | 7 Wings
Approval Detail : Plan approval
Layout Approval No |  | CBPPE/RB/2022/APL/00032 |  |  |  | Dated | 2022-09-28
Approved Floor plan No. |  | CBPPE/RB/2022/APL/00032 |  |  |  | Dated | 2022-09-28
Commencement Certificate No. |  | CBPPE/RB/2022/APL/00032 |  |  |  | Dated | 2022-09-28
Valid Up to: Building No.1 (Type A, B) - G + 11th Floor Building No.2 (Type C, D) - G + 9th Floor Building No.3 (Type E, F) - G + 7th Floor Building No.4 (Type G) - G + 5th Floor
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2022-09-28 |  | Expected Completion |  | 30/06/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 12081.8 |  | Approved no of units |  | Flats = 357 & shops = 51
Approved no of Floors |  | Building No.1 (Type A, B) - G + 1st to 11th Floor Building No.2 (Type C, D) - G + 1st to 9th Floor Building No.3 (Type E, F) - G + 1st to 7th Floor Building No.4 (Type G) - G + 5th Floor
Proposed no of Floors |  | Building No.1 (Type A, B) - G + 1st to 11th Floor Building No.2 (Type C, D) - G + 1st to 9th Floor Building No.3 (Type E, F) - G + 1st to 7th Floor Building No.4 (Type G) - G + 5th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Building No.1 (Type A & B) - G + 1st to 11th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 11
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% |  | 93.64% |  | 95% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% | [5 empty] | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% | [5 empty] | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 11 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 72.73% | [5 empty] | Plinth in process | 8.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 11
Construction details: |  | Building No.1 (Type B) - G + 1st to 11th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 11
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% |  | 92.73% |  | 95% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% | [5 empty] | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% | [5 empty] | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 11 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 54.55% | [5 empty] | Plinth in process | 8.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 11
Construction details: |  | Building No.2 (Type C & D) - G + 1st to 9th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 9
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% |  | 93.89% |  | 95% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% | [5 empty] | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% | [5 empty] | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% | [5 empty] | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 9 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 77.78% | [5 empty] | Plinth in process | 6.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 9
Construction details: |  | Building No.2 (Type D) - G + 1st to 9th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 9
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% |  | 93.33% |  | 95% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% | [5 empty] | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% | [5 empty] | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% | [5 empty] | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 9 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 66.67% | [5 empty] | Plinth in process | 6.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 9
Construction details: |  | Building No.3 (Type E, F) - G + 1st to 7th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth in process | 5.25
Possession |  | 7 | 100% | [5 empty] | Plinth completed | 7
Progress % |  | 100% |  |  | Disbursement % |  | 100% |  | Plinth completed | 7
Construction details: |  | Building No.4 (Type G) - G + 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 4 Floor, Flooring upto 3 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 4 Floor, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 82% |  | 92% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 80% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 60% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 60% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Stage of construction - Building No.3 (Type F): Plinth & RCC upto 1st slab work completed. Other work are in process…
Prithvi Anand Pati - Building no.3 (E & F Wing) |  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 100%
|  | RCC |  |  | 25%
|  | Brick |  |  | 0%
|  | Plaster |  |  | 0%
|  | Flooring |  |  | 0%
|  | Painting & Wooden Work |  |  | 0%
|  | Finishing |  |  | 0%
% Progress |  |  | 20% |  | % Disbursement |  |  | 37.5%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6500/-
Society, Maintenace & Electricity For 1 Year | [5 empty] | 100000/-
Recommended rate of Parking | [5 empty] | 100000/-
Development charges | [5 empty] | 100000/-
Distressed valuation of the Property | [5 empty] | 2800
Commercial Area Details : | [11 empty] | `
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No.1 (Type A) |  | 8 | 1170.0683 |  |  | 1813.6059
Building No.1 (Type B) |  | 8 | 1955.3635 |  |  | 3030.8134
Building No.2 (Type C) |  | 6 | 1137.0024 |  |  | 1762.3537
Building No.2 (Type D) |  | 11 | 2160.7654 |  |  | 3349.1863
Building No.3 (Type F) |  | 6 | 1177.9045 |  |  | 1825.752
Building No.4 (Type G) |  | 12 | 2160.6577 |  |  | 3349.0195
Total |  | 51 | 9761.7618 |  |  | 15130.7308
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No.1 (Type A) |  | 43 | 23124.0859 |  |  | 34908.1364
Building No.1 (Type B) |  | 87 | 33113.5085 |  |  | 50170.9179
Building No.2 (Type C) |  | 53 | 22602.1934 |  |  | 34214.2297
Building No.2 (Type D) |  | 53 | 22602.1934 |  |  | 34436.8454
Building No.3 (Type E) |  | 46 | 20072.5996 |  |  | 30108.8993
Building No.3 (Type F) |  | 45 | 19522.7744 |  |  | 29458.6192
Building No.4 (Type G) |  | 30 | 20539.3266 |  |  | 30808.9899
Total |  | 357 | 161576.6818 |  |  | 244106.6378
Grand Total |  | 408 | 171338.4436 |  |  | 259237.3686
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1
Type A
Ground Floor For Commercial & Parking
1 |  | Shop | 125.8042 |  | 0 | 194.9966 | N | Ground Floor
2 |  | Shop | 125.8042 |  | 0 | 194.9966 | N
3 |  | Shop | 139.5391 |  | 0 | 216.2856 | N
4 |  | Shop | 193.8865 |  | 0 | 300.5242 | N
5 |  | Shop | 193.8865 |  | 0 | 300.5242 | N
6 |  | Shop | 139.5391 |  | 0 | 216.2856 | N
7 |  | Shop | 125.8042 |  | 0 | 194.9966 | N
8 |  | Shop | 125.8042 |  | 0 | 194.9966 | N
1st Floor For Residential
1 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N | 1st Floor For Residential |  | 46.756
2 |  | 2BHK | 537.7694 |  | 111.0037 | 917.6579 | N
3 |  | 2BHK | 537.7694 |  | 111.0037 | 917.6579 | N
4 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
2nd to 7th & 9th to 11th Floor
1 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N | 2nd to 7th & 9th to 11th Floor |  | 46.756
2 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
3 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
4 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
8th Floor (Part Refuge Area)
1 |  | Refuge Area | [5 empty] | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
3 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
4 |  | 2BHK | 537.7694 |  | 0 | 806.6542 | N
Type B
Ground Floor For Commercial & Parking
1 |  | Shop | 318.4992 |  | 0 | 493.6738 | N | Ground Floor
2 |  | Shop | 223.1915 |  | 0 | 345.9469 | N
3 |  | Shop | 187.6703 |  | 0 | 290.889 | N
4 |  | Shop | 262.6986 |  | 0 | 407.1829 | N
5 |  | Shop | 262.6986 |  | 0 | 407.1829 | N
6 |  | Shop | 187.6703 |  | 0 | 290.889 | N
7 |  | Shop | 223.1915 |  | 0 | 345.9469 | N
8 |  | Shop | 289.7432 |  | 0 | 449.102 | N
1st Floor For Residential
1 |  | 1BHK | 380.615 |  | 80.6762 | 651.5987 | N | 1st Floor For Residential
2 |  | 1BHK | 380.615 |  | 169.6514 | 740.574 | N
3 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
4 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
5 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
6 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
7 |  | 1BHK | 380.615 |  | 169.6514 | 740.574 | N
8 |  | 1BHK | 380.615 |  | 80.6762 | 651.5987 | N
2nd to 7th & 9th to 11th Floor
1 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N | 2nd to 7th & 9th to 11th Floor |  | 33.4325
2 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
3 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
4 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
5 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
6 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
7 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
8 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
8th Floor (Part Refuge Area)
1 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
3 |  | Refuge Area |  |  |  |  | N
4 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
5 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
6 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
7 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
8 |  | 1BHK | 380.615 |  | 0 | 570.9226 | N
Building No.2
Type C
Ground Floor For Commercial, Society Office & Parking
1 |  | Shop | 245.1802 |  | 0 | 380.0294 | N | Ground Floor
2 |  | Shop | 187.6703 |  | 0 | 290.889 | N
3 |  | Shop | 147.709 |  | 0 | 228.9489 | N
4 |  | Shop | 115.4816 |  | 0 | 178.9964 | N
5 |  | Shop | 205.8109 |  | 0 | 319.0069 | N
6 |  | Shop | 235.1503 |  | 0 | 364.483 | N
1st Floor For Residential
1 |  | 1BHK | 331.5958 |  | 135.734 | 633.1277 | N | 1st Floor For Residential
2 |  | 1BHK | 359.8674 |  | 74.2931 | 614.0943 | N
3 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
4 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
5 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
6 |  | 1BHK | 364.0062 |  | 100.9125 | 646.9218 | N
2nd to 7th & 9th Floor
1 |  | 1BHK | 331.5958 |  | 0 | 497.3937 | N | 2nd to 7th & 9th Floor
2 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
3 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
4 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
5 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
6 |  | 1BHK | 364.0062 |  | 0 | 546.0093 | N
8th Floor (Part Refuge Area)
1 |  | 1BHK | 331.5958 |  | 0 | 497.3937 | N | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
3 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
4 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
5 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
6 |  | Refuge Area
Type D
Ground Floor For Commercial & Parking
1 |  | Shop | 207.7215 |  | 0 | 321.9684 | N | Ground Floor
2 |  | Shop | 187.6703 |  | 0 | 290.889 | N
3 |  | Shop | 147.709 |  | 0 | 228.9489 | N
4 |  | Shop | 115.4816 |  | 0 | 178.9964 | N
5 |  | Shop | 221.2949 |  | 0 | 343.0071 | N
6 |  | Shop | 268.48 |  | 0 | 416.144 | N
7 |  | Shop | 161.6591 |  | 0 | 250.5717 | N
8 |  | Shop | 181.4541 |  | 0 | 281.2539 | N
9 |  | Shop | 181.4541 |  | 0 | 281.2539 | N
10 |  | Shop | 201.2491 |  | 0 | 311.9361 | N
11 |  | Shop | 286.5915 |  | 0 | 444.2168 | N
1st Floor For Residential
1 |  | 1BHK | 364.0062 |  | 279.4334 | 825.4427 | N | 1st Floor For Residential
2 |  | 2BHK | 568.2316 |  | 66.2793 | 918.6267 | N
3 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
4 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
5 |  | 1BHK | 359.8674 |  | 84.7773 | 624.5784 | N
6 |  | 1BHK | 331.5958 |  | 103.0653 | 600.459 | N
2nd to 7th, 9th Floor
1 |  | 1BHK | 364.0062 |  | 0 | 546.0093 | N | 2nd to 7th, 9th Floor
2 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
3 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
4 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
5 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
6 |  | 1BHK | 331.5958 |  | 0 | 497.3937 | N
8th Floor (Part Refuge Area)
1 |  | Refuge Area | [5 empty] | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
3 |  | 2BHK | 568.2316 |  | 0 | 852.3473 | N
4 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
5 |  | 1BHK | 359.8674 |  | 0 | 539.8011 | N
6 |  | 1BHK | 331.5958 |  | 0 | 497.3937 | N
Building No.3
Type E
Ground Floor For Residential & Parking
001 |  | 1BHK | 343.0487 |  | 0 | 514.573 | N | Ground Floor
002 |  | 2BHK | 588.2526 |  | 0 | 882.3789 | N
003 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
004 |  | 1BHK | 341.8646 |  | 0 | 512.797 | N
1st To 7th Floor For Residential
101…...701 |  | 1BHK | 375.8789 |  | 0 | 563.8183 | N | 1st To 7th Floor For Residential
102…...702 |  | 2BHK | 586.638 |  | 0 | 879.957 | N
103…...703 |  | 2BHK | 588.2526 |  | 0 | 882.3789 | N
104…...704 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
105…...705 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
106…...706 |  | 1BHK | 341.8646 |  | 0 | 512.797 | N
Type F
Ground Floor For Parking, Commercial & Residential
1 |  | Shop | 279.0029 |  | 0 | 432.4545 | N | Ground Floor
2 |  | Shop | 204.3007 |  | 0 | 316.6661 | N
3 |  | Shop | 184.495 |  | 0 | 285.9672 | N
4 |  | Shop | 184.495 |  | 0 | 285.9672 | N
5 |  | Shop | 164.6892 |  | 0 | 255.2683 | N
6 |  | Shop | 160.9218 |  | 0 | 249.4288 | N
001 |  | 1BHK | 316.9998 |  | 0 | 475.4997 | N
002 |  | 1BHK | 371.358 |  | 0 | 557.037 | N
003 |  | 2BHK | 586.638 |  | 0 | 879.957 | N
1st Floor For Residential
101 |  | 1BHK | 316.9998 |  | 0 | 475.4997 | N | 1st Floor For Residential
102 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
103 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
104 |  | 2BHK | 587.1762 |  | 0 | 880.7643 | N
105 |  | 2BHK | 586.638 |  | 72.9799 | 952.9369 | N
106 |  | 1BHK | 375.8789 |  | 101.4776 | 665.2959 | N
2nd To 7th Floor
201…...701 |  | 1BHK | 316.9998 |  | 0 | 475.4997 | N | 2nd To 7th Floor
202…...702 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
203…...703 |  | 1BHK | 370.0663 |  | 0 | 555.0995 | N
204…...704 |  | 2BHK | 587.1762 |  | 0 | 880.7643 | N
205…...705 |  | 2BHK | 586.638 |  | 0 | 879.957 | N
206…...706 |  | 1BHK | 375.8789 |  | 0 | 563.8183 | N
Building No. 4
Type G
Ground Floor For Commercial, Society Office, Drivers Room & Parking
1 |  | Shop | 184.172 |  | 0 | 285.4667 | N | Ground Floor For Commercial, Society Office, Drivers Room & Parking |  | 16.4694 | 10.764
2 |  | Shop | 169.9636 |  | 0 | 263.4435 | N
3 |  | Shop | 114.6366 |  | 0 | 177.6867 | N |  |  | 10.0903
4 |  | Shop | 228.8426 |  | 0 | 354.7061 | N
5 |  | Shop | 152.9564 |  | 0 | 237.0825 | N
6 |  | Shop | 213.2348 |  | 0 | 330.514 | N
7 |  | Shop | 149.8349 |  | 0 | 232.2441 | N
8 |  | Shop | 117.8658 |  | 0 | 182.692 | N
9 |  | Shop | 221.0926 |  | 0 | 342.6935 | N
10 |  | Shop | 226.2593 |  | 0 | 350.7019 | N
11 |  | Shop | 199.3493 |  | 0 | 308.9914 | N
12 |  | Shop | 182.4498 |  | 0 | 282.7972 | N
1st to 5th Floor For Residential
1 |  | 1BHK | 475.6612 |  | 0 | 713.4917 | N | 1st to 5th Floor For Residential |  | 39.565
2 |  | 2.5BHK | 855.5227 |  | 0 | 1283.2841 | N
3 |  | 2BHK | 710.2087 |  | 0 | 1065.3131 | N
4 |  | 1BHK | 543.3667 |  | 0 | 815.0501 | N
5 |  | 2BHK | 729.9068 |  | 0 | 1094.8603 | N
6 |  | 2.5BHK | 793.1992 |  | 0 | 1189.7987 | N
Remarks:
1. Building 1 & 2 = Finishing work is pending. Few flats are occupied by tenants. Building 4 = Construction work was in process at the time of visit. Building 3 = All work completed. Please provide OC. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Open Balcony + C.B Area. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We have updated approved layout plan, floor plan (for Type A, B, C, D & G) & CC (on 30/12/2023). 9. As per RERA, completion period of project Prithvi Anand Kuber Complex is expired on 30/06/2025 but still project is under construction. 9. On Site, we meet Mr. Nitish : 9168038060.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Harshad Pawade |  | Report Prepared By : |  |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Prithvi Anand Kuber Complex
Google Map :
Bldg No.4
Bldg No.4
Bldg No.4

## 1%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 9
Particulars | total floor | 9
plinth | 10 | 10 | 100%
slab | 10 | 1 | 10% |  | Parking |  | Rate
Bricks | 9 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 9 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 9 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 9 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 9 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 4 | 0 | 0 | 0 | 0 | 0
RCC | 4 | 3 |  | Recommended |  | 30 | 3 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 14% | 33% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 2(C)%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 1 | 12.5% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5 | 0 | 0 | 0 | 0 | 0
RCC | 5 | 3.75 |  | Recommended |  | 30 | 3.75 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 15% | 33.75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 2(D)%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 1 | 12.5% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5 | 0 | 0 | 0 | 0 | 0
RCC | 5 | 3.75 |  | Recommended |  | 30 | 3.75 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 15% | 33.75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 3% (E)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 2 | 25% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 10 | 0 | 0 | 0 | 0 | 0
RCC | 10 | 7.5 |  | Recommended |  | 30 | 7.5 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 20% | 37.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 3% (F)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 2 | 25% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 10 | 0 | 0 | 0 | 0 | 0
RCC | 10 | 7.5 |  | Recommended |  | 30 | 7.5 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 20% | 37.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.51 | 9.6525 | CB | 2.75 | 1 | 2.75 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.39 | 2.75 | 6.5725 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.75 | 7.5625 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.75 | 2.44 | 6.71 | CB | 1.85 | 0.45 | 0.8325 |  |  | 0
|  |  |  | 0 | FB | 2.75 | 1 | 2.75 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.15 | 1.22 | 2.623 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.15 | 1.22 | 2.623 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 2.39 | 2.39 |  |  |  | 0 |  |  | 0
| passage2 | 1 | 2.75 | 2.75 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 440.07 | 40.8835 |  |  | 68.163 | 6.3325 |  | 0 | 0
|  |  | 508.233 | 47.216

## Note
Date |  | Description
21/12/2020. | Dhanashree | 1. Rate has not changed.

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
proptiger | Prithvi Regency | 1BHK | 239 | 346.55 | 4481.3158 | 1553000
proptiger | Prithvi Regency | 1BHK | 308 | 446.6 | 4480.5195 | 2001000
proptiger | Prithvi Regency | 1BHK | 311 | 450.95 | 4481.6499 | 2021000
proptiger | Prithvi Regency | 2BHK | 486 | 704.7 | 4481.3396 | 3158000
housing | Prithvi Regency | 1BHK | 239 | 346.55 | 4481.3158 | 1553000
housing | Prithvi Regency | 1BHK | 308 | 446.6 | 4480.5195 | 2001000
housing | Prithvi Regency | 1BHK | 311 | 450.95 | 4481.6499 | 2021000
housing | Prithvi Regency | 1BHK | 321 | 465.45 | 4481.6844 | 2086000
housing | Prithvi Regency | 2BHK | 486 | 704.7 | 4481.3396 | 3158000
Average |  |  | 0 | 0 | 4481.2062
Valuation Adopted |  |  |  |  | 4500