## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Sammaan Capital | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | SCL Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-09-01 | [6 empty] | Axis Sanpada |  |  | SCL Vashi
Name of the builder group |  |  |  | Joyville Shapoorji Housing Private Limited | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | Joyville Shapoorji Housing Private Limited | [9 empty] | SCL Thane
Name of the Project |  |  |  | Joyville Virar Phase 3 & 6 | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Aman Yadav 8850808009 | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | 9136919687 | [9 empty] | SCL Virar
Name / No of the Building |  |  |  | Joyville Virar Phase 3 : Palm Grove Joyville Virar Phase 6 : Palm Breeze & Palm Springs Joyville Virar Phase 6 : Palm
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Sale Plans | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | Phase 3 (Tower 2) = P99000018521 Phase 6 (Tower 1 & 4) = P99000031256 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Joyville Virar Phase 3 & 6, Survey No.296, 297, 298, 299, 303, 304, 324 & 390-B (Old) ; S.No. 296/1, 296/2, 296/3, 296/4, 296/5, 296/6, 296/7 & 296/8 ; S.No. 297/1, 297/2 & 297/3 ; S.No. 298/1, 298/2, 298/3, 298/4, 298/5 & 298/6 ; S.No. 299/1, 299/2 & 299/3 ; S.No. 304 ; S.No. 324/1, 324/2, 324/3 & 324/4 ; S.No. 390B/1 & 390B/2 (New), near Viva City A2, Viva City Road, , Bolinj, Virar (West), Vasai, Palghar - 401303. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 296, 297, 298, 299, 303, 304, 324 & 390-B (Old) ; S.No. 296/1, 296/2, 296/3, 296/4, 296/5, 296/6, 296/7 & 296/8 ; S.No. 297/1, 297/2 & 297/3 ; S.No. 298/1, 298/2, 298/3, 298/4, 298/5 & 298/6 ; S.No. 299/1, 299/2 & 299/3 ; S.No. 304 ; S.No. 324/1, 324/2, 324/3 & 324/4 ; S.No. 390B/1 & 390B/2 (New) | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | NA | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Viva City Road |  | Locality/Village |  | Bolinj | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Virar (West) |  | District |  | Palghar | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Vasai |  | Pin Code |  | 401303 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Viva City A2 |  | Distance from city centre: |  | 2.4 KM from Virar Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Stephen Menezes Marg
West | NA | Channel |  |  | Water Body
North | NA | 20.00 M.Wide D.P. Road |  |  | Viva City Road
South | NA | Other Plot |  |  | Pond
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.4388152,72.7933408
Location Link |  | https://maps.app.goo.gl/iGzFufQNq9e7fffD9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 66224.41
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.77262
Total FSI availaible for the project |  |  |  | 1.8726
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 124013.36
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-Virar City Municipal Corporation. (VVCMC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Tower 2 : Palm Grove
Layout Approval No |  | VVCMC/AMEND/BP/VP-0059/143/2019-20 |  |  | Dated | 2019-10-16 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | VVCMC/AMEND/BP/VP-0059/143/2019-20 |  |  | Dated | 2019-10-16 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Fire Noc No Valid Up to: |  |  |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | VVCMC/TP/OC/VP-0059/186/2023-24 Approved upto : Bldg No. T2 = Gr/St + 3 Podium + 1st to 20th Floor |  |  | Dated | 2024-02-16 | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Tower 4 : Palm Breeze
Layout Approval No |  | VVCMC/TP/AMEND/VP/0059/277/2021-22 |  |  | Dated | 2021-07-09 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | VVCMC/TP/AMEND/VP/0059/277/2021-22 |  |  | Dated | 2021-07-09 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | VVCMC/TP/RDP/VP-0059/277/2021-22 |  |  | Dated | 2021-07-09 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Building No. T2 = Stilt + P1 to P3 + 1st to 20th Floor (Total Built Up Area = 10925.01 Sq.M.) Building No.T4 = Gr/Stilt + 1st to 23rd Floor (Total Built Up Area = 12767.50 Sq.M.) | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
O. Certificate No.: |  | VVCMC/TP/OC/VP-0059/53/PO/2024/APL/00072 Approved upto : Building No.T4 = Gr/Stilt + 1st to 23rd Floor |  |  | Dated | 2024-12-03 | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Tower 1 : Palm Springs
Approved Floor plan No. |  | VVCMC/TP/AMEND/VP/0059/277/2021-22 |  |  | Dated | 2021-07-09 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | VVCMC/TP/RDP/VP-0059/277/2021-22 |  |  | Dated | 2021-07-09 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Building No. T1 = Stilt + P1 to P3 + 1st to 20th Floor (Residential = 380 Flats) (Total Built Up Area = 19531.29 Sq.M.) | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  |  |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | VVCMC/PO/2025/APL/00107 Approved upto : Bldg No. T1 = Gr/St + P1 to P3 + 1st to 20th Floor |  |  | Dated | 2025-03-27 | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) Fot Tower 1, 2 & 4 |  |  | 43223.8
Approved no of units |  |  | Flats - 564, Shops - 12
Approved no of Floors |  |  | Tower 1 : Palm Springs = Gr/St + P1 to P3 + 1st to 20th Floor Tower 4 : Palm Breeze = Gr/Stilt + 1st to 23rd Floor
Proposed no of Floors |  |  | Tower 1 : Palm Springs = Gr/St + P1 to P3 + 1st to 20th Floor
Tower 2 : Palm Grove = Stilt + P1 to P3 + 1st to 20th Floor
Tower 4 : Palm Breeze = Gr/Stilt + 1st to 23rd Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | Completed |  |  |  |  | As per RERA - 31/03/2025
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Goa Themed Club house, Skating Park, Kids Play Area, Senior Lounge, Swimming Pool, Banquet Hall, Indoor Games, Gym, Half Basketball Court, Jogging Track, Swing Plaza
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Tower 1 : Palm Springs = Gr/St + P1 to P3 + 1st to 20th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 100% |  | 100% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 20 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 20 | 100% |  |  |  |  | Plinth in process | 15
Possession |  | 20 | 100% |  |  |  |  | Plinth completed | 20
Construction details: |  | Tower 2 : Palm Grove = Stilt + P1 to P3 + 1st to 20th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 100% |  | 100% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 20 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 20 | 100% |  |  |  |  | Plinth in process | 15
Possession |  | 20 | 100% |  |  |  |  | Plinth completed | 20
Construction details: |  | Tower 4 : Palm Breeze = Gr/Stilt + 1st to 23rd Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 17.25
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Progress % |  | Podium |  | Disbursement % |  | Floors |  |  | Completed
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7400 |  |  |  | Rate Matched with Other Report (Aug 24 - 16429 - Joyville all wing) | [7 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000 |  |  |  | By Akash Mote ( Cost Sheet) | [7 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Corups Fund Charges |  |  |  |  | 25000 |  |  |  | On 09/10/2024
Advance Maintenance Charges |  |  |  |  | 107000
Society Formation Charges |  |  |  |  | 5000
Club House, Development Charges |  |  |  |  | 70000
Share Application Money Charges |  |  |  |  | 1000
Electric/Water Charges |  |  |  |  | 59000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Any Other Amenities Charges |  |  |  |  | 167274 | [11 empty] | 1600000 | 700000 | 600000
Recommended rate of Parking |  |  |  |  | 400000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 5920 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 12 |  | 2463.153 |  | 3817.8872
Total |  | 12 |  | 2463.153 |  | 3817.8872
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1 | Flats | 380 |  | 143432.4528 |  | 216043.0761
Tower 4 |  | 184 |  | 94078.4741 |  | 141117.7111
Total |  | 564 |  | 237510.9269 |  | 357160.7872
Grand Total |  | 576 |  | 239974.0799 |  | 360978.6744
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Tower 4 : Palm Breeze
Ground Floor for Meter Room, Society Office, Commercial & Parking | [8 empty] | 10.764
1 |  | Shop | 240.7605 | 0 | 240.7605 | 0 | 373.1788
2 |  | Shop | 152.7412 | 0 | 152.7412 | 0 | 236.7488
3 |  | Shop | 232.0266 | 0 | 232.0266 | 0 | 359.6413
4 |  | Shop | 207.9863 | 0 | 207.9863 | 0 | 322.3788
5 |  | Shop | 145.567 | 0 | 145.567 | 0 | 225.6288
6 |  | Shop | 186.8415 | 0 | 186.8415 | 0 | 289.6043
7 |  | Shop | 186.2861 | 0 | 186.2861 | 0 | 288.7434
8 |  | Shop | 140.7931 | 0 | 140.7931 | 0 | 218.2293
9 |  | Shop | 206.4202 | 0 | 206.4202 | 0 | 319.9512
10 |  | Shop | 369.6734 | 0 | 369.6734 | 0 | 572.9938
11 |  | Shop | 153.2966 | 0 | 153.2966 | 0 | 237.6097
12 |  | Shop | 240.7605 | 0 | 240.7605 | 0 | 373.1788
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No. T1 : Palm Springs
1st Floor for Residential | [8 empty] | 10.764
A1 |  | 1BHK | 388.1498 | 0 | 388.1498 | 67.0974 | 649.3222 | 36.058
A2 |  | 1BHK | 388.1498 | 0 | 388.1498 | 73.841 | 656.0658
A3 |  | 1BHK | 360.1634 | 0 | 360.1634 | 73.841 | 614.0862
A4 |  | 1BHK | 360.1634 | 0 | 360.1634 | 68.5667 | 608.8118
A5 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
A6 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
A7 |  | 1BHK | 392.1325 | 0 | 392.1325 | 75.7786 | 663.9773
A8 |  | 1BHK | 392.1325 | 0 | 392.1325 | 75.7786 | 663.9773
A9 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
A10 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
B1 |  | 1BHK | 360.1634 | 0 | 360.1634 | 73.841 | 614.0862
B2 |  | 1BHK | 360.1634 | 0 | 360.1634 | 73.841 | 614.0862
B3 |  | MP Room | 284.6002 | 0 | 284.6002 | 23.6808 | 450.581
B4 |  | 1BHK | 388.1498 | 0 | 388.1498 | 73.841 | 656.0658
B5 |  | 1BHK | 388.1498 | 0 | 388.1498 | 48.5241 | 630.7489
B6 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
B7 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
B8 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
B9 |  | 1BHK | 388.688 | 0 | 388.688 | 20.7207 | 603.7528
2nd to 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 20th Floor
A1 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
A2 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
A3 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
A4 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
A5 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
A6 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
A7 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 588.1988
A8 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 588.1988
A9 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
A10 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B1 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
B2 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
B3 |  | MP Room | 284.6002 | 0 | 284.6002 | 0 | 426.9002
B4 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
B5 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
B6 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B7 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B8 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B9 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
5th, 7th, 9th, 11th, 13th, 15th, 17th & 19th Floor (Part Refuge Area)
A1 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
A2 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
A3 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
A4 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
A5 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
A6 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
A7 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 588.1988
A8 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 588.1988
A9 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
A10 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B1 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
B2 |  | 1BHK | 360.1634 | 0 | 360.1634 | 0 | 540.2452
B3 |  | MP Room | 284.6002 | 0 | 284.6002 | 0 | 426.9002
B4 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
B5 |  | 1BHK | 388.1498 | 0 | 388.1498 | 0 | 582.2248
B6 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B7 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B8 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
B9 |  | 1BHK | 388.688 | 0 | 388.688 | 0 | 583.0321
Tower 4 : Palm Breeze
1st Floor for Residential
1 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
2 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
3 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
4 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
5 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
6 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
7 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
8 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
2nd to 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
1 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
2 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
3 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
4 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
5 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
6 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
7 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
8 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
8th, 10th, 12th, 14th, 16th, 18th, 20th & 22nd Floor (Part Refuge Area)
1 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
2 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
3 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
4 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
5 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
6 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
7 |  | 1BHK | 410.4919 | 0 | 410.4919 | 0 | 615.7378
8 |  | 2BHK | 612.1002 | 0 | 612.1002 | 0 | 918.1504
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Tower 1, 2 & 4 = All work Completed. OC Received. | [6 empty] | Tower 4 = Finishing work is in process.(Internal visit not allowed).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated Tower 4 Plans & CC (on 05/10/2024).
* | Please check for Environment Clearance Certificate.
* | We consider flat numbering from Sale plan. Attached Below.
* | As per Rera Tower 1 & 4 are registered but as per bank offices request we have done APF for Tower 4 only.
* | Recommended Rates / Other charges of the Property have been revised on 11/10/2024.
* | We have upadated approved OC for Tower 4 from RERA site on 14/04/2025
* | We have updated OC & approved 4th to 20th floor plans for Tower No. 1 (On 31/05/2025).
* | Please provide approved Ground Floor to 3rd podium Floor Plan for Tower No. 1 & legible layout plan.
* | Recommended Rates / Other charges of the Property have been revised on 11/10/2024 & 02/06/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Joyville Virar Phase 3 & 6
Layout :
Sale Plan :
Google Map :
Formulas:
Bolinj = [Bolinj, row above]
T4
T5
T1
T2
T3
T6
T7
Tower 4
Tower 5
Tower 1
Tower 2
Tower 3
Tower 6
Tower 7
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C54: SACHIN: Floor with height
Note on C56: SACHIN: Survey Nos.
Note on C58: SACHIN: Height from AMSL
Note on C71: SACHIN: Floor with height
Note on C73: SACHIN: Survey Nos.
Note on C75: SACHIN: Height from AMSL
Note on D78: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F162: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H201: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0