## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 03/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-03
Name of the builder group |  |  |  | Yash Development
Name of the builder company |  |  |  | Yash Development
Name of the Project |  |  |  | Daivi Eterneety
Provided Contact Details ( Name & Contact No.) |  |  |  | 8828997102
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Ms. Sejal : 7039538982.
Name / No of the Building |  |  |  | Shreeji Daivi (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | P51800029609
Project location details |  | Daivi Eterneety, CTS/Survey No.15/F, 15/G & 15/I, near M.K.N Bhatia High School & Jr. College, S.V.Road, Shri Punit Nagar, Kandivali, Borivali West, Borivali, Mumbai - 400092.
CTS/Survey No |  | 15/F, 15/G & 15/I
Locality |  | Shri Punit Nagar
Road |  | S.V.Road |  | Locality/Village |  | Kandivali
City |  | Borivali West |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400092
Nearby Landmark |  | M.K.N Bhatia High School & Jr. College |  | Distance from city centre: |  | 2 KM from Borivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Karishma Apartments
West | NA | NA |  |  | Dev Nagar Derasar Lane
North | NA | NA |  |  | Heena Tower
South | NA | NA |  |  | Internal road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.214603,72.84845
Location Link |  | https://goo.gl/maps/jj46oFMhaRL1SmnD6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3436.89
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 3.5026
Total FSI availaible for the project |  |  |  | 4.5026
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 15475.03
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mumbai Corporation Of Greater Mumbai (MCGM)
Layout Approval No |  | P-6360/2021/(15FAnd Other)/R/C Ward/Kandivali R/C/337/4/Amend |  |  | Dated | 08/11/2023.
Approved Floor plan No. |  | P-6360/2021/(15FAnd Other)/R/C Ward/Kandivali R/C/337/4/Amend |  |  | Dated | 08/11/2023.
Commencement-CC No Valid Up to: |  | P-6360/2021/(15F And Other)/R/C Ward/KANDIVALI R/C/FCC/7/Amend |  |  | Dated | 17/12/2024.
|  | This C.C. is extended further for work of building comprising of Wing ‘A’ & ‘B’ having 2 level Basement + Stilt + 1st to 3rd level Podium + 1st upper floor + 2nd to 21st upper floors by restricting C.C. of 22nd part upper floor as per approved amended plans dated 14.11.2024. |  |  | Valid Upto Date | 11/04/2025.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 15475.03
Approved no of units |  |  | Flats - 169
Approved no of Floors |  |  | Wing A & B = 2B + Gr/Stilt + 1st to 3rd Podium + 1st to 18th Floor
Proposed no of Floors |  |  | Wing A & B = 2B + Gr/Stilt + 1st to 3rd Podium + Amenity Floor + 1st to 31st Floor
Wing B = 2B + Gr/Stilt + 1st to 3rd Podium + Amenity Floor + 1st to 31st Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A & B = 2B + Gr/Stilt + 1st to 3rd Podium + Amenity Floor + 1st to 31st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 24 Slab, Brickwork upto 21 Floor, Internal Plaster upto 20 Floor, External Plaster upto 16.8 Floor, Flooring upto 12 Floor, Painting upto 6 Floor Completed | , RCC upto 24 Slab, Brickwork upto 21 Floor, Internal Plaster upto 20 Floor, External Plaster upto 16.8 Floor, Flooring upto 12 Floor, Painting upto 6 Floor
Basement | 2 | Ground | 1 | Podium | 3 | Floors | 31 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 24 Slab, Brickwork upto 21 Floor, Internal Plaster upto 20 Floor, External Plaster upto 16.8 Floor, Flooring upto 12 Floor, Painting upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.75
Excavation |  | 31 | 100% | 57.61% |  | 76.83% |  | Excavation in process | 15.5
Plinth |  | 31 | 100% |  |  |  |  | Excavation Completed | 31
RCC (Including podiums) |  | 24 | 68.57% |  |  |  |  | Footing in Process | 7.75
Brickwork | Brickwork & Internal Plaster | 21 | 67.74% |  |  |  |  | Footing Completed | 15.5
Internal Plaster | Brickwork & Internal Plaster | 20 | 64.52% |  |  |  |  | Basement 1 | 23.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.8 | 54.19% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 38.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 19.35% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 31
Construction details: |  | Wing B = 2B + Gr/Stilt + 1st to 3rd Podium + Amenity Floor + 1st to 31st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 8.45 Floor Completed | , RCC upto 17 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 8.45 Floor
Basement | 2 | Ground | 1 | Podium | 3 | Floors | 31 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 8.45 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.75
Excavation |  | 31 | 100% | 37.66% |  | 64.6% |  | Excavation in process | 15.5
Plinth |  | 31 | 100% |  |  |  |  | Excavation Completed | 31
RCC (Including podiums) |  | 17 | 48.57% |  |  |  |  | Footing in Process | 7.75
Brickwork | Brickwork & Internal Plaster | 13 | 41.94% |  |  |  |  | Footing Completed | 15.5
Internal Plaster | Brickwork & Internal Plaster | 9.75 | 31.45% |  |  |  |  | Basement 1 | 23.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8.45 | 27.26% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 31
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 16000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 12800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | rate sheet
Wing A |  | 77 |  | 87778.1596 |  | 140445.0553 |  |  | visitor | market
Wing B |  | 92 |  | 87937.3591 |  | 140699.7746 |  |  | 16500 | 15000
Total |  | 169 |  | 175715.5187 |  | 281144.8299 |  |  |  | 15200
Building details Floor Wise | [9 empty] | 15800
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A
2nd & 1st Basement Floor for Parking
Ground Floor for Parking
1st to 3rd Podium Floor for Parking
1st Floor for Fitness Center & Other Amenities
2nd Floor for residential (Part Refuge Area)
1 |  | 3BHK | 1100.4037 | 0 | 1760.646 | 2nd Floor for residential (Part Refuge Area) |  | 15902.6862 |  | 27290012.256
2 |  | 3BHK | 1076.2924 | 0 | 1722.0678 |  |  | 90.62 |  | 26692050.528
3 |  | Refuge Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 4BHK | 1750.657 | 0 | 2801.0511 |  |  | 15351.3799 |  | 43416292.608
3rd to 8th & 10th to 15th Floor | [9 empty] | 0
1 |  | 3BHK | 1100.4037 | 0 | 1760.646 | 3rd to 8th & 10th to 15th Floor |  | 14824.1047 | 15960.0515 | 27290012.256
2 |  | 3BHK | 1076.2924 | 0 | 1722.0678 |  |  | 15156.1979 |  | 26692050.528
3 |  | 2BHK | 830.4426 | 0 | 1328.7082 |  |  | 14224.3425 | 15302.0811 | 20594976.48
4 |  | 2BHK | 773.0705 | 0 | 1236.9128 |  |  | 15279.9781 | 15118.2852 | 19172147.904
5 |  | 4BHK | 1750.657 | 0 | 2801.0511 |  |  |  |  | 43416292.608
9th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 3BHK | 1100.4037 | 0 | 1760.646 | 9th Floor (Part Refuge Area) |  |  |  | 27290012.256
2 |  | 3BHK | 1076.2924 | 0 | 1722.0678 |  |  |  |  | 26692050.528
3 |  | Refuge Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 4BHK | 1750.657 | 0 | 2801.0511 |  |  |  |  | 43416292.608
16th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 3BHK | 1100.4037 | 0 | 1760.646 | 16th Floor (Part Refuge Area) |  |  |  | 27290012.256
2 |  | 3BHK | 1076.2924 | 0 | 1722.0678 |  |  |  |  | 26692050.528
3 |  | Refuge Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 4BHK | 1750.657 | 0 | 2801.0511 |  |  |  |  | 43416292.608
17th Floor | [9 empty] | 0
1 |  | 3BHK | 1152.8244 | 0 | 1844.519 | 17th Floor |  | 14150.0301 | 15234.3236 | 28590045.12
2 |  | 3BHK | 1107.6156 | 0 | 1772.185 |  |  | 14727.5824 |  | 27468866.88
3 |  | 2BHK | 830.4426 | 0 | 1328.7082 |  |  | 14224.3425 | 15302.0811 | 20594976.48
4 |  | 2BHK | 773.0705 | 0 | 1236.9128 |  |  | 15279.9781 | 15118.2852 | 19172147.904
5 |  | 4BHK | 1750.657 | 0 | 2801.0511 |  |  |  |  | 43416292.608
18th Floor (Part Terrace Area) | [9 empty] | 0
1 |  | 3BHK | 1152.8244 | 0 | 1844.519 | 18th Floor (Part Terrace Area) |  | 14150.0301 | 15234.3236 | 28590045.12
2 |  | 3BHK | 1107.6156 | 0 | 1772.185 |  |  | 14727.5824 |  | 27468866.88
3 |  | Terrace Area | [5 empty] | #DIV/0! | #DIV/0! | 0
4 | [7 empty] | #DIV/0! | #DIV/0! | 0
5 |  | 4BHK | 1750.657 | 0 | 2801.0511 |  |  |  |  | 43416292.608
Wing B | [9 empty] | 0
2nd & 1st Basement Floor for Parking | [9 empty] | 0
Ground Floor for Parking | [9 empty] | 0
1st to 3rd Podium Floor for Parking | [9 empty] | 0
1st Floor for Double Height Yogalaya & Other Amenities | [9 empty] | 0
2nd Floor for residential (Part Refuge Area) | [9 empty] | 0
1 |  | Void |  |  |  | 2nd Floor for residential (Part Refuge Area) |  |  |  | 0
2 | [9 empty] | 0
3 |  | Refuge Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 3BHK | 1107.508 | 0 | 1772.0127 |  |  |  |  | 27466197.408
6 |  | 2BHK | 875.9743 | 0 | 1401.5589 |  |  | 13484.9844 | 15482.7598 | 21724163.136
3rd to 8th & 10th to 15th Floor | [9 empty] | 0
1 |  | 3BHK | 1075.1083 | 0 | 1720.1733 | 3rd to 8th & 10th to 15th Floor |  |  |  | 26662686.336
2 |  | 3BHK | 1078.0146 | 0 | 1724.8234 |  |  |  |  | 26734762.08
3 |  | 2BHK | 761.6606 | 0 | 1218.657 |  |  |  |  | 18889183.872
4 |  | 2BHK | 744.9764 | 0 | 1191.9623 |  |  |  |  | 18475415.712
5 |  | 3BHK | 1107.508 | 0 | 1772.0127 |  |  | 14729.0138 |  | 27466197.408
6 |  | 2BHK | 875.9743 | 0 | 1401.5589 |  |  |  |  | 21724163.136
9th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 3BHK | 1075.1083 | 0 | 1720.1733 | 9th Floor (Part Refuge Area) |  |  |  | 26662686.336
2 |  | 3BHK | 1078.0146 | 0 | 1724.8234 |  |  |  |  | 26734762.08
3 |  | Refuge Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 3BHK | 1107.508 | 0 | 1772.0127 |  |  | 14729.0138 |  | 27466197.408
6 |  | 2BHK | 875.9743 | 0 | 1401.5589 |  |  |  |  | 21724163.136
16th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 3BHK | 1075.1083 | 0 | 1720.1733 | 16th Floor (Part Refuge Area) |  |  |  | 26662686.336
2 |  | 3BHK | 1078.0146 | 0 | 1724.8234 |  |  |  |  | 26734762.08
3 |  | Refuge Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 3BHK | 1107.508 | 0 | 1772.0127 |  |  |  |  | 27466197.408
6 |  | 2BHK | 875.9743 | 0 | 1401.5589 |  |  |  |  | 21724163.136
17th Floor | [9 empty] | 0
1 |  | 3BHK | 1112.1365 | 0 | 1779.4184 | 17th Floor |  | 4.064 |  | 27580984.704
2 |  | 3BHK | 1131.9422 | 0 | 1811.1076 |  |  |  |  | 28072167.552
3 |  | 2BHK | 761.6606 | 0 | 1218.657 |  |  |  |  | 18889183.872
4 |  | 2BHK | 744.9764 | 0 | 1191.9623 |  |  |  |  | 18475415.712
5 |  | 3BHK | 1107.508 | 0 | 1772.0127 |  |  | 4.416 |  | 27466197.408
6 |  | 2BHK | 875.9743 | 0 | 1401.5589 |  |  |  |  | 21724163.136
18th Floor (Part Terrace Area) | [9 empty] | 0
1 |  | 3BHK | 1112.1365 | 0 | 1779.4184 | 18th Floor (Part Terrace Area) |  | 4.064 |  | 27580984.704
2 |  | 3BHK | 1131.9422 | 0 | 1811.1076 |  |  |  |  | 28072167.552
3 |  | Terrace Area | [7 empty] | 0
4 | [9 empty] | 0
5 |  | 3BHK | 1107.508 | 0 | 1772.0127 |  |  | 4.416 |  | 27466197.408
6 |  | 2BHK | 875.9743 | 0 | 1401.5589 |  |  |  |  | 21724163.136
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor | [9 empty] | 0
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 0
3rd to 8th Floor | [9 empty] | 0
1 |  |  |  | 0 | 0 | 3rd to 8th Floor |  |  |  | 0
2 |  |  |  | 0 | 0 | 3rd to 8th Floor |  |  |  | 0
3 |  |  |  | 0 | 0 | 3rd to 8th Floor |  |  |  | 0
4 |  |  |  | 0 | 0 | 3rd to 8th Floor |  |  |  | 0
5 |  |  |  | 0 | 0 | 3rd to 8th Floor |  |  |  | 0
2nd & 5th Floor | [9 empty] | 0
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 0
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 0
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 0
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 0
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 0
Remarks: | [9 empty] | 0
* | Construction work is in process at the time of Visit. Internal photo was not allowed. (Slow Speed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised C.C. from MCGM (on 22/02/2024).
* | We have updated latest approved floor plans from MCGM Site & CC (On 06/04/2024).
* | We have updated latest CC from MCGM site (On 15/07/2024 & 14/01/2025).
* | Please Provide Revised approved plans.
* | Validity of CC is expired on 11/04/2025. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Rahul Salve |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Daivi Eterneety
Layout Plan :
Google Map :
Wing A
Wing A
Wing B
Wing A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted