## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 05/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-05
Name of the builder group |  |  |  | Inspira Realty And Infra Private Limited
Name of the builder company |  |  |  | Inspira Realty And Infra Private Limited
Name of the Project |  |  |  | Gurukripa
Provided Contact Details ( Name & Contact No.) |  |  |  | 9820038581/9833405230/ 9920975838/8655258030
Site Person - Contact Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Wing A & Wing B
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | P51800047648
Project location details |  | Gurukripa, CTS No.199, near Brihanmumbai Municipal Corporation School, Rd No. 2, Sindhi Society, Chembur, Chembur West, Kurla, Mumbai - 400071.
CTS No |  | 199
Locality |  | Sindhi Society
Road |  | Rd No. 2 |  | Locality/Village |  | Chembur
City |  | Chembur West |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400071
Nearby Landmark |  | Brihanmumbai Municipal Corporation School |  | Distance from city centre: |  | 3KM from Chembur Railway Station Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Viceroy Building
West | NA | NA |  |  | Rd/BMC School
North | NA | NA |  |  | Rd No. 2/Gurukrupa Apartments
South | NA | NA |  |  | Om Vaikunth Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.0492583,72.8882327
Location Link |  | https://goo.gl/maps/zstAytFvb8cogsge6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3445.9
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.9667
Total FSI availaible for the project |  |  |  | 2.9667
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10223
Total number of Buildings |  |  |  | 02 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | MCGM
Layout Approval No |  | CHE/ES/0339/M/337(NEW) |  |  | Dated | 2024-09-13
Approved Floor plan No. |  | CHE/ES/0339/M/337(NEW) |  |  | Dated | 2024-09-13
Commencement-CC No Valid Up to: |  | CHE/ES/0339/M/337(NEW)/FCC/2/Amend |  |  | Dated | 2024-07-09
|  | Full C.C for wing A and C.C upto 16th floor level for wing B (by restricting C.C. of Flat No.01 of 16th Floor and 17th floor for wing B , for availed installment facility as per policy) as per approved amended plans dated 28/06/2024 . |  |  | Valid Upto Date | 2025-03-21
Commencement-CC No Valid Up to: |  | CHE/ES/0339/M/337(NEW)/FCC/3/Amend |  |  | Dated | 2024-10-01
|  | Full C.C for wing A and C.C upto 18 th floor level for wing B (by restricting C.C. of Flat No.03 of 18th Floor and entire 19th floor for wing B , for availed installment facility as per policy) as per approved amended plans dated 20/09/2024 . |  |  | Valid Upto Date | 2025-09-30
Commencement-CC No Valid Up to: |  | CHE/ES/0339/M/337(NEW)/FCC/4/Amend |  |  | Dated | 2024-12-12
|  | Full C.C for wing A and Wing B as per approved amended plans dated 13/09/2024. |  |  | Valid Upto Date | 2026-03-21
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10223
Approved no of units |  |  | Flats - 165, Shop = 2
Approved no of Floors |  |  | A Wing = Gr + P1 to P3 + 4th to 19th Floor
Proposed no of Floors |  |  | A Wing = Gr + P1 to P3 + 4th to 19th Floor
B Wing = Gr + P1 to P3 + 4th to 19th Floor
C Wing = G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 30/09/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = Gr + P1 to P3 + 4th to 19th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 17 Floor, Flooring upto 12 Floor, Painting upto 10 Floor Completed | , External Plaster upto 17 Floor, Flooring upto 12 Floor, Painting upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 17 Floor, Flooring upto 12 Floor, Painting upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 82.89% |  | 92.63% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 20 | 100% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 89.47% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 63.16% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 52.63% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | B Wing = Gr + P1 to P3 + 4th to 19th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 13 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed | , External Plaster upto 13 Floor, Flooring upto 4 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 13 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 74.74% |  | 89.47% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 20 | 100% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 68.42% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 21.05% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 15.79% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 20000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 16000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 82 |  | 46916.401 |  | 72720.4215
B Wing |  | 83 |  | 52749.6278 |  | 81761.9232
Total |  | 165 |  | 99666.0288 |  | 154482.3446
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
A Wing
Ground Floor For Electric room, Comercial, Parking & Meter Room
1 |  | Shop | 583.947 | 0 | 583.947 | 0 | 905.1178
2 |  | Shop | 338.3125 | 0 | 338.3125 | 0 | 524.3844
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
A Wing
1st to 3rd Podium Floor For Parking
4th Floor For Residential (Part Fitness Centre Area) | [8 empty] | 10.764
1 |  | Fitness Centre Area
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | Fitness Centre Area
6
5th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
6th to 10th & 13th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
11th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
12th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 + 6 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
14th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 + 4 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
5 + 6 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
15th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 + 6 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
16th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 + 4 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
5 + 6 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
17th & 19th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 + 4 |  | 2.5BHK | 918.2768 | 0 | 918.2768 | 0 | 1423.3291
5 + 6 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
18th Floor
1 |  | 1BHK | 426.362 | 0 | 426.362 | 0 | 660.8612
2 |  | 2BHK | 804.609 | 0 | 804.609 | 0 | 1247.1439
3 + 4 |  | 2.5BHK | 918.2768 | 0 | 918.2768 | 0 | 1423.3291
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
B Wing
Ground Floor For Parking & Meter Room
1st to 3rd Podium Floor For Parking
4th Floor For Residential (Part Fitness Centre Area)
1 |  | 2BHK | 1036.6808 | 0 | 1036.6808 | 0 | 1606.8553
2 |  | fitness Centre Area & Society Office
3
4
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
5th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
6th to 10th & 13th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
11th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 + 4 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
12th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
14th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
6 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
15th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 + 4 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
5 + 6 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
16th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 + 4 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
5 + 6 |  | 2.5BHK | 918.2768 | 0 | 918.2768 | 0 | 1423.3291
17th & 19th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 + 4 |  | 2.5BHK | 893.0891 | 0 | 893.0891 | 0 | 1384.2881
5 + 6 |  | 2.5BHK | 918.2768 | 0 | 918.2768 | 0 | 1423.3291
18th Floor
1 |  | 2BHK | 802.9944 | 0 | 802.9944 | 0 | 1244.6413
2 |  | 2BHK | 800.0881 | 0 | 800.0881 | 0 | 1240.1366
3 |  | 1BHK | 426.5773 | 0 | 426.5773 | 0 | 661.1948
4 |  | 1BHK | 460.8068 | 0 | 460.8068 | 0 | 714.2506
5 + 6 |  | 2.5BHK | 918.2768 | 0 | 918.2768 | 0 | 1423.3291
Remarks:
* | Construction work is in process at the time of Visit.(Internal visit not allowed).
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated latest CC & Plans from MCGM site (On 27/09/2024).
* | We have updated revised approved CC from MCGM site on 18/12/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Gurukripa
Layout :
Google Map :
A Wing
A Wing
Gurukripa
B
A
A
B
B
Note on H147: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted