## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-04
Branch Name/ID |  | Mahindra Rural Housing Finance - Kalyan |  |  | Date & Time of Site Visit | 07/09/2025 @ 03:24 PM
Name of the person met at site & Contact No |  | Mr.Kiran 8888877555 Mr.Rohit 9930034003 |  |  | Date of Report Release | 08/09/2025
Project Details
Name of the project |  | Dheeraj Heights Phase 1
Address |  | Dheeraj Heights Phase 1, Survey No.11/2, 11/8, near The Polymath School, Deep Mauli Apartment Road, Narpoli, Bhiwandi (East), Bhiwandi, Thane - 421302. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 11/2, 11/8 | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Narpoli | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Deep Mauli Apartment Road | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Bhiwandi (East) | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Bhiwandi | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 421302 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51700051830 | [11 empty] | Mahad | Daund
Landmark |  | The Polymath School | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.277833,73.033944 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/tEcLMFxG63cQRdWu7 | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Sashwat Home | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | Ground Floor, Opp Polymath School, S No.11/2/1, 11/2/2, 11/8/2, Anjur Phata Road, Narpoli, Bhiwandi, Thane - 421302 | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | IDBI Bank Ltd. IFSC Code - IBKL0000430
Contact No. |  | Mr. Rohit 9923334003
Location of the project Municipal Limit : |  | Maharashtra Housing and Area Development Authority (MHADA)
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | PMAY Building No.1 & 2 |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | EWS Flat = 288 |  |  | Exposure Limit (Proposed) | 43.2
Approved No. of Floor |  | PMAY Building No.1 & 2 = Gr + 1st to 14th Floor
Proposed No. of Floor |  | PMAY Building No.1 & 2 = Gr + 1st to 14th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | S. No.11 H No.1 | Police Dept Reservation (295A) | 18.00 M Wide DP Road | Building No.3
|  | Physical on site |  | Open Plot/ Internal Road | Open Plot | Internal Road | Bldg No.3 (Dheeraj Heights Phase-2)
Verification of survey No. (Title document) |  | Survey No.11/8/2 (Old Survey No.11/8 Paiki)
Plot area mentioned in the sale deed (As per 7/12) |  | 8000 Sq.M |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 6130.61 Sq.M
Approach road |  | Yes, Approx 20ft
Connectivity |  | 1. 0.27Km From Polymath School. 2. 1.2Km From Saraswati English High School. 3. 1.8Km From Global Hospital. 4. 2.5Km From Sankalp Hospital. 5. 1.6Km From Gaondevi Mandir. 6. 2.0Km From Hanuman Mandir. 7. 1.0Km From Reliance Smart Point 8. 2.1Km From Ramdev Super Market 9. 1.3Km From Anjur Phata Bus Stop. 10. 2.1Km From Bhiwandi Road Railway Station.
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 6130.61
|  | Permissible FSI |  |  |  | 2.5
|  | Permissible TDR/Paid FSI |  |  |  | 0.60346
|  | Total FSI availaible for the project |  |  |  | 3.1035
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 19026.11
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19026.11
Building plan approvals - Approval No : |  | EE/BP/PMAY/A/MHADA/159/2023 Date - 21/02/2023
Building height / No. of Floors |  | PMAY Building No.1 = Gr + 1st to 14th Floor (Height = 43.80M) PMAY Building No.2 = Gr + 1st to 14th Floor (Height = 43.80M) | [5 empty] | 48.9
Construction/Building Permission |  | EE/BP/PMAY/A/MHADA/378/2023 Date: 15/05/2023 Valid Upto - This Plinth CC is issued for work upto plinth level only and same is valid up to 14/05/2024.
EE/BP/PMAY/A/MHADA/849/2023 Date :03/11/2023 Valid Upto - This further C.C is granted under Section 45 of MRTP Act 1966 for the Bldg No.1 & 2 upto Gr./Stilt + 1st to 14th floor of height 43.80m Comprising 288 EWS as per approved plan issued This office vide letter no.EE/BP/PMAY/A/MHADA/159/2023 Dtd.21/02/2023
NA / Land conversion |  | Name of the authority : |  | Tahsildar Bhiwandi
|  | Reference No : |  | Mhasul/K.1/Te.10/42B/Aakarni/SR-103/2022/2295 Date: 09/03/2022
|  | Validity & area : mentioned |  | Date - 09/03/2022 Area - 8000Sq.Mt. |  |  |  | Valid For one Year.
Other statutory permissions Fire NOC |  | BNSMNP/Fire/252/2023 Date :24/04/2023 Building No. 1 & 2 = Gr + 1st to 14th Floor (43.80 M Height)
CONSTRUCTION PROGRESS
Baseline start date |  | 07/07/2023 |  | Baseline finish date | 2025-12-29
Construction details:
PMAY Building No.1 = Gr + 1st to 14th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 12 Floor, Internal Plaster upto 10 Floor, External Plaster upto 4 Floor Completed
|  |  |  | 0 | 1 | 0 | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 12 Floor, Internal Plaster upto 10 Floor, External Plaster upto 4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 3.5
Excavation |  | 0% |  | 14 | 100% | 67.86% |  | Excavation in process | 7
Plinth |  | 10% |  | 14 | 100% |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 40% |  | 15 | 100% |  |  | Footing in Process | 3.5
Brickwork |  | 15% |  | 12 | 85.71% |  |  | Footing Completed | 7
Internal Plaster |  | 5% |  | 10 | 71.43% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 4 | 28.57% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 10.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 14
PMAY Building No.2 = Gr + 1st to 14th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 12 Floor Completed
|  |  |  | 0 | 1 | 0 | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 12 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 3.5
Excavation |  | 0% |  | 14 | 100% | 69.29% |  | Excavation in process | 7
Plinth |  | 10% |  | 14 | 100% |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 40% |  | 15 | 100% |  |  | Footing in Process | 3.5
Brickwork |  | 15% |  | 14 | 100% |  |  | Footing Completed | 7
Internal Plaster |  | 5% |  | 12 | 85.71% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 10.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 14
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
PMAY Building No.1 |  | 144 |  | 49761.8105 |  | 74642.7158
PMAY Building No.2 |  | 144 |  | 49761.8105 |  | 74642.7158
Total |  | 288 |  | 99523.6211 |  | 149285.4316
Grand Total |  | 288 |  | 99523.6211 |  | 149285.4316
BUILDING / BLOCK - Configuration Details
Details of Residential in Building | [7 empty] | & Commercials |  | 10.764
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
PMAY Building No.1
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | FB Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
PMAY Building No.1
Ground Floor For Residential, Entrance Lobby, Meter Room, Society Office & Parking
1 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 | 28.3972
2 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966
3 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966
4 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966
5 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966
6 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
1st to 7th, 9th to 12th & 14th Floor For Residential
1 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
2 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
3 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
4 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
5 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
6 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
7 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
8 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
9 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
10 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
11 |  | 1BHK | 321.1978 |  | 321.1978 |  | 481.7966
12 |  | 1BHK | 321.1978 |  | 321.1978 |  | 481.7966
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
2 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
3 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
4 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
5 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
6 |  | - | Refuge Area |  |  |  | -
7 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
8 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
9 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
10 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
11 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
12 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
PMAY Building No.2
Ground Floor For Residential, Entrance Lobby, Meter Room, Society Office & Parking | [8 empty] | 3200
1 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 | 28.3972 | 1541749.248 | 5220
2 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 |  | 1541749.248
3 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 |  | 1541749.248
4 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 |  | 1541749.248
5 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 |  | 1541749.248
6 |  | 1BHK | 321.1978 | 0 | 321.1978 | 0 | 481.7966 |  | 1541749.248
1st to 7th, 9th to 12th & 14th Floor | [8 empty] | 0
1 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
2 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
3 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
4 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
5 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
6 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
7 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
8 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 |  | 1663813.008
9 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
10 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
2 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
3 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
4 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
5 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
6 |  | - | Refuge Area |  |  |  | -
7 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
8 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416 | 3269.5982
9 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
10 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
11 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
12 |  | 1BHK | 321.1978 | 25.4299 | 346.6277 | 0 | 519.9416
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3200
Recommended of Parking ( If Available) |  |  |  |  | 1,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. (labour found)
2 | AAC Block, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | 3 to 4 Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + FB Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr.Kiran 8888877555 & Mr.Rohit 9930034003
11 | We have updated Fire Noc on 31/07/2024.
12 | The project banner shows an incorrect RERA No. (P517000518530), but according to the RERA site, Dheeraj Heights Phase 1 has RERA No. P51700051830.
Photographs Of Property : |  | Dheeraj Heights Phase 1
Remark No. 12 :
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mangesh Laxman Bapardekar |  | Authorized Signatory Name & Seal of the agency
Building No.1
Building No.2
Phase 1
Building No.3
Phase 2
Dheeraj Heights Phase 1
Dheeraj Heights Phase 2
Bldg No. 02
Bldg No. 01
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C55: RERA Start date
Note on F55: RERA completion date
Note on H87: if multiple buildings are in project and are connected internally
Note on C89: AAC Block or Brick
Note on H91: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3