## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-04
Branch Name/ID |  | Mahindra Rural Housing Finance - Virar |  |  | Date & Time of Site Visit | 05/09/2025 at 13:41
Name of the person met at site & Contact No |  | Mr. Usman 9323281903 |  |  | Date of Report Release | 06/09/2025
Project Details
Name of the project |  | Wonder Park | [6 empty] | As per visitor, Wonder Park is Building No. 2
Address |  | Wonder Park, Survey No.115, H.No. B, Plot No. 3, Old S.No. 115, H.No. 6(P), 8/1A(P), 8/2, 9, 10B(+9P), 11/C(P), B/2(P), 13/3(P), 18(P), 19(P) & S.No. 116, H.No. 1A, 1B1, C, 2(P), 1E(P), 8(P), near Neminath Hiloni Heights, Gokhiware Road, Gokhiware, Vasai East, Vasai, Palghar - 401208. | [6 empty] | Wonder infinity is bldg no. 1 also RERA is different |  |  | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 115, H.No. B, Plot No. 3, Old S.No. 115, H.No. 6(P), 8/1A(P), 8/2, 9, 10B(+9P), 11/C(P), B/2(P), 13/3(P), 18(P), 19(P) & S.No. 116, H.No. 1A, 1B1, C, 2(P), 1E(P), 8(P) | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Gokhiware | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Gokhiware Road | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Vasai East | [9 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Vasai | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Palghar | [9 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 401208 | [9 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P99000029971 | [12 empty] | Mahad | Daund
Landmark |  | Neminath Hiloni Heights | [12 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.4044829,72.8467184 | [9 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/2KV9ZUV1tpxBQjka8 | [12 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Wonder Developers | [12 empty] | Mahasala | Bhor
Office address (agreement) |  | Shop No.1 Wonder Park S.No.115 Plot No. B Gokhiware Vasai East Dist Palghar-401208 | [12 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [12 empty] | Murud | Velhe
Builder Bank Details |  | Bassein Catholic Cooperative Bank Limited IFSC Code : BACB0000018
Contact No. |  | Ms. Monika Singh /Mr. Govinda Goswami 8483826580
Location of the project Municipal Limit : |  | Vasai - Virar City Municipal Corporation. (VVCMC)
Project Type (Apartments/Plot/ Combined) |  | Apartments + Shop
No of Wings / Buildings |  | Building No. 2 (Wing A & B) |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flats = 294, Shop = 14, Office = 09 |  |  | Exposure Limit (Proposed) | 44.1
Approved No. of Floor |  | Building No. 2 = Gr. + 1st to 18th Floor
Proposed No. of Floor |  | Building No. 2 = Gr. + 1st to 18th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Other Plot | Other Plot | Other Plot | 12 M W Internal Road
|  | Physical on site |  | Shebro complex | Guardwel’s Horizon | Open Plot | Internal Road
Verification of survey No. (Title document) |  | Survey No. 115, H.No. B, Plot No. 3
Plot area mentioned in the sale deed (As per 7/12) |  | 7785 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 7378.78
Approach road |  | Yes, Approx 130ft
Connectivity |  | 1. 0.55Km from St. Joseph English High School 2. 1.4Km from Holy Family Convent High School 3. 0.45Km from Platinum Hospital Vasai 4. 0.65Km from Mediprime Multi-speciality Hospital 5. 0.85Km from Vinayak Super Market 6. 1.20Km from Shree Balaji super market 7. 0.70Km from Shree Ganesh Mandir 8. 0.65Km from Gokhiware Shiv Mandir 9. 0.18Km from Father Wadi Naka Bus stop 10. 4.60Km from Vasai Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 7378.78
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 2.527
|  | Total FSI availaible for the project |  |  |  | 3.627
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 29987.64
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 26762.59
Building plan approvals - Approval No : |  | VVCMC/TP/AMEND/VP/632B/380/2023-24 |  |  |  | Date | 2024-02-20
Building height / No. of Floors |  | Building No. 2 = Gr. + 1st to 18th Floor (Total Height = 56.96 M)
Construction/Building Permission Valid Upto |  | VVCMC/TP/RDP/VP-632B/380/2023-24 Building 2 = Stilt/Gr. + 1st to 18th Floor (Total Builtup Area = 26762.59 Mtrs.) |  |  |  | Date | 2024-02-20
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: | [5 empty] | Date
Environmental Clearance Certificate (EC) No Valid Up for: | [5 empty] | Date
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 2021-07-18 |  | Baseline finish date |  | 2028-09-30 |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 12 Floor, Painting upto 6 Floor Completed
Construction details:
Building No. 2 (Wing A & B) = Gr + 1st + 18th Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 18 | Piling Work in process | 4.5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 12 Floor, Painting upto 6 Floor Completed | [5 empty] | Excavation in process | 9
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 18
Excavation |  | 0% |  | 18 | 100% | 83.33% |  | Footing in Process | 4.5
Plinth |  | 10% |  | 18 | 100% |  |  | Footing Completed | 9
RCC (Including podiums) |  | 40% |  | 19 | 100% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 18 | 100% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 18 | 100% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 18 | 100% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 12 | 66.67% |  |  | Plinth in process | 13.5
Painting & Wooden |  | 5% |  | 6 | 33.33% |  |  | Plinth completed | 18
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
Construction details:
Building No. 2 = Gr + 1st + 18th Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 18 | Piling Work in process | 4.5
Stage of construction: |  | 0 | [5 empty] | Excavation in process | 9
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 18
Excavation |  | 0% |  | 0 | 0% | 0% |  | Footing in Process | 4.5
Plinth |  | 10% |  | 0 | 0% |  |  | Footing Completed | 9
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 13.5
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 18
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 2 (Wing A + B) | Shop | 14 |  | 3033.5105 |  | 4701.9412
| Office | 9 |  | 3986.6734 |  | 6179.3438
Total |  | 9 |  | 3986.6734 |  | 6179.3438
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 2 | Wing A | 156 |  | 71385.1527 |  | 107337.249
| Wing B | 138 |  | 68457.9367 |  | 102930.0638
Total |  | 294 |  | 139843.0894 |  | 210267.3128
Grand Total |  | 303 |  | 143829.7628 |  | 216446.6567
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
55%
Building No.2
Wing A + B
Ground Floor For Commercial, Entrance Lobby & Parking
1 |  | Shop | 305.59 | 0 | 305.59 | 0 | 473.6644 |  |  | 10.764
2 |  | Shop | 163.0746 | 0 | 163.0746 | 0 | 252.7656
3 |  | Shop | 163.0746 | 0 | 163.0746 | 0 | 252.7656
4 |  | Shop | 225.2905 | 0 | 225.2905 | 0 | 349.2003
5 |  | Shop | 251.9852 | 0 | 251.9852 | 0 | 390.5771
6 |  | Shop | 209.2522 | 0 | 209.2522 | 0 | 324.3408
7 |  | Shop | 209.2522 | 0 | 209.2522 | 0 | 324.3408
8 |  | Shop | 209.2522 | 0 | 209.2522 | 0 | 324.3408
9 |  | Shop | 209.2522 | 0 | 209.2522 | 0 | 324.3408
10 |  | Shop | 251.9852 | 0 | 251.9852 | 0 | 390.5771
11 |  | Shop | 225.2905 | 0 | 225.2905 | 0 | 349.2003
12 |  | Shop | 163.0746 | 0 | 163.0746 | 0 | 252.7656
13 |  | Shop | 163.0746 | 0 | 163.0746 | 0 | 252.7656
14 |  | Shop | 284.062 | 0 | 284.062 | 0 | 440.296
1st Floor For Commercial & Residential
1 |  | Office | 484.0571 | 0 | 484.0571 | 0 | 750.2885
2 |  | Office | 555.9606 | 0 | 555.9606 | 0 | 861.7389 | 51.3785
3 |  | Office | 555.9606 | 0 | 555.9606 | 0 | 861.7389 | 51.3785
4 |  | Office | 315.1807 | 0 | 315.1807 | 0 | 488.5301
5 |  | Office | 555.9606 | 0 | 555.9606 | 0 | 861.7389
6 |  | Office | 296.01 | 0 | 296.01 | 0 | 458.8155
7 |  | Office | 316.1387 | 0 | 316.1387 | 0 | 490.015
8 |  | Office | 453.7026 | 0 | 453.7026 | 0 | 703.239
9 |  | Office | 453.7026 | 0 | 453.7026 | 0 | 703.239
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Building No.2
Wing A
1st Floor For Residential & Commercial | [10 empty] | 10.764
1 |  | - | Commercial
2 |  | -
3 |  | -
4 |  | -
5 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167 | 26.9225
6 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167
7 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561
8 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561
9 |  | 1BHK | 280.5098 | 161.6753 | 442.1851 | 0 | 663.2777 | 25.71
2nd Floor For Residential
1 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349 |  |  | 3806742.42
2 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 97.2527 | 753.5876 |  |  | 4370808.312
3 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 97.2527 | 753.5876 |  |  | 4370808.312
4 |  | 1BHK | 287.1835 | 204.0047 | 491.1882 | 65.0146 | 801.7969 |  |  | 4650422.049
5 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167 |  |  | 4115776.86
6 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167 |  |  | 4115776.86
7 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561 |  |  | 4012765.38
8 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561 |  |  | 4012765.38
9 |  | 1BHK | 280.5098 | 161.6753 | 442.1851 | 0 | 663.2777 |  |  | 3847010.544
3rd to 7th, 9th to 12th & 14th to 18th Floor For Residential
1 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
2 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
3 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
4 |  | 1BHK | 287.1835 | 204.0047 | 491.1882 | 0 | 736.7823
5 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167
6 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167
7 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561
8 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561 | 6359.704
9 |  | 1BHK | 280.5098 | 161.6753 | 442.1851 | 0 | 663.2777
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
2 |  | - | Refuge Area
3 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
4 |  | 1BHK | 287.1835 | 204.0047 | 491.1882 | 0 | 736.7823 | 6175.5009
5 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167
6 |  | 1BHK | 297.8399 | 175.2379 | 473.0778 | 0 | 709.6167
7 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561 | 6504.2427
8 |  | 1BHK | 290.8433 | 170.3941 | 461.2374 | 0 | 691.8561
9 |  | 1BHK | 280.5098 | 161.6753 | 442.1851 | 0 | 663.2777
Wing B
1st Floor For Residential & Commercial
1 |  | 1BHK | 280.4022 | 161.6753 | 442.0775 | 0 | 663.1162
2 |  | 1BHK | 278.0341 | 161.6753 | 439.7094 | 0 | 659.5641
3 |  | 2BHK | 491.6995 | 192.4065 | 684.106 | 0 | 1026.159 | 45.3425
4 |  | 1BHK | 276.9577 | 163.4783 | 440.436 | 0 | 660.654
5 |  | - | Commercial
6 |  | -
7 |  | -
8 |  | -
2nd Floor For Residential
1 |  | 1BHK | 280.4022 | 161.6753 | 442.0775 | 0 | 663.1162 |  | 3846074.076
2 |  | 1BHK | 278.0341 | 161.6753 | 439.7094 | 0 | 659.5641 |  | 3825471.78
3 |  | 2BHK | 491.6995 | 192.4065 | 684.106 | 0 | 1026.159 |  | 5951722.374
4 |  | 1BHK | 276.9577 | 163.4783 | 440.436 | 0 | 660.654 |  | 3831792.939
5 |  | 2BHK | 486.7481 | 182.3152 | 669.0633 | 48.6533 | 1052.2483 |  | 6103039.995
6 |  | 1BHK | 278.0341 | 159.0919 | 437.126 | 97.2527 | 752.9418 |  | 4367062.44
7 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 97.2527 | 753.5876 |  | 4370808.312
8 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349 |  | 3806742.42
3rd to 7th, 9th to 12th & 14th to 18th Floor For Residential
1 |  | 1BHK | 280.4022 | 161.6753 | 442.0775 | 0 | 663.1162
2 |  | 1BHK | 278.0341 | 161.6753 | 439.7094 | 0 | 659.5641
3 |  | 2BHK | 491.6995 | 192.4065 | 684.106 | 0 | 1026.159 | 6792.3195
4 |  | 1BHK | 276.9577 | 163.4783 | 440.436 | 0 | 660.654
5 |  | 2BHK | 486.7481 | 182.3152 | 669.0633 | 0 | 1003.595
6 |  | 1BHK | 278.0341 | 159.0919 | 437.126 | 0 | 655.6891
7 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
8 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
8th & 13th Floor For Residential (Part Refuge Area)
1 |  | 1BHK | 280.4022 | 161.6753 | 442.0775 | 0 | 663.1162
2 |  | 1BHK | 278.0341 | 161.6753 | 439.7094 | 0 | 659.5641
3 |  | 2BHK | 491.6995 | 192.4065 | 684.106 | 0 | 1026.159
4 |  | 1BHK | 276.9577 | 163.4783 | 440.436 | 0 | 660.654
5 |  | - | Refuge Area
6 |  | 1BHK | 278.0341 | 159.0919 | 437.126 | 0 | 655.6891
7 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
8 |  | 1BHK | 275.8813 | 161.6753 | 437.5566 | 0 | 656.3349
Ground Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
1st Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5800
Recommended of Parking ( If Available) |  |  |  |  | 2,50,000/-
REMARKS ON RECOMMENDATION
1 | Building No. 2 = Construction work is in process at the time of Visit (labour found) Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + F.B Area.
5 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
6 | We have considered rate by verifying it from market inquire.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | Car parking is subjected to authentic documentation.
9 | On Site, we meet Mr. Usman 9323281903
10 | Layout consist Building No. 1, 2 & CFC Building. But As per site met person (Mr. Usman 9323281903), Wonder Infinity (RERA no. P99000077174) consist of Building No. 1 . we have drafted APF Report for Wonder Park (RERA no. P99000029971) Building No. 2. | [7 empty] | But approved plans of Building no. 1 are not legible & CFC Building plans are not provided. So we have done drafting APF for Building No. 2
11 | Please check for Environmental Clearance Certificate & Fire Noc.
Photographs Of Property : |  | Wonder Park
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Navnath Bhatkar |  | Authorized Signatory Name & Seal of the agency
Bldg No.2
Bldg 2
Bldg 1
CFC Bldg
Bldg 2A
Bldg 2B
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C60: RERA Start date
Note on H93: if multiple buildings are in project and are connected internally
Note on C95: AAC Block or Brick
Note on H97: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3