## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-07
Name of the builder group |  |  |  | Riddhi Siddhi Enterprises
Name of the builder company |  |  |  | Riddhi Siddhi Enterprises
Name of the Project |  |  |  | Atlantic
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Karan – 8412992233
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Karan : 8412992233 & Mr. Ashish : 9571851172
Name / No of the Building |  |  |  | Building Type A (Wing A & B) Building Type B Building Type C
Docouments Provided |  |  |  | Approved Plans, CC & Fire Noc
RERA No. |  |  |  | P51700034411
Project location details |  | Atlantic, Survey No.251 H.No.3(Pt), 4(Pt) S.No.252 H.No.2(Pt) & S.No.261 H.No.1(Pt), near Kon Gaon Police Station / Chamunda apartment, Kalyan Bhiwandi Road, Jambhulwadi, Kon, Kalyan West, Bhiwandi, Thane - 421311.
Survey No |  | 251 H.No.3(Pt), 4(Pt) S.No.252 H.No.2(Pt) & S.No.261 H.No.1(Pt)
Locality |  | Jambhulwadi
Road |  | Kalyan Bhiwandi Road |  | Locality/Village |  | Kon
City |  | Kalyan West |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421311
Nearby Landmark |  | Kon Gaon Police Station / Chamunda apartment |  | Distance from city centre: |  | 3.3KM from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Plot No.254 |  |  | Chawl
West | NA | Plot No. 266 |  |  | Houses |  |  | Kon Gaon Police Station
North | NA | Plot No. 260/262 |  |  | Open Plot
South | NA | Bhiwandi Kalyan Road |  |  | Kalyan Bhiwandi Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.246239,73.109895
Location Link |  | https://goo.gl/maps/9XLXTp93iU3NWHo66
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5847.03
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1371
Total FSI availaible for the project |  |  |  | 2.2371
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13080.19 |  |  |  | 13227.02
Total number of Buildings |  |  |  | 03 Building - 4 Wings |  |  |  | 03 Building - 4 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mumbai Metropolitan Region Development Authority
Layout Approval No |  | SROT/BSNA/2501/BP/KON-57/Amended CC/307/2023 |  |  | Dated | 2023-02-24 |  | SROT/BSNA/2501/BP/KON-57/CC/460/2021
Approved Floor plan No. |  | SROT/BSNA/2501/BP/KON-57/Amended CC/307/2023 |  |  | Dated | 2023-02-24
Commencement-CC No Valid Up to: |  | SROT/BSNA/2501/BP/KON-57/Amended CC/307/2023 |  |  | Dated | 2023-02-24
|  | Poposed Built up Area = 13080.19 sq.m | [5 empty] | Type A - Wing A = G + 1st to 7th Floor Type A - Wing B = G + 1st to 12th Floor Type B & C = G + 1st to 12th Floor
Fire Noc Details Valid Up to: |  | MFS/51/2022/379 |  |  | Dated | 2022-05-07
Bldg Type A - Wing A = Gr/Mezzanine + 1st Floor (Height - 11.17m) Bldg Type A - Wing B = Gr/St. + 1st to 18th Floor (Height - 58.20m) Bldg Type B & C = Gr/St + 1st to 17th Floor (Height - 53.70m)
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 13080.19
Approved no of units |  |  | Flats - 245, Store - 8
Approved no of Floors |  |  | Building Type A - Wing A = Gr + Mezzanine + 1st Floor Building Type A - Wing B = Gr/St. + 1st to 18th Floor Building Type B = Gr/St. + 1st to 17th Floor Building Type C = Gr/St. + 1st to 4th Floor
Proposed no of Floors |  |  | Building Type A - Wing A = Gr + Mezzanine + 1st Floor
|  |  | Building Type A - Wing B = Gr/St + 1st to 18th Floor |  |  |  |  | Fire Noc
Building Type B = Gr/St + 1st to 17th Floor
Building Type C = Gr/St. + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building Type A - Wing A = Gr + Mezzanine + 1st Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 0.5 Floor, Painting upto 0.5 Floor Completed | , Flooring upto 0.5 Floor, Painting upto 0.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 0.5 Floor, Painting upto 0.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 82.5% |  | 92.5% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 2 | 100% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 1 | 100% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 1 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0.5 | 50% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0.5 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Construction details: |  | Building Type A - Wing B = Gr/St + 1st to 18th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 10 Floor, Internal Plaster upto 4 Floor Completed | , RCC upto 17 Slab, Brickwork upto 10 Floor, Internal Plaster upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 18 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 10 Floor, Internal Plaster upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 51.62% |  | 75.73% |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 17 | 89.47% |  |  |  |  | Footing in Process | 4.5
Brickwork | Brickwork & Internal Plaster | 10 | 55.56% |  |  |  |  | Footing Completed | 9
Internal Plaster | Brickwork & Internal Plaster | 4 | 22.22% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 13.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Construction details: |  | Type B = G + 1st to 17th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 15 Floor, Internal Plaster upto 4 Floor Completed | , RCC upto 17 Slab, Brickwork upto 15 Floor, Internal Plaster upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 17 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 15 Floor, Internal Plaster upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.25
Excavation |  | 17 | 100% | 56.16% |  | 78.92% |  | Excavation in process | 8.5
Plinth |  | 17 | 100% |  |  |  |  | Excavation Completed | 17
RCC (Including podiums) |  | 17 | 94.44% |  |  |  |  | Footing in Process | 4.25
Brickwork | Brickwork & Internal Plaster | 15 | 88.24% |  |  |  |  | Footing Completed | 8.5
Internal Plaster | Brickwork & Internal Plaster | 4 | 23.53% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 17
Construction details: |  | Building Type C = Gr/St. + 1st to 4th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6200 |  |  |  | visitor | online
Recommended rate of the Ground + Mezzanine Floor Store Per Sq. Ft. |  |  |  |  | 12000
Recommended rate of the 1st Floor Store Per Sq. Ft. |  |  |  |  | 10000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000 |  |  |  | 6200 | 6200
Distressed valuation of the Property |  |  |  |  | 4960 |  |  |  | 7100
Commercial Area Details :(Store)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A -Wing A |  | 8 |  | 5730.323 |  | 10969.5278
Total |  | 8 |  | 5730.323 |  | 10969.5278
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 165269.3823 | 108596.8927
Type A- Wing B |  | 105 |  | 44848.0176 |  | 67272.0264
Type B |  | 100 |  | 42588.358 |  | 63882.537
Type C |  | 40 |  | 15430.194 |  | 23145.291
Total |  | 245 |  | 102866.5696 |  | 154299.8545
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Mezzanine area | Saleable area Loading : | Floor
55%
Building Type A (Wing A)
Ground (3.85m height) + Mezzanine Floor (3.55m height) For Commercial & Parking
1 |  | Store | 755.2022 | 336.6979 | 1692.4452 | Ground (3.85m height) + Mezzanine Floor (3.55m height) For Commercial & Parking |  | 103.7356
2 |  | Store | 755.2022 | 336.6979 | 1692.4452
3 |  | Store | 755.2022 | 336.6979 | 1692.4452
4 |  | Store | 755.2022 | 336.6979 | 1692.4452
1st Floor (4.3mtr height) For Commercial
1 |  | Store | 677.3785 | 0 | 1049.9367 | 1st Floor (4.3mtr height) For Commercial
2 |  | Store | 677.3785 | 0 | 1049.9367
3 |  | Store | 677.3785 | 0 | 1049.9367
4 |  | Store | 677.3785 | 0 | 1049.9367
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building Type A (Wing B)
Stilt Floor For Driver's Room, Society Office, Electrical Car With Charging Point & Parking | [9 empty] | 5.7225
1st Floor For Residential | [8 empty] | 10.764 | 5.7225
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 1st Floor For Residential |  | 30.4717 | 54.8352 | 5.835
2 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.7225
3 |  | 1BHK | 424.1554 | 0 | 636.2331 |  |  |  | 54.8352 | 5.7225
4 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.835
5 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  | 54.8352
6 |  | 1BHK | 424.1554 | 0 | 636.2331
2nd Floor | [8 empty] | 10.764 | 5.7225
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 2nd Floor |  | 30.4717 | 54.8352 | 5.835
2 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.7225
3 |  | 1BHK | 424.1554 | 0 | 636.2331 |  |  |  | 54.8352 | 5.7225
4 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.835
5 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  | 54.8352
6 |  | 1BHK | 424.1554 | 0 | 636.2331
3rd Floor | [8 empty] | 10.764 | 5.7225
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 3rd Floor |  | 30.4717 | 54.8352 | 5.835
2 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.7225
3 |  | 1BHK | 424.1554 | 0 | 636.2331 |  |  |  | 54.8352 | 5.7225
4 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.835
5 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  | 54.8352
6 |  | 1BHK | 424.1554 | 0 | 636.2331
4th to 7th, 9th to 12th & 14th to 17th Floor | [7 empty] | 12 | 10.764 | 5.7225
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 4th to 7th, 9th to 12th & 14th to 17th Floor |  | 30.4717 | 54.8352 | 5.835
2 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.7225
3 |  | 1BHK | 424.1554 | 0 | 636.2331 |  |  |  | 54.8352 | 5.7225
4 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.835
5 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  | 54.8352
6 |  | 1BHK | 424.1554 | 0 | 636.2331
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3 | 10.764 | 5.7225
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 8th, 13th & 18th Floor (Part Refuge Area) |  | 30.4717 | 54.8352 | 5.835
2 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.7225
3 |  | Refuge Area | [6 empty] | 54.8352 | 5.7225
4 |  | 2BHK | 568.2854 | 0 | 852.4281 |  |  |  |  | 5.835
5 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  | 54.8352
6 |  | 1BHK | 424.1554 | 0 | 636.2331
Building Type B | [10 empty] | 83.7977
Stilt Floor For Parking
1st to 7th & 9th to 12th & 14th to 17th Floor For Residential | [7 empty] | 15
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 1st to 7th & 9th to 12th & 14th to 17th Floor For Residential
2 |  | 1BHK | 422.4063 | 0 | 633.6094 | 1st to 7th & 9th to 12th & 14th to 17th Floor For Residential
3 |  | 1BHK | 424.1554 | 0 | 636.2331 | 1st to 7th & 9th to 12th & 14th to 17th Floor For Residential
4 |  | 1BHK | 422.4063 | 0 | 633.6094 | 1st to 7th & 9th to 12th & 14th to 17th Floor For Residential
5 |  | 1BHK | 422.4063 | 0 | 633.6094 | 1st to 7th & 9th to 12th & 14th to 17th Floor For Residential
6 |  | 1BHK | 424.1554 | 0 | 636.2331 | 1st to 7th & 9th to 12th & 14th to 17th Floor For Residential
8th & 13th Floor (Part Refuge Area) | [7 empty] | 2 | 10.764 | 5.7225
1 |  | 1BHK | 422.4063 | 0 | 633.6094 | 8th & 13th Floor (Part Refuge Area) |  | 30.4717 | 54.8352 | 5.835
2 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  |  | 5.7225
3 |  | Refuge Area | [6 empty] | 54.8352 | 5.7225
4 |  | 2BHK | 568.2854 | 0 | 852.4281 |  |  |  |  | 5.835
5 |  | 1BHK | 422.4063 | 0 | 633.6094 |  |  |  | 54.8352
6 |  | 1BHK | 424.1554 | 0 | 636.2331
Building Type C
Stilt Floor For Parking
1st to 4th Floor For Residential | [7 empty] | 4
1 |  | 1BHK | 385.7548 | 0 | 578.6323 | 1st to 4th Floor For Residential |  | 28.0401
2 |  | 1BHK | 385.7548 | 0 | 578.6323 |  |  | 6843.7247
3 |  | 1BHK | 385.7548 | 0 | 578.6323 |  |  |  | 6740.0319
4 |  | 1BHK | 385.7548 | 0 | 578.6323
5 |  | 1BHK | 385.7548 | 0 | 578.6323
6 |  | 1BHK | 385.7548 | 0 | 578.6323 |  |  |  | 10.764 |  | #DIV/0!
7 |  | 1BHK | 385.7548 | 0 | 578.6323
8 |  | 1BHK | 385.7548 | 0 | 578.6323
9 |  | 1BHK | 385.7548 | 0 | 578.6323
10 |  | 1BHK | 385.7548 | 0 | 578.6323
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Type A (Wing A) = Work is same as last visit (dtd.08/06/2025) but work is in process. Type A (Wing B) & Type B = Construction work is in process at the time of Visit. Type C = Work not yet Started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet +Attached Mezzanine + Encl Balcony + OP Area. | [6 empty] | We considered Gross carpet area = Net carpet + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation. | [6 empty] | Since Type C have received CC on 10/05/2021, but as of construction work is not started.
* | As per the revised approved plan dated 24/02/2023, the approved structure of Type A (Wing A) is reduced to Gr/Mezzanine + 1st Floor (earlier it was Gr + 1st to 7th Floor) & approved structure of Type C is reduced to Gr/St. + 1st to 4th Floor (earlier it was G + 1st to 12th Floor)
* | We have updated revised approved plans, CC & Fire Noc on 31/03/2025
* | Elevation Plan of Type A (Wing A) is attached below.
* | Since Building Type C have received CC on 24/02/2023, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Atlantic
Layout :
Elevation Plan of Type A (Wing A)
Google Map :
Formulas:
Kon = [Kon, row above]
Type A (Wing B)
Type A-Wing A
Type A-Wing B
Type B
Type C
Ground Floor
Mezzanine Floor
1st Floor
Type A
A Wing
Type A
B Wing
Type A
B Wing
Type B
Type A
B Wing
Type B
Type C
Type A : Wing A
Type A : Wing A
Type A : Wing B
Type B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted