## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Badlapur | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-06 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Shree Balaji Realty | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Shree Balaji Realty | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Balaji Sarvoday | [9 empty] | IBHF Andheri
Name of the Project as per RERA |  |  |  | Balaji Sarvoday - A Wing, B Wing and E Wing | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Vivek Singh - 8652442484
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Shankar 8097279745 |  |  |  | Mr. Shankar 8097279745
Name / No of the Building |  |  |  | Wing A, B & E
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700052121 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Balaji Sarvoday , Survey No.28, H.No.6 & H.No.3/1, Old Survey No. 242 A, near Krishna Plaza building, Shivaji Shelar Marg, Chole, Chole, Thakurli, Kalyan, Thane - 421201. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 28, H.No.6 & H.No.3/1, Old Survey No. 242 A | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Chole | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Shivaji Shelar Marg |  | Locality/Village |  | Chole | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Thakurli |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kalyan |  | Pin Code |  | 421201 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Krishna Plaza building |  | Distance from city centre: |  | 1.1 KM from Thakurli Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 18.00 M Wide Road |  |  | Shivaji Shelar Marg
West | NA | Road/Plot B |  |  | Krishna Plaza building
North | NA | Other Plot |  |  | Open Plot
South | NA | 24.00 M Wide Road/Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.220246,73.103066
Location Link |  | https://maps.app.goo.gl/UPNFJTaSwD52Sq8G7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10292.94
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.8214
Total FSI availaible for the project |  |  |  | 2.9214
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 30069.36
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan Dombivli Municipal Corporation (KMDC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | KDMC/TPD/BP/DOM/2022-23/82/31 |  |  | Dated | 2024-05-21 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | KDMC/TPD/BP/DOM/2022-23/82/31 |  |  | Dated | 2024-05-21 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Approved Floor plan No. (Only Ground & 1st Floor For Wing A & B) |  | KDMC/TPD/BP/DOM/2022-23/82 |  |  | Dated | 2023-03-09 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/DOM/2022-23/82/31 |  |  | Dated | 2024-05-21 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
|  | Wing A = Gr + 1st to 28th Floor (Residential) Wing B = Gr + 1st to 28th Floor (Residential) Wing E = Gr + 1st to 4th Floor (Commercial) | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
Building wise Construction details | [17 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Approved area of building (Sq.Mt) for Wing A, B & E |  |  | 29221.21 | [14 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Approved no of units |  |  | Flats - 388, Shops - 5, Offices -12 | [14 empty] | Bhiwandi Nizampur City Municipal Corporation
Approved no of Floors |  |  | Wing A = Gr + 1st to 28th Floor Wing B = Gr + 1st to 28th Floor Wing E = Gr + 1st to 4th Floor | [14 empty] | Maharashtra Industrial Development Corporation (MIDC)
Proposed no of Floors |  |  | Wing A = Gr + 1st to 28th Floor | [14 empty] | Mira-Bhayandar Municipal Corporation
Wing B = Gr + 1st to 28th Floor
Wing E = Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Cycling & Jogging Track, Children's Play Area, Indoor Games Power Backup, Badminton Court, Lift(s), 24x7 Security, Sewage Treatment
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 8 Floor Completed | , RCC upto 14 Slab, Brickwork upto 8 Floor
Construction details: |  | Wing A = Gr + 1st to 28th Floor | [5 empty] | Excavation, Plinth
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 28 | Completed | Completed
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 8 Floor Completed | [5 empty] | Piling Work in process | 7
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 14
Excavation |  | 28 | 100% | 31.45% |  | 60.91% |  | Excavation Completed | 28
Plinth |  | 28 | 100% |  |  |  |  | Footing in Process | 7
RCC (Including podiums) |  | 14 | 48.28% |  |  |  |  | Footing Completed | 14
Brickwork | Brickwork & Internal Plaster | 8 | 28.57% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Plinth in process | 21
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 28
Possession |  | 0 | 0% |  |  |  |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 8 Floor Completed | , RCC upto 14 Slab, Brickwork upto 8 Floor
Construction details: |  | Wing B = Gr + 1st to 28th Floor | [5 empty] | Excavation, Plinth
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 28 | Completed | Completed
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 8 Floor Completed | [5 empty] | Piling Work in process | 7
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 14
Excavation |  | 28 | 100% | 31.45% |  | 60.91% |  | Excavation Completed | 28
Plinth |  | 28 | 100% |  |  |  |  | Footing in Process | 7
RCC (Including podiums) |  | 14 | 48.28% |  |  |  |  | Footing Completed | 14
Brickwork | Brickwork & Internal Plaster | 8 | 28.57% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Plinth in process | 21
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 28
Possession |  | 0 | 0% |  |  |  |  | All work Completed. Possession granted to the Building.
Construction details: |  | Wing E = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Completed
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Piling Work in process | 1
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 2
Excavation |  | 4 | 100% | 100% |  | 100% |  | Excavation Completed | 4
Plinth |  | 4 | 100% |  |  |  |  | Footing in Process | 1
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing Completed | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Plinth in process | 3
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth completed | 4
Possession |  | 4 | 100%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7750 |  |  | 7500 to 7750 by bhargav on 08/05/2025
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 14000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 11000
Floor Rise Rate from Floor
Other Charges |  |  |  |  | 255000
Club Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 6200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A & B | Shop | 4 |  | 6607.589 |  | 9911.3836 |  | Housing |  | Sheet
Wing E | Shop | 1 |  | 1719.0646 |  | 2578.5969 |  | 7189.3976 | 1BHK | 6200000 | 8714.4213
| Office | 12 |  | 9659.9258 |  | 14489.8886 |  | 6117.1828 | 2BHK | 8200000 | 6524.995
Total |  | 17 |  | 17986.5794 |  | 26979.8691 |  | 6653.2902 | 3BHK | 11300000 | 7619.7081
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | OK
Wing A |  | 206 |  | 116633.4458 |  | 175262.3032 |  | OK | Metro Luxuria | 7500 | 50%
Wing B |  | 182 |  | 99364.7983 |  | 149047.1974
Total |  | 388 |  | 215998.244 |  | 324309.5005 |  | https://housing.com/in/buy/projects/page/303768-shree-balaji-sarvoday-a-wing-b-wing-and-e-wing-by-shree-balaji-realty-mumbai-in-dombivli-east
Grand Total |  | 405 |  | 233984.8235 |  | 351289.3697
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Wing A & B
Ground Floor For Commercial & Parking | [8 empty] | 10.764
1 |  | Shop | 1886.2834 | 0 | 1886.2834 | 0 | 2829.425 | 150
2 |  | Shop | 1620.4126 | 0 | 1620.4126 | 0 | 2430.6188
3 |  | Shop | 1816.3174 | 0 | 1816.3174 | 0 | 2724.476
4 |  | Shop | 1284.5758 | 0 | 1284.5758 | 0 | 1926.8636
1st Floor For Parking Area Handover to KDMC
2nd Floor For Parking Area Handover to KDMC
Wing E
Ground Floor For Commercial & Parking
1 |  | Shop | 1719.0646 | 0 | 1719.0646 | 0 | 2578.5969
1st Floor For Commercial | [7 empty] | 215.28
1 |  | Office | 2317.2739 | 0 | 2317.2739 | 0 | 3475.9109 | 25.0953
2 |  | Office | 275.3431 | 0 | 275.3431 | 0 | 413.0147
2nd Floor | [7 empty] | 42.735
1 |  | Office | 459.9995 | 0 | 459.9995 | 0 | 689.9993
2 |  | Office | 459.9995 | 0 | 459.9995 | 0 | 689.9993 | 10.764
3 |  | Office | 459.9995 | 0 | 459.9995 | 0 | 689.9993
4 |  | Office | 527.2638 | 0 | 527.2638 | 0 | 790.8957
3rd Floor
1 |  | Office | 2317.2739 | 0 | 2317.2739 | 0 | 3475.9109
2 |  | Office | 130.8902 | 0 | 130.8902 | 0 | 196.3354 | 10.764
3 |  | Office | 131.859 | 0 | 131.859 | 0 | 197.7885
4th Floor
1 |  | Office | 2317.2739 | 0 | 2317.2739 | 0 | 3475.9109
2 |  | Office | 130.8902 | 0 | 130.8902 | 0 | 196.3354 | 10.764
3 |  | Office | 131.859 | 0 | 131.859 | 0 | 197.7885
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet + Encl Bal. Area | Open Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading : | 32.026
50%
Wing A | [7 empty] | 1
3rd Floor For Residential | [7 empty] | 36.206 | 7.075 | 29.131
1 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139 | 10.764
2 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
3 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 132.9569 | 754.9923
4 |  | 2BHK | 588.8554 | 34.4717 | 623.3271 | 159.0919 | 1014.5366
5 |  | 2BHK | 590.6853 | 34.4717 | 625.157 | 159.0919 | 1017.2814
6 |  | 3BHK | 782.898 | 34.4717 | 817.3697 | 107.4678 | 1279.7885
7 |  | 2BHK | 603.1338 | 34.4717 | 637.6055 | 32.8302 | 989.2385 |  | 7500
8 |  | 1BHK | 432.7666 | 32.7764 | 465.543 | 0 | 698.3145 | 20
4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th Floor For Residential
1 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
2 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
3 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
4 |  | 2BHK | 588.8554 | 34.4717 | 623.3271 | 0 | 934.9906 | 7246177.4677 | 7501177.4677 | 7500000
5 |  | 2BHK | 590.6853 | 34.4717 | 625.157 | 0 | 937.7355 |  |  | -1177.4677
6 |  | 3BHK | 782.898 | 34.4717 | 817.3697 | 0 | 1226.0546
7 |  | 2BHK | 603.1338 | 34.4717 | 637.6055 | 0 | 956.4083
8 |  | 1BHK | 432.7666 | 32.7764 | 465.543 | 0 | 698.3145 | 2
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
2 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
3 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
4 |  | 2BHK | 588.8554 | 34.4717 | 623.3271 | 0 | 934.9906
5 |  | Refuge Area
6 |  | 3BHK | 782.898 | 34.4717 | 817.3697 | 0 | 1226.0546
7 |  | 2BHK | 603.1338 | 34.4717 | 637.6055 | 0 | 956.4083
8 |  | 1BHK | 432.7666 | 32.7764 | 465.543 | 0 | 698.3145 | 3
18th, 23rd & 28th Floor For Part Refuge Area
1 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
2 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
3 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
4 |  | 2BHK | 588.8554 | 34.4717 | 623.3271 | 0 | 934.9906
5 |  | 1BHK | 486.3444 | 34.4717 | 520.8161 | 0 | 781.2242
- |  | Refuge Area
6 |  | 3BHK | 782.898 | 34.4717 | 817.3697 | 0 | 1226.0546
7 |  | 2BHK | 603.1338 | 34.4717 | 637.6055 | 0 | 956.4083
8 |  | 1BHK | 432.7666 | 32.7764 | 465.543 | 0 | 698.3145 | 10.764
Wing B | [7 empty] | 21
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th Floor For Residential
1 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
2 |  | 2BHK | 588.8554 | 32.7764 | 621.6318 | 0 | 932.4476
3 |  | 2BHK | 619.2099 | 34.4717 | 653.6816 | 0 | 980.5224
4 |  | 1BHK | 424.1016 | 32.7764 | 456.878 | 0 | 685.317
5 |  | 1BHK | 424.1016 | 32.7764 | 456.878 | 0 | 685.317
6 |  | 2BHK | 563.2801 | 34.4717 | 597.7518 | 0 | 896.6277
7 |  | 2BHK | 563.2801 | 34.4717 | 597.7518 | 0 | 896.6277 | 5
8th, 13th, 18th, 23rd, 28th Floor For Part Refuge Area
1 |  | 1BHK | 426.2329 | 32.7764 | 459.0093 | 0 | 688.5139
2 |  | 2BHK | 588.8554 | 32.7764 | 621.6318 | 0 | 932.4476
3 |  | 2BHK | 619.2099 | 34.4717 | 653.6816 | 0 | 980.5224
4 |  | 1BHK | 424.1016 | 32.7764 | 456.878 | 0 | 685.317
5 |  | 1BHK | 424.1016 | 32.7764 | 456.878 | 0 | 685.317
6 |  | 1BHK | 449.6123 | 34.4717 | 484.084 | 0 | 726.126
- |  | Refuge Area
7 |  | 2BHK | 563.2801 | 34.4717 | 597.7518 | 0 | 896.6277
Remarks:
* | Wing A & B = Construction work is in process at the time of Visit. Wing E = All work completed. Please Provide OC.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Encl Balcony + Open Balcony Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved CC & Plans for Wing E & 2nd to 28th Floor Plan for Wing A & B on 16/04/2025. | [6 empty] | * | Please check for Environment Clearance Certificate.
* | We have referred Approved Plans (Sheet No.1, 3 to 9) from RERA Site on 16/04/2025
* | Please check For Environment Clearance Certificate & Fire Noc. | [6 empty] | Proposed structure has been revised to G + 28th floor with ref to building picture on builder website.
* | Provide approved Floor plan Sheet No.2 dtd.21/05/2024
* | Recommended Rates/Other Charges of the Property have been revised on 23/10/2023.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Balaji Sarvoday
Layout :
Google Map :
Formulas:
Chole = [Chole, row above]
Note on E13: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E14: Sachin: If exisiting Building is provided write it or else NA
Wing A
Wing B
Wing C
Wing D
Wing E
N
A Wing
A Wing
B Wing
E Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar