## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-07
Name of the builder group |  |  |  | Kapleshwara Homes Llp
Name of the builder company |  |  |  | Kapleshwara Homes Llp
Name of the Project |  |  |  | Kapleshwara Residency
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Niraj Sharma 8425899000
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Niraj Sharma 8425899000
Name / No of the Building |  |  |  | Building A (Dhruhi) Building B (Kaira) Building C (Shivansh)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51700049543
Project location details |  | Kapleshwara Residency, Survey No.84(New) 119 (Old), H.No.6C, near Shree Empire, Dawadi Gaon Road, Sonar Pada, Golivali, Dombivli (East), Kalyan, Thane - 421201.
Survey No |  | 84(New) 119 (Old), H.No.6C
Locality |  | Sonar Pada
Road |  | Dawadi Gaon Road |  | Locality/Village |  | Golivali
City |  | Dombivli (East) |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Nearby Landmark |  | Shree Empire |  | Distance from city centre: |  | 3.5 KM from Dombivli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Pragron Engineering Company
North | NA | NA |  |  | Regency Anantam Sales office
South | NA | NA |  |  | Shree Empire
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.206496, 73.111144
Location Link |  | https://goo.gl/maps/Tj3U4HmbUgBJfwW38
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6338.01
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.4233
Total FSI availaible for the project |  |  |  | 4.5233
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 28668.91
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan Dombivli Municipal Corporation (KDMC)
Layout Approval No |  | KDMC/TPD/BP/27Village/2018-19/29/215 |  |  | Dated | 2023-10-03
Approved Floor plan No. |  | KDMC/TPD/BP/27Village/2018-19/29/215 |  |  | Dated | 2023-10-03
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/27Village/2018-19/29/215 |  |  | Dated | 2023-10-03
Type A = Gr/Stilt + 4P + 5th floor (Pt) to 9th Floor (Pt) + 10th to 25th Floor 15th Recreational Floor Type A (For Mhada) = 5th Floor (Pt) to 9th Floor (Pt) Type B = Gr/Stilt + 4P + 5th to 26th Floor Type C = Gr/Stilt + 4P + 5th to 26th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 28668.91
Approved no of units |  |  | Sale Flats - 455, Mhada Flats - 25, Shops - 26
Approved no of Floors |  |  | Building A (Dhruhi) = Gr/Stilt + 4P + 5th to 25th Floor Building B (Kaira) = Gr/Stilt + 4P + 5th to 26th Floor Building C (Shivansh)= Gr/Stilt + 4P + 5th to 26th Floor
Proposed no of Floors |  |  | Building A (Dhruhi) = Gr/Stilt + 4P + 5th to 30th Floor
Building B (Kaira) = Gr/Stilt + 4P + 5th to 30th Floor
Building C (Shivansh) = Gr/Stilt + 4P + 5th to 30th Floor
Expected Completion |  |  | As per RERA - 31/12/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming pool, Temple, Sit-outs, Star gazing, Indoor games, Toddler play area, Music room, Gymnasium, Jogging track, Mini party lawn, Amphiltheatre, Cafeteria etc
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building A (Dhruhi) = Gr/Stilt + 4P + 5th to 30th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 26 Slab, Brickwork upto 25 Floor, Internal Plaster upto 12 Floor, External Plaster upto 6 Floor Completed | , RCC upto 26 Slab, Brickwork upto 25 Floor, Internal Plaster upto 12 Floor, External Plaster upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 30 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 26 Slab, Brickwork upto 25 Floor, Internal Plaster upto 12 Floor, External Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 54.8% |  | 77.33% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 26 | 83.87% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 25 | 83.33% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 12 | 40% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 20% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building B (Kaira) = Gr/Stilt + 4P + 5th to 30th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 26 Slab, Brickwork upto 22 Floor, Internal Plaster upto 14 Floor, External Plaster upto 8 Floor Completed | , RCC upto 26 Slab, Brickwork upto 22 Floor, Internal Plaster upto 14 Floor, External Plaster upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 30 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 26 Slab, Brickwork upto 22 Floor, Internal Plaster upto 14 Floor, External Plaster upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 55.22% |  | 77.49% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 26 | 83.87% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 22 | 73.33% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 14 | 46.67% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 26.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building C (Shivansh) = Gr/Stilt + 4P + 5th to 30th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 30 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 15.16% |  | 48.87% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 4 | 12.9% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7800 |  |  | 7500 to 7800 | akash mote verbal |  | 2025-07-28
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 14000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 6240
Commercial Area Details : Shop
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building A (Dhruhi) | Sale | 16 |  | 3862.3385 |  | 7705.1941
Building B (Kaira) | Sale | 10 |  | 2491.866 |  | 4971.0305
Total |  | 26 |  | 6354.2045 |  | 12676.2246
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building A (Dhruhi) | Sale | 135 |  | 62413.1165 |  | 93619.6747
| Mhada | 25 |  | 11653.8599 |  | 17480.7898
Building B (Kaira) | Sale | 160 |  | 75996.3157 |  | 113994.4736
Building C (Shivansh) | Sale | 160 |  | 76624.0722 |  | 114936.1083
Sale Flats |  | 455 |  | 215033.5044 |  | 322550.2566
Mhada Flats |  | 25 |  | 11653.8599 |  | 17480.7898
Total |  | 480 |  | 226687.3643 |  | 340031.0464
Grand Total |  | 506 |  | 233041.5688 |  | 352707.271
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
50%
Building A (Dhruhi)
Ground Floor For Entrance Looby, Society Office, Meter Room, Commercial & Parking
11 | Sale | Shop | 268.2389 | 88.4801 | 535.0784 | Ground Floor For Entrance Looby, Society Office, Meter Room, Commercial & Parking |  |  | 10.764
12 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
13 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
14 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
15 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
16 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
17 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
18 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
19 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
20 | Sale | Shop | 180.1894 | 59.4173 | 359.41 |  |  | 16.74
21 | Sale | Shop | 180.1894 | 59.4173 | 359.41
22 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
23 | Sale | Shop | 268.2389 | 88.4801 | 535.0784 |  |  | 16.8516
24 | Sale | Shop | 278.1418 | 91.8169 | 554.938
25 | Sale | Shop | 318.9373 | 105.2719 | 636.3139 |  |  | 29.632
26 | Sale | Shop | 208.2834 | 68.782 | 415.598 |  |  | 19.328
Building B (Kaira)
Ground Floor For Entrance Looby, Society Office, Meter Room, Commercial & Parking
1 | Sale | Shop | 268.2389 | 88.4801 | 535.0784 | Ground Floor For Entrance Looby, Society Office, Meter Room, Commercial & Parking
2 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
3 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
4 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
5 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
6 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
7 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
8 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
9 | Sale | Shop | 204.7313 | 67.5979 | 408.4938
10 | Sale | Shop | 268.2389 | 88.4801 | 535.0784
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building A (Dhruhi)
1st to 4th Podium Floor For Parking
5th to 7th & 9th Floor For Residential | [7 empty] | https://housing.com/in/buy/projects/page/293834-kapleshwara-residency-by-kapleshwara-homes-llp-in-dombivli-east
1 | Mhada | 2BHK | 537.5542 | 0 | 806.3312 | 5th to 7th & 9th Floor For Residential |  | 46.7971
2 | Mhada | 2BHK | 543.0438 | 0 | 814.5657
3 | Mhada | 1BHK | 391.702 | 0 | 587.5529
4 | Mhada | 1BHK | 391.702 | 0 | 587.5529 |  |  |  | Housing |  | Sheet
5 | Mhada | 1BHK | 434.9732 | 0 | 652.4599 |  |  |  | 7320.9036 | 7658.8843 | 47L (1BHK)
6 | Sale | 1RK | 283.0932 | 0 | 424.6398 |  |  |  | 7535.7986 | 7611.418 | 68L (2BHK)
7 | Sale | 1RK | 276.5272 | 0 | 414.7907 |  |  |  | 7318.4895
8 | Sale | 1RK | 274.3744 | 0 | 411.5615 |  |  |  | 7658.8843
9 | Sale | 1RK | 273.1903 | 0 | 409.7855 |  |  | 24.4474 | 7813.1662
8th Floor (Part Refuge Area) | [8 empty] | 7529.4484
1 | Mhada | 2BHK | 537.5542 | 0 | 806.3312 | 8th Floor (Part Refuge Area)
2 | Mhada | 2BHK | 543.0438 | 0 | 814.5657 |  |  |  | Regency Anantam |  | 7600
3 | Mhada | 1BHK | 391.702 | 0 | 587.5529
4 | - | Refuge Area
5 | Mhada | 1BHK | 439.4941 | 0 | 659.2412
6 | Sale | 1RK | 283.0932 | 0 | 424.6398
7 | Mhada | 2BHK | 546.1654 | 0 | 819.248
8 | Sale | 1RK | 273.1903 | 0 | 409.7855
10th, 11th, 12th, 14th, 16th, 17th, 19th, 20th, 21st, 22nd & 24th, 25th Floor
1 | Sale | 2BHK | 573.7212 | 0 | 860.5818 | 10th, 11th, 12th, 14th, 16th, 17th, 19th, 20th, 21st, 22nd & 24th, 25th Floor |  | 48.3541
2 | Sale | 2BHK | 579.1032 | 0 | 868.6548
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | Sale | 1BHK | 427.869 | 0 | 641.8035
5 | Sale | 1BHK | 439.4941 | 0 | 659.2412
6 | Sale | 1BHK | 427.3308 | 0 | 640.9962
7 | Sale | 2BHK | 577.2733 | 0 | 865.91
8 | Sale | 1BHK | 461.4527 | 0 | 692.179
13th, 18th & 23rd Floor (Part Refuge Area)
1 | Sale | 2BHK | 573.7212 | 0 | 860.5818 | 13th, 18th & 23rd Floor (Part Refuge Area)
2 | Sale | 2BHK | 579.1032 | 0 | 868.6548
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | - | Refuge Area
5 | Sale | 1BHK | 439.4941 | 0 | 659.2412
6 | Sale | 1BHK | 427.3308 | 0 | 640.9962
7 | Sale | 2BHK | 577.2733 | 0 | 865.91
8 | Sale | 1BHK | 461.4527 | 0 | 692.179
15th Floor For Recreational Area
Building B (Kaira)
1st to 4th Podium Floor For Parking
5th to 7th & 9th Floor For Residential
1 | Sale | 1BHK | 391.702 | 0 | 587.5529 | 5th to 7th & 9th Floor For Residential
2 | Sale | 1BHK | 387.1811 | 0 | 580.7716
3 | Sale | 1BHK | 391.702 | 0 | 587.5529
4 | Sale | 1BHK | 391.702 | 0 | 587.5529
5 | Sale | 2BHK | 522.9151 | 0 | 784.3727
6 | Sale | 2BHK | 538.6306 | 0 | 807.9458
7 | Sale | 2BHK | 540.9986 | 0 | 811.498
8 | Sale | 1BHK | 402.3583 | 0 | 603.5375
8th Floor (Part Refuge Area)
1 | - | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
2 | Sale | 1BHK | 387.1811 | 0 | 580.7716
3 | Sale | 1BHK | 391.702 | 0 | 587.5529
4 | Sale | 1BHK | 391.702 | 0 | 587.5529
5 | Sale | 2BHK | 522.9151 | 0 | 784.3727
6 | Sale | 2BHK | 538.6306 | 0 | 807.9458
7 | Sale | 2BHK | 540.9986 | 0 | 811.498
8 | Sale | 1BHK | 402.3583 | 0 | 603.5375
10th, 11th, 12th, 14th, 16th, 17th, 19th, 20th, 21st, 22nd & 24th, 25th Floor
1 | Sale | 1BHK | 427.869 | 0 | 641.8035 | 10th, 11th, 12th, 14th, 16th, 17th, 19th, 20th, 21st, 22nd & 24th, 25th Floor
2 | Sale | 1BHK | 423.3481 | 0 | 635.0222
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | Sale | 1BHK | 427.869 | 0 | 641.8035
5 | Sale | 2BHK | 558.9745 | 0 | 838.4618
6 | Sale | 2BHK | 574.69 | 0 | 862.0349
7 | Sale | 2BHK | 577.1657 | 0 | 865.7485
8 | Sale | 1BHK | 438.633 | 0 | 657.9495
13th, 18th & 23rd Floor (Part Refuge Area)
1 | - | Refuge Area |  |  |  | 13th, 18th & 23rd Floor (Part Refuge Area)
2 | Sale | 1BHK | 423.3481 | 0 | 635.0222
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | Sale | 1BHK | 427.869 | 0 | 641.8035
5 | Sale | 2BHK | 558.9745 | 0 | 838.4618
6 | Sale | 2BHK | 574.69 | 0 | 862.0349
7 | Sale | 2BHK | 577.1657 | 0 | 865.7485
8 | Sale | 1BHK | 438.633 | 0 | 657.9495
26th Floor (Part Terrace Area)
1 | - | Terrace Area |  |  |  | 26th Floor (Part Terrace Area)
2 | -
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | Sale | 1BHK | 427.869 | 0 | 641.8035
5 | Sale | 2BHK | 558.9745 | 0 | 838.4618
6 | Sale | 2BHK | 574.69 | 0 | 862.0349
7 | - | Terrace Area
8 | -
15th Floor For Recreational Area
Building C (Shivansh)
Ground Floor For Entrance Lobby, Gym, Driver Room, Meter Room, Creche, Society Office & Parking
1st to 4th Podium Floor For Parking
5th to 7th & 9th Floor For Residential
1 | Sale | 2BHK | 540.1375 | 0 | 810.2063 | 5th to 7th & 9th Floor For Residential
2 | Sale | 1BHK | 391.702 | 0 | 587.5529
3 | Sale | 1BHK | 391.702 | 0 | 587.5529
4 | Sale | 1BHK | 391.702 | 0 | 587.5529
5 | Sale | 1BHK | 391.702 | 0 | 587.5529
6 | Sale | 1BHK | 391.702 | 0 | 587.5529
7 | Sale | 2BHK | 540.1375 | 0 | 810.2063
8 | Sale | 2BHK | 558.7592 | 0 | 838.1389
8th Floor (Part Refuge Area)
1 | Sale | 2BHK | 540.1375 | 0 | 810.2063 | 8th Floor (Part Refuge Area)
2 | Sale | 1BHK | 391.702 | 0 | 587.5529
3 | Sale | 1BHK | 391.702 | 0 | 587.5529
4 | Sale | 1BHK | 391.702 | 0 | 587.5529
5 | Sale | 1BHK | 391.702 | 0 | 587.5529
6 | - | Refuge Area
7 | Sale | 2BHK | 540.1375 | 0 | 810.2063
8 | Sale | 2BHK | 558.7592 | 0 | 838.1389
10th, 11th, 12th, 14th, 16th, 17th, 19th, 20th, 21st, 22nd & 24th, 25th Floor
1 | Sale | 2BHK | 576.3046 | 0 | 864.4568 | 10th, 11th, 12th, 14th, 16th, 17th, 19th, 20th, 21st, 22nd & 24th, 25th Floor
2 | Sale | 1BHK | 427.869 | 0 | 641.8035
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | Sale | 1BHK | 427.4384 | 0 | 641.1577
5 | Sale | 1BHK | 427.869 | 0 | 641.8035
6 | Sale | 1BHK | 427.5461 | 0 | 641.3191
7 | Sale | 2BHK | 576.1969 | 0 | 864.2954
8 | Sale | 2BHK | 594.9263 | 0 | 892.3894
13th, 18th & 23rd Floor (Part Refuge Area)
1 | Sale | 2BHK | 576.3046 | 0 | 864.4568 | 13th, 18th & 23rd Floor (Part Refuge Area)
2 | Sale | 1BHK | 427.869 | 0 | 641.8035
3 | Sale | 1BHK | 427.869 | 0 | 641.8035
4 | Sale | 1BHK | 427.4384 | 0 | 641.1577
5 | Sale | 1BHK | 427.869 | 0 | 641.8035
6 | - | Refuge Area
7 | Sale | 2BHK | 576.1969 | 0 | 864.2954
8 | Sale | 2BHK | 594.9263 | 0 | 892.3894
26th Floor (Part Terrace Area)
1 | - | Terrace Area |  |  |  | 26th Floor (Part Terrace Area)
2 | -
3 | -
4 | -
5 | Sale | 1BHK | 421.7335 | 0 | 632.6003
6 | Sale | 1BHK | 427.5461 | 0 | 641.3191
7 | Sale | 2BHK | 576.1969 | 0 | 864.2954
8 | Sale | 2BHK | 594.9263 | 0 | 892.3894
15th Floor For Recreational Area
Remarks:
1 | Building A, B & C = Construction work is in process at the time of Visit. Internal visit was not allowed.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | We have updated latest CC from Rera (On 04/12/2024).
11 | We have updated latest approved floor plans (On 27/12/2024).
12 | We have updated Building nomenclature as per the letter provided by the bank officials on mail on 28/03/2025. Document attached Below.
13 | Recommended Rates / Other charges of the Property have been revised on 28/07/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram parshuram Lambore |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kapleshwara Residency
Layout :
Remark No. 12 :
Google Map :
Formulas:
Golivali = [Golivali, row above]
Building A
Building B
Building C
Building A
Building B
Building C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted