## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 13/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-06
Name of the builder group |  |  |  |  | M/s.Shivkrupa Builders & Developers
Name of the builder company |  |  |  |  | M/s.Shivkrupa Builders & Developers
Name of the Project |  |  |  |  | Priyanshi Residency
Contect Details ( Name & Contect No.) |  |  |  |  | 9004150006
Name / No of the Building |  |  |  |  | Building No.1 Building No.2 (A1 & A2 Wings) Building No.3 Building No.4
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC, Cost Sheet.
RERA No. |  |  |  |  | P52000016200
Project location details |  | Priyanshi Residency, Gut No. 12, Plot No. 1&2, Mumbai - Pune Expressway, Usarli Khurd, Panvel, Raigad.
Gut No |  | 12 |  |  | Plot No | 1&2 | Locality | Usarli Khurd
Road | Mumbai - Pune Expressway |  |  |  | District | Raigad
City | Panvel |  |  |  | Pin Code | 410206
Near by Landmark |  | Shri Renuka Yellama Temple |  |  | Distance from city centre: |  | 2.9 Km from Panvel Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Road |  | Road |  | Chawl
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 18.977605,73.137755
Location Link |  | https://goo.gl/maps/H7RtQ2t9pK378ZXt5
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial.
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 2195.89
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 2195.89
Total number of Buildings |  |  |  |  | 04 Building ( 02 Wings )
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/NAINA/PANVEL/USARLI KHURD/BP-227/CC/2018/1296. |  |  |  | Dated | 22/02/2018.
Approved Floor plan No. |  | CIDCO/NAINA/PANVEL/USARLI KHURD/BP-227/CC/2018/1296. |  |  |  | Dated | 22/02/2018.
Commencement Certificate No. |  | CIDCO/NAINA/PANVEL/USARLI KHURD/BP-227/CC/2018/1296. |  |  |  | Dated | 22/02/2018.
Valid Up to: Building No 1 = Stilt + 1st to 4th Floor Building No 2(Wing A1 & A2) = G + 1st to 4th Floor. Building No 3 & 4 = Stilt + 1st to 3rd Floor
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 22/02/2018. |  | Expected Completion |  | 30/06/2021.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2195.89 |  | Approved no of units |  |  | Shop = 09 Flat = 49
Approved no of Floors |  | Building No 1 = Stilt + 1st to 4th Floor Building No 2 ( Wing A1 & A2) = G + 1st to 4th Floor. Building No 3 & 4 = Stilt + 1st to 3rd Floor.
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Building No 1 = Stilt + 1st to 4th Floor Building No 2 ( Wing A1 & A2) = G + 1st to 4th Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 85% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No 3 = Stilt + 1st to 3rd Floor Building No 4 = Stilt + 1st to 3rd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 2 Floor, Flooring upto 2 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 2 Floor, Flooring upto 2 Floor, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 80% |  | 91.67% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 66.67% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 66.67% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 33.33% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 5600
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 9900/-
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 3,00,000/-
Development charges | [5 empty] | 180000/-
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 4480
Commercial Area Details.
Building /Wing |  | Total No of units |  |  | Total carpet area |  | Total Sealable Area
Building No.1 |  | 6 |  |  | 444.1226 |  | 872
Residential Area Details.
Building No.2 | Wing A1 | 10 |  |  | 3187.7586 |  | 5931
| Wing A2 | 17 |  |  | 5349.2236 |  | 9771
Building No.3 |  | 11 |  |  | 2083.9965 |  | 4110
Building No.4 |  | 11 |  |  | 2495.0145 |  | 3846
Total |  | 49 |  |  | 13115.9932 |  | 23658
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.1
Ground Floor is For Commercial
1 |  | Shop | 74.2716 |  | 0 | 148 | N | Ground Floor
2 |  | Shop | 87.2422 |  | 0 | 174 | N
3 |  | Shop | 60.5475 |  | 0 | 114 | N
4 |  | Shop | 60.5475 |  | 0 | 114 | N
5 |  | Shop | 87.2422 |  | 0 | 174 | N
6 |  | Shop | 74.2716 |  | 0 | 148 | N
1st & 3rd Floor
1 |  | 1BHK | 318.7759 |  | 56.511 | 602 | N | 1st & 3rd Floor
2 |  | 1BHK | 318.7759 |  | 56.511 | 602 | N
2nd Floor
1 |  | 1BHK | 318.7759 |  | 42.1411 | 556 | N | 2nd Floor
2 |  | 1BHK | 318.7759 |  | 74.1101 | 602 | N
4th Floor
1 |  | 1BHK | 318.7759 |  | 42.1411 | 556 | N | 4th Floor
2 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N
Building No.2
Wing A1
Ground Floor is For Residential & Stilt
1 |  | 1BHK | 318.7759 |  | 0 | 491 | N | Ground Floor
1st & 3rd Floor
1 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N | 1st & 3rd Floor
2 |  | 1BHK | 318.7759 |  | 47.9536 | 561 | N
3 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N
4 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N
2nd & 4th Floor
1 |  | 1BHK | 318.7759 |  | 75.5633 | 605 | N | 2nd & 4th Floor
2 |  | 1BHK | 318.7759 |  | 47.9536 | 561 | N
3 |  | 1BHK | 318.7759 |  | 72.0515 | 602 | N
4 |  | 1BHK | 318.7759 |  | 72.0515 | 602 | N
Wing A2
Ground Floor is For Residential & Parking
1 |  | 1BHK | 318.7759 |  | 0 | 491 | N | Ground Floor
1st & 3rd Floor
1 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N | 1st & 3rd Floor
2 |  | 1BHK | 318.7759 |  | 48.8416 | 605 | N
3 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N
4 |  | 1BHK | 301.2844 |  | 56.2419 | 508 | N
2nd & 4th Floor
1 |  | 1BHK | 318.7759 |  | 72.0515 | 602 | N | 2nd & 4th Floor
2 |  | 1BHK | 318.7759 |  | 72.0515 | 602 | N
3 |  | 1BHK | 318.7759 |  | 74.1101 | 605 | N
4 |  | 1BHK | 301.2844 |  | 0 | 508 | N
Building No.3
Ground Floor is For Commercial & Stilt
1 |  | Shop | 79.3307 |  | 0 | 158 | N | Ground Floor
2 |  | Shop | 53.3679 |  | 0 | 106 | N
3 |  | Shop | 53.3679 |  | 0 | 106 | N
1st & 3rd Floor
1 |  | 1RK | 243.1103 |  | 53.9341 | 471 | N | 1st & 3rd Floor
2 |  | 1RK | 231.3722 |  | 52.2549 | 464 | N
2nd Floor
1 |  | 1RK | 243.1103 |  | 53.9793 | 471 | N | 2nd Floor
2 |  | 1RK | 231.3722 |  | 48.2765 | 464 | N
Building No.4
Ground Floor is for stilt
1st & 2nd Floor
1 |  | 1RK | 232.0449 |  | 0 | 357 | N | 1st & 2nd Floor
2 |  | 1RK | 226.8782 |  | 0 | 350 | N
3 |  | 1RK | 223.649 |  | 0 | 345 | N
4 |  | 1RK | 223.649 |  | 0 | 345 | N
3rd Floor
1 |  | 1RK | 232.0449 |  | 0 | 357 | N | 3rd Floor
2 |  | 1RK | 226.8782 |  | 0 | 350 | N
3 |  | 1RK | 223.649 |  | 0 | 345 | N
4 |  | Terrace Area
Remarks: 1. Construction work was stopped at the time of visit. Work is same since visit (dtd.10/09/2022). 2. We considered Saleable area as per Builder's Area Sheet. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. Car parking is subjected to authentic documentation. 7. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 8. The project has received first CC on 22/02/2018, But construction work is not yet completed. 9. As per RERA, completion period of project Priyanshi Residency is expired on 30/06/2021 but still project is under construction. 8 On site We meet Mr. Hanumant(Supervisor) - 9594440423.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Priyanshi Residency
Google Map :
2A
1

## 1
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
| 4 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 1900-01-03 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 10 | 10
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 75 | 85

## 2
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 7.5 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 75 | Recommended |  |  | 30 | 30 | 15 | 7.5 | 0 | 0 | 0
| 4 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 3 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 7.5 | 7.5
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 72.5 | 82.5

## 3
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 3 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## 4
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 100 | Progress |  |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 50 | Recommended |  |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
| 3 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 1.5 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 3 | 0 |  | Plaster | 5 | 5
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 70 | 80

## Wing A
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.6 | 3.65 | 9.49 | CB |  |  | 0 | 2.625 | 2.5 | 6.5625
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.2 | 2.2 | 4.84 | CB | 2.3 | 2 | 4.6 |  |  | 0
|  |  |  | 0 | FB | 2.35 |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 6.63
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 71.3653
| Bed1 | 2.6 | 2.6 | 6.76 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 1 | 1.2 | DB |  |  | 0 |  |  | 0
| toilet2 | 0.9 | 1.2 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.4 | 0.9 | 2.16 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 274.8049 | 25.53 |  |  | 49.5144 | 4.6 |  | 70.6388 | 6.5625

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Sheet3
Axis Sanpada
Axis Goregaon
Axis Kalina
Middle Class
Upper Class
Developing
Developed
Residential
Commercial
Residential & Commercial