## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 09/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-06
Name of the builder group |  |  |  |  | M/s. Braj Developers
Name of the builder company |  |  |  |  | M/s. Braj Developers.
Name of the Project |  |  |  |  | Braj City
Contect Details ( Name & Contect No.) |  |  |  |  | Mr.Rajesh (09699202797) Mr.Bhanu (08976661114)
Name / no of the Building |  |  |  |  | Wing A & B
Docouments Provided |  |  |  |  | 1. Approved Layout, 2.Approved Building Plan 3. CC 4. Cost Sheet.
RERA Number |  |  |  |  | P99000006444
Project location details |  | Braj City, S. No.826, Plot No.165, Grukrupa Ind. Estate, Opp. Sunderam High School, Village-Mahim, Tal-Palghar, Dist. Palghar.
Plot No | 165 |  |  | S No /G. No/ Khasra No./CTS No. |  | 826 | Locality | Mahim
Road | Mahim Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401 402.
Near by Landmark |  | Opp. Sunderam High School |  |  | Distance from city centre: |  | About 3.1 Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Bldg |  | Fia Pride |  | U/C Bldg |  | Chawl
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC
Latitude & Longitude |  | 19.683753,72.757172
Location Link |  | https://goo.gl/maps/g7XbCeuqyKKkbTUt5
Approval details:
Approved usage of the Property: Commercial & Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 1879.5(Net Plot-1680.20 Sq.Mt.)
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.2
Total FSI availaible for the project |  |  |  |  | 1.2
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 2016.24
Total number of Buildings |  |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | BP/Mouje.Mahim/tal.Palghar/S.No.826/Plot No.165/Palghar/1186/Resi. & Comm, |  |  |  | Dated | 06/10/2015.
Building plan approval No |  | BP/Mouje.Mahim/tal.Palghar/S.No.826/Plot No.165/Palghar/1186/Resi. & Comm, |  |  |  | Dated | 06/10/2015. | Expiry date:NA
Date of Commencement of Construction |  | MHSL/KS.1/T.1/NAP/SR-103/2018 Valid Up to: Gr.+ 1st to 4th Floor |  |  |  | Dated | 06/04/2021.
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 06/04/2021. |  | Expected Completion |  | 31/03/2026.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2016.24 |  | Approved no of units |  | Flats = 36 & Shops = 20
Approved no of Floors |  | Gr.+1st to 3rd Floor |  |  | No of floors at site : See Construction details
Proposed no of Floors |  |  | Gr.+ 1st to 4th Floor
Quality of construction: Good |  |  |  |  | Projected life: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Wing A = Gr.+ 1st to 4th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 92.5% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Wing B = Gr.+ 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 86.25% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 3950
Recommended rate of the Shop Per Sq. Ft. ( on Saleble area) | [5 empty] | 5500
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Water & Electricity Charges | [5 empty] | 45000
Club Charges | [5 empty] | NA
Maintenance Charges For 24 Months | [5 empty] | 30000
Society formation charges | [5 empty] | 60000
Recommended rate of Parking | [5 empty] | NA
Development charges | [5 empty] | 135000
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3160
Commercial Area Details
Building / Wing |  | No of unit |  |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 13 |  |  | 1292.14 |  | 2390
Wing B |  | 7 |  |  | 908.3182 |  | 1685
Total |  | 20 |  |  | 2200.4582 |  | 4075
Residential Area Details
Building / Wing |  | No of unit |  |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 18 |  |  | 8039.55 |  | 12345
Wing B |  | 18 |  |  | 8035.02 |  | 11650.779
Total |  | 36 |  |  | 16074.57 |  | 23995.779
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Builder Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
A Wing
Ground Floor For Parking & Commercial Shop
1 |  | Shop | 69.19 |  | 0 | 127 | NA | Ground Floor
2 |  | Shop | 69.19 |  | 0 | 127 | NA
3 |  | Shop | 69.19 |  | 0 | 127 | NA
4 |  | Shop | 69.19 |  | 0 | 127 | NA
5 |  | Shop | 69.19 |  | 0 | 127 | NA
6 |  | Shop | 62.44 |  | 0 | 115 | NA
7 |  | Shop | 168 |  | 0 | 310 | NA
8 |  | Shop | 142 |  | 0 | 265 | NA
9 |  | Shop | 135 |  | 0 | 250 | NA
10 |  | Shop | 105 |  | 0 | 195 | NA
11 |  | Shop | 135 |  | 0 | 250 | NA
12 |  | Shop | 118 |  | 0 | 220 | NA
13 |  | Shop | 80.75 |  | 0 | 150 | NA
1st, 2nd & 3rd Floor
A Wing
1 |  | 1BHK | 395.62 |  | 0 | 610 | NA | 1st, 2nd & 3rd
2 |  | 1BHK | 431.31 |  | 0 | 665 | NA
3 |  | 1BHK | 388.62 |  | 0 | 595 | NA
4 |  | 1BHK | 431.98 |  | 0 | 665 | NA
5 |  | 2BHK | 556.37 |  | 0 | 850 | NA
6 |  | 1BHK | 475.95 |  | 0 | 730 | NA
B Wing
Ground Floor For Parking & Commercial Shop
14 |  | Shop | 81.1606 |  | 0 | 150 | NA | Ground Floor
15 |  | Shop | 118.5 |  | 0 | 220 | NA
16 |  | Shop | 135 |  | 0 | 250 | NA
17 |  | Shop | 105 |  | 0 | 195 | NA
18 |  | Shop | 134.6576 |  | 0 | 250 | NA
19 |  | Shop | 142 |  | 0 | 265 | NA
20 |  | Shop | 192 |  | 0 | 355 | NA
1st, 2nd & 3rd Floor
1 |  | 1BHK | 474.94 |  | 0 | 688.663 | NA | 1st, 2nd & 3rd |  | 3913.0164 | 431.0544
2 |  | 2BHK | 556.37 |  | 0 | 806.7365 | NA
3 |  | 1BHK | 431.98 |  | 0 | 626.371 | NA
4 |  | 1BHK | 388.12 |  | 0 | 562.774 | NA
5 |  | 1BHK | 431.31 |  | 0 | 625.3995 | NA
6 |  | 1BHK | 395.62 |  | 0 | 573.649 | NA
Remarks: 1. A Wing = Lift & Finishing work is pending. Work is same as last visit (06/12/2023) but some flats are occupied by tenants. B Wing = Work was stopped at the time of visit. Work is same as last visit (06/12/2023). 2. We adpoted carpet area & saleable area as per Builder area statement 3. We have considered rate by verifying it from market inquire. 4. We have considered Other charges from cost sheet. 6. We have considered construction percentage as per proposed no of Floors (G + 1st to 4th) because construction goes beyond approved no of floors (G + 1st to 3rd). Please provide revised Approved Plans & CC. 7. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 8. We have updated revised CC from Rera on 12/09/2024. 9. Construction work goes beyond approved no. of floor. Please provide revised approved plans. 8. On site we met Mr.Govind Rathod : 8668692314. 8. As per RERA, completion period of project Braj City is expired on 31/03/2024 but still Construction work of project is Pending.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOS OF PROPERTY : Braj City
Google Map :
A Wing

## Note
2021-02-05 | Pratiksha

## A%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
| 4 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 4 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 10 | 10
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 75 | 85

## B%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 3.75 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 37.5 | Recommended |  |  | 30 | 30 | 15 | 3.75 | 0 | 0 | 0
| 4 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 1.5 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 3.75 | 3.75
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 68.75 | 78.75

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0