## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-06 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Samrin Infrastructure | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Samrin Infrastructure | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Changuna Aangan | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 9372735016
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Vishal : 8850096949
Name / No of the Building |  |  |  | Building 01
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, & Cost Sheet. | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700051386 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Changuna Aangan, Survey No.162 & 167 H. No. 04, near Sudama Regency, Diva Shil Road, Lokgram, Khardipada, Dawale, Diva East, Thane, Thane - 400612. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 162 & 167 H. No. 04 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Lokgram, Khardipada | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Diva Shil Road |  | Locality/Village |  | Dawale | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Diva East |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Thane |  | Pin Code |  | 400612 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Sudama Regency |  | Distance from city centre: |  | 2.00KM from Diva Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Open Plot
West | NA | 45.00 M. Wide Road |  |  | Diva Shil Road/Sudama Regency
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot/Sudama Greens |  |  | Open Plot/Divine Heights
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.170178,73.046397
Location Link |  | https://maps.app.goo.gl/QkarxgWcYPKNEAt19
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3995.06
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.627
Total FSI availaible for the project |  |  |  | 4.727 |  |  |  | 4.727
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 18884.51
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Muncipal Cooperation (TMC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | S11/0240/21/TMC/TD-DP/TPS/4374/23 |  |  | Dated | 2023-04-18 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | S11/0240/21/TMC/TD-DP/TPS/4374/23 |  |  | Dated | 2023-04-18 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | S11/0240/21/TMC/TDD/4374/23 |  |  | Dated | 2023-04-18 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Gr(PT) + Stilt(PT) + 1st Floor + 2nd to 18th Floor + 19th (PT) Floor | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | TMC/CFO/M/HR/04/05 |  |  | Dated | 2023-04-13 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Gr + 1st to 19th Floor (Height 60.05 Mtrs) | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | Gr + 1st to 19th Floor (Height 60.05 Mtrs) |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 18884.51
Approved no of units |  |  | Flats - 337, Shops - 16
Approved no of Floors |  |  | Building 1 = Gr + 1st to 19th Floor
Proposed no of Floors |  |  | Building 1 = Gr + 1st to 19th Floor
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, etc. |  |  |  |  | https://www.squareyards.com/thane-residential-property/samrin-changuna-aangan/225289/project
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building 1 = Gr + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab, Brickwork upto 2 Floor Completed | , RCC upto 6 Slab, Brickwork upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab, Brickwork upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 22.79% |  | 54.53% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 6 | 30% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 2 | 10.53% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | B Wing = 1B + G + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5500 | [11 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 200000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 4400 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 16 |  | 7052.0226 |  | 10930.635
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 337 |  | 133192.4443 |  | 200222.4054
Total
Grand Total |  | 353 |  | 140244.4669 |  | 211153.0404
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Building 1
Ground Floor For Commercial, Entrance Lobby, Meter Room, Driver Room & Parking
1 |  | Shop | 474.1542 | 177.4919 | 651.6461 | 0 | 1010.0515 | 43.918 | 43.918 |  | 10.764
2 |  | Shop | 310.3261 | 101.7521 | 412.0782 | 0 | 638.7212 | 28.8522 | 28.8522
3 |  | Shop | 651.3296 | 214.4609 | 758.5601 | 0 | 1175.7681
4 |  | Shop | 247.4644 | 81.4792 | 328.9435 | 0 | 509.8625
5 |  | Shop | 194.1826 | 63.9855 | 258.1681 | 0 | 400.1605
6 |  | Shop | 133.4736 | 43.9451 | 177.4187 | 0 | 274.999
7 |  | Shop | 140.2549 | 47.001 | 187.2559 | 0 | 290.2467
8 |  | Shop | 269.3153 | 134.6038 | 403.9191 | 0 | 626.0746
9 |  | Shop | 280.0793 | 139.8567 | 419.9359 | 0 | 650.9007
10 |  | Shop | 160.7065 | 53.8792 | 214.5857 | 0 | 332.6079
11 |  | Shop | 174.6997 | 57.5121 | 232.2118 | 0 | 359.9282
12 |  | Shop | 664.1388 | 438.3165 | 810.2443 | 0 | 1255.8787
13 |  | Shop | 436.6955 | 144.2161 | 580.9116 | 0 | 900.4129
14 |  | Shop | 420.7648 | 138.6188 | 559.3836 | 0 | 867.0445
15 |  | Shop | 453.9179 | 149.5227 | 603.4406 | 0 | 935.3329
16 |  | Shop | 302.3608 | 150.9586 | 453.3194 | 0 | 702.6451
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Builder Saleable Area | Builder salable area loading and our loading is same 1.50
50%
Buidling 1 | [11 empty] | 10.764
1st Floor For Residential, Creche & Void
- |  | Void
-
-
-
-
-
-
-
-
1 |  | 1BHK | 369.6358 | 0 | 369.6358 | 0 | 554.4536 | 30.5633
2 |  | 1BHK | 370.6045 | 0 | 370.6045 | 0 | 555.9068
3 |  | 1.5BHK | 492.453 | 0 | 492.453 | 84.8203 | 823.4998 | 42.8988
4 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 214.3812 | 867.4582
5 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 399.8073 | 895.9496
6 |  | 1.5BHK | 492.453 | 0 | 492.453 | 710.0257 | 916.1859
7 |  | 1BHK | 370.6045 | 0 | 370.6045 | 0 | 555.9068
8 |  | 1BHK | 369.6358 | 0 | 369.6358 | 0 | 554.4536
- |  | Creche
- |  | Void
2nd to 7th, 9th to 12th & 14th to 17th Floor | [7 empty] | 14
1 |  | 1.5BHK | 485.4564 | 0 | 485.4564 | 0 | 728.1846 |  | 5905.096 | 1.4976
2 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518 |  | 6679.8619 | 1.503
3 |  | 1BHK | 319.4755 | 0 | 319.4755 | 0 | 479.2133 |  | 6677.6113
4 |  | 1BHK | 319.4755 | 0 | 319.4755 | 0 | 479.2133 |  | 6677.6113
5 |  | 1BHK | 322.7047 | 0 | 322.7047 | 0 | 484.0571 |  | 6610.7906 | 1.4998
6 |  | 1.5BHK | 492.6683 | 0 | 492.6683 | 0 | 739.0024 |  | 5818.6548 | 1.5
7 |  | 1BHK | 386.1047 | 0 | 386.1047 | 0 | 579.157 |  | 5525.2719
8 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329 |  | 5659.3804 | 1.4989
9 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944 |  | 5657.7648
10 |  | 1BHK | 320.8748 | 0 | 320.8748 | 0 | 481.3123 |  | 6648.4905
11 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342 |  | 6615.2037
12 |  | 1.5BHK | 492.453 | 0 | 492.453 | 0 | 738.6795 |  | 5821.1985
13 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978 |  | 5402.025 | 1.4981
14 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978 |  | 5402.025
15 |  | 1.5BHK | 492.453 | 0 | 492.453 | 0 | 738.6795 |  | 4332.0547
16 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342 |  | 6615.2037
17 |  | 1BHK | 320.8748 | 0 | 320.8748 | 0 | 481.3123 |  | 6648.4905
18 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944 |  | 5657.7648
19 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329 |  | 5659.3804
8th & 13th Floor (Part Refuge Area) | [8 empty] | 5500
1 |  | 1.5BHK | 485.4564 | 0 | 485.4564 | 0 | 728.1846 |  | 4005015.3
2 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518 |  | 2634785.01
3 |  | 1BHK | 319.4755 | 0 | 319.4755 | 0 | 479.2133 |  | 2635673.04
4 |  | 1BHK | 319.4755 | 0 | 319.4755 | 0 | 479.2133 |  | 2635673.04
5 |  | 1BHK | 322.7047 | 0 | 322.7047 | 0 | 484.0571 |  | 2662313.94
6 |  | 1.5BHK | 492.6683 | 0 | 492.6683 | 0 | 739.0024 |  | 4064513.31
7 |  | 1BHK | 386.1047 | 0 | 386.1047 | 0 | 579.157 |  | 3185363.61
8 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329 |  | 3109881.06
9 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944 |  | 3110769.09
10 |  | 1BHK | 320.8748 | 0 | 320.8748 | 0 | 481.3123 |  | 2647217.43
11 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342 |  | 2660537.88
12 |  | 1.5BHK | 492.453 | 0 | 492.453 | 0 | 738.6795 |  | 4062737.25
13 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978 |  | 4377987.9
14 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978
15 |  | Refuge Area
16 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342
17 |  | 1BHK | 320.8748 | 0 | 320.8748 | 0 | 481.3123
18 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944
19 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329
18th Floor (Part Society Office 1, 2, Fitness Centre & Refuge Area)
1 |  | 1.5BHK | 485.4564 | 0 | 485.4564 | 0 | 728.1846
2 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
3 |  | 1BHK | 319.4755 | 0 | 319.4755 | 0 | 479.2133
4 |  | 1BHK | 319.4755 | 0 | 319.4755 | 0 | 479.2133
5 |  | 1BHK | 322.7047 | 0 | 322.7047 | 0 | 484.0571
6 |  | 1.5BHK | 492.6683 | 0 | 492.6683 | 0 | 739.0024
7 |  | 1BHK | 386.1047 | 0 | 386.1047 | 0 | 579.157
8 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329
9 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944
10 |  | Society Office 2
11 |  | Fitness Centre
12 |  | 1.5BHK | 492.453 | 0 | 492.453 | 0 | 738.6795
13 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978
14 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978
15 |  | Refuge Area
16 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342
17 |  | Society Office 1
18 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944
19 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329
19th Floor (Part Terrace Area)
1 |  | Terrace Area
2
3
4
5
6
7
8 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329
9 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944
10 |  | 1BHK | 320.8748 | 0 | 320.8748 | 0 | 481.3123
11 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342
12 |  | 1.5BHK | 492.453 | 0 | 492.453 | 0 | 738.6795
13 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978
14 |  | 1.5BHK | 530.6652 | 0 | 530.6652 | 0 | 795.9978
15 |  | 1.5BHK | 492.453 | 0 | 492.453 | 0 | 738.6795
16 |  | 1BHK | 322.4894 | 0 | 322.4894 | 0 | 483.7342
17 |  | 1BHK | 320.8748 | 0 | 320.8748 | 0 | 481.3123
18 |  | 1BHK | 377.0629 | 0 | 377.0629 | 0 | 565.5944
19 |  | 1BHK | 376.9553 | 0 | 376.9553 | 0 | 565.4329
Remarks:
* | Construction work is in process at the time of visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram Lambore |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Changuna Aangan
Layout :
Google Map :
Formulas:
Dawale = [Dawale, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F122: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H165: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate