## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | Ambalal Bhanji Gami
Name of the builder company |  |  |  | Ambalal Bhanji Gami
Name of the Project |  |  |  | Gami Ved
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Vinod – 9594616299
Site Person - Contact Details (Name & Contact No.) |  |  |  | 8286627211
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | Shree Balaji Co.Op Housing Society | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700051520 |  |  |  | #N/A |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Gami Ved, Plot No.13, Sector 18, Existing Building Name Shree Balaji Co.Op Housing Society, near Shiv Shakti Chs/Ajinkyatara CHS, Manoj Bhavsar Rd, Shiv Prasad Society, Nerul, Navi Mumbai, Thane, Thane - 400706. | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 13, Sector 18, Existing Building Name Shree Balaji Co.Op Housing Society | [9 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Shiv Prasad Society | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Manoj Bhavsar Rd |  | Locality/Village |  | Nerul | [5 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Navi Mumbai |  | District |  | Thane | [5 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Thane |  | Pin Code |  | 400706 | [8 empty] | Mahad | Daund
Nearby Landmark |  | Shiv Shakti Chs/Ajinkyatara CHS |  | Distance from city centre: |  | 1.2KM from Nerul Railway Station | [8 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [10 empty] | Mangaon | Ambegaon
[15 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [10 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [10 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [10 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Shivshakti Apartment
West | NA | Other Plot |  |  | Ajinkyatara CHS
North | NA | 15M Wide Rd |  |  | Manoj Bhavsar Rd/New Mangalmurti Chs
South | NA | Other Plot |  |  | Shiv Sagar Society
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.035519, 73.009722
Location Link |  | https://goo.gl/maps/iwSN2Tf8YYCnQs7L9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2024
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 1.798
Total FSI availaible for the project |  |  |  | 4.798
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 9711.216
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Municipal Corporation (NMMC)
Layout Approval No |  | NRV/A/17162 |  |  | Dated | 2023-04-11
Approved Floor plan No. |  | NRV/A/17162 |  |  | Dated | 2023-04-11
Commencement-CC No Valid Up to: |  | NMMC/TPO/BP/17162/2023 |  |  | Dated | 2023-04-11
St + 1st to 30th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9711.216
Approved no of units |  |  | Rehab Flats - 100, Sale Flats = 70, Society Share -1, NMMC - 1, Cidco Share - 1.
Approved no of Floors |  |  | St + 1st to 30th Floor
Proposed no of Floors |  |  | St + 1st to 30th Floor
Expected Completion |  |  | As per RERA - 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Jogging Track, Gymnasium, Senior Citizen Area, Sky High Garden or Roof Top Garden, Kid's Play Area, Yoga Area, Swimming Pool, Sit Out Area.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | St + 1st to 30th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 10 Floor Completed | , External Plaster upto 20 Floor, Flooring upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 30 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 75% |  | 90% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 31 | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 66.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 33.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 18000 |  |  | RATE 18000 by TRUPTI VERBAL on 23/06/2025
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor |  |  |  |  | 50
Development Charges
Club Charges |  |  |  |  | 100000
Legal Charges
Gas Connection Charges
Water, MSEB, Development Charges |  |  |  |  | 40000
Society Formation Charges + Infrastructure + Maintanence |  |  |  |  | 150000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 14400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Society Share |  | 1 |  | 204.0316 |  | 316.249
Cidco Share |  | 1 |  | 239.3375 |  | 370.9732
NMMC Share |  | 1 |  | 100.4819 |  | 155.747
Sale |  | 70 |  | 39489.5854 |  | 61208.8574
Rehab |  | 100 |  | 32175.5335 |  | 49872.077
Total |  | 173 |  | 72208.97 |  | 111923.9035
Grand Total |  | 173 |  | 72208.97 |  | 111923.9035
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
45%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Sale / Rehab | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Ground Floor For Entrance Lobby, Meter Room, Fire Control Room & Parking
1st Floor For Residential, Fitness Centre, Society Office, Driver Room & Swiming Pool | [8 empty] | 10.764
1 | Sale | 1BHK | 505.8004 | 0 | 783.9906 | 1st Floor For Residential, Fitness Centre, Society Office, Driver Room & Swiming Pool |  | 44.97 | 35.895 | 18750.2258
2 | Cidco Share | 1RK | 239.3375 | 0 | 370.9732 |  |  | 21.22
3 | Sale | 1BHK | 505.8004 | 0 | 783.9906 |  |  |  |  | 15944.0696
4 | NMMC Share | Room | 100.4819 | 0 | 155.747 |  |  | 21.22
5 | Society Share | Room | 204.0316 | 0 | 316.249
2nd to 6th, 8th to 11th, 13th to 16th & 18th Floor For Residential | [9 empty] | 15000
1 | Rehab | 1BHK | 308.4639 | 0 | 478.1191 | 2nd to 6th, 8th to 11th, 13th to 16th & 18th Floor For Residential |  | 5.0312 |  | 7171786.791 | 30745.4762
2 | Sale | 2BHK | 610.8355 | 0 | 946.795 |  |  |  |  | 14201924.724
3 | Rehab | 1BHK | 308.3348 | 0 | 477.9189 |  |  |  |  | 7168783.635
4 | Rehab | 1BHK | 308.3348 | 0 | 477.9189 |  |  |  |  | 7168783.635
5 | Sale | 2BHK | 610.8355 | 0 | 946.795 |  |  |  |  | 14201924.724
6 | Rehab | 1BHK | 308.4639 | 0 | 478.1191 |  |  |  |  | 7171786.791
7th, 12th & 17th Floor (Part Refuge Area)
1 | Rehab | 1BHK | 308.4639 | 0 | 478.1191 | 7th, 12th & 17th Floor (Part Refuge Area)
2 | Sale | 2BHK | 610.8355 | 0 | 946.795 | 7th, 12th & 17th Floor (Part Refuge Area)
3 | Rehab | 1BHK | 308.3348 | 0 | 477.9189 | 7th, 12th & 17th Floor (Part Refuge Area) |  |  |  | 14201924.724
4 | Rehab | 1BHK | 308.3348 | 0 | 477.9189 | 7th, 12th & 17th Floor (Part Refuge Area)
5 | Sale | 2BHK | 610.8355 | 0 | 946.795 | 7th, 12th & 17th Floor (Part Refuge Area)
6 | Rehab | 1BHK | 308.4639 | 0 | 478.1191 | 7th, 12th & 17th Floor (Part Refuge Area)
19th to 21st & 23rd to 26th Floor
1 | Rehab | 1BHK | 349.9592 | 0 | 542.4367 | 19th to 21st & 23rd to 26th Floor
2 | Sale | 2BHK | 610.8355 | 0 | 946.795 | 19th to 21st & 23rd to 26th Floor |  |  | 15526.0646 | 13730.5333
3 | Rehab | 1BHK | 350.3144 | 0 | 542.9873 | 19th to 21st & 23rd to 26th Floor
4 | Rehab | 1BHK | 350.3144 | 0 | 542.9873 | 19th to 21st & 23rd to 26th Floor
5 | Sale | 2BHK | 610.8355 | 0 | 946.795 | 19th to 21st & 23rd to 26th Floor
6 | Rehab | 1BHK | 349.9592 | 0 | 542.4367 | 19th to 21st & 23rd to 26th Floor
22nd Floor (Refuge Area@ Mid Landing)
1 | Rehab | 1BHK | 349.9592 | 0 | 542.4367 | 22nd Floor (Refuge Area@ Mid Landing)
2 | Sale | 2BHK | 610.8355 | 0 | 946.795 | 22nd Floor (Refuge Area@ Mid Landing)
3 | Rehab | 1BHK | 350.3144 | 0 | 542.9873 | 22nd Floor (Refuge Area@ Mid Landing)
4 | Rehab | 1BHK | 350.3144 | 0 | 542.9873 | 22nd Floor (Refuge Area@ Mid Landing)
5 | Sale | 2BHK | 610.8355 | 0 | 946.795 | 22nd Floor (Refuge Area@ Mid Landing)
6 | Rehab | 1BHK | 349.9592 | 0 | 542.4367 | 22nd Floor (Refuge Area@ Mid Landing)
27th Floor (Refuge Area @ Mid Landing)
1 | Sale | 1BHK | 372.3483 | 0 | 577.1398 | 27th Floor (Refuge Area @ Mid Landing)
2 | Sale | 2BHK | 583.3012 | 0 | 904.1168 | 27th Floor (Refuge Area @ Mid Landing)
3 | Sale | 1BHK | 367.0524 | 0 | 568.9312 | 27th Floor (Refuge Area @ Mid Landing) |  |  |  | 15907.0195
4 | Sale | 1BHK | 367.0524 | 0 | 568.9312 | 27th Floor (Refuge Area @ Mid Landing) |  |  |  | 15907.0195
5 | Sale | 2BHK | 583.3012 | 0 | 904.1168 | 27th Floor (Refuge Area @ Mid Landing)
6 | Sale | 1BHK | 372.3483 | 0 | 577.1398 | 27th Floor (Refuge Area @ Mid Landing) |  |  |  | 15893.8948
28th & 30th Floor
1 | Sale | 1BHK | 372.3483 | 0 | 577.1398 | 28th & 30th Floor
2 | Sale | 2BHK | 583.3012 | 0 | 904.1168 | 28th & 30th Floor
3 | Sale | 1BHK | 367.0524 | 0 | 568.9312 | 28th & 30th Floor
4 | Sale | 1BHK | 367.0524 | 0 | 568.9312 | 28th & 30th Floor
5 | Sale | 2BHK | 583.3012 | 0 | 904.1168 | 28th & 30th Floor
6 | Sale | 1BHK | 372.3483 | 0 | 577.1398 | 28th & 30th Floor
29th Floor For Recreational
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Recommended Rates of the Property have been revised on 23/06/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Gami Ved
Layout :
Google Map :
Formulas:
Nerul = [Nerul, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC