## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/S. Eiffel Developers & Realtor Ltd
Name of the builder company |  |  |  |  | M/S. Eiffel Developers & Realtor Ltd
Name of the Project |  |  |  |  | Xrbia Express City
Contect Details ( Name & Contect No.) |  |  |  |  | Mr. Ravikany (8291373191/8291373199)
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No. |  |  |  |  | Phase 1 (PP3, QQ12, QQ16, QQ21) - P52000007138 Phase 2 (PP7, QQ13, QQ17, QQ9) - P52000011789 Phase 4 (PP1, PP2) - P52000008195
Approved Layout Plan : |  | Not Legible |  |  |  |  | Dated | 13/10/2014.
Project location details |  | Xrbia Express City Phase I, S.NO.91/1, 91/2, 91/3, 91/5, 91/6, 91/7A/1, 91/8, 91/9, 91/7A/2, & 91/13, New Lonavala, Madap, Tal- Khalapur, Dist- Raigad.
S.NO. |  | 91/1, 91/2, 91/3, 91/5, 91/6, 91/7A/1, 91/8, 91/9, 91/7A/2, & 91/13. |  |  | Locality |  | Madap
Road |  | Mada Internal Road |  |  | District |  | Raigad.
City |  | Raigad. |  |  | Pin Code |  | 410 203.
Near by Landmark |  | Vijay Galaxy |  |  | Distance from city centre: |  | About 14 Km from Lowjee Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Open |  | Mahad Village |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 18.825522, 73.234281
Location Link |  | https://goo.gl/maps/WprR2UVWQpEL9CHE8
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 110840
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | NA
Total FSI availaible for the project |  |  |  |  | 1.1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 104245.02
Total number of Buildings |  |  |  |  | 22 Buildings
Approval Detail : Plan approval
Layout Approval No |  | Not Legible |  |  |  | Dated | 13/10/2014.
Building plan approval No |  | Not Legible |  |  |  | Dated | 13/10/2014.
C.certificate No |  | MS/L.N.A.1(B)/P.K.111/2014 Valid Up to: Plinth Level |  |  |  | Dated | 30/10/2014.
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 30/10/2014. |  | Expected Completion |  | 2023-03-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 104245.02 |  | Approved no of units residential |  |  | 872- Flats
Approved no of Floors |  | Gr. + 1st to 7th Floor (Duplex Buildings) |  |  | No of floors at site : See Construction details
Proposed no of Floors |  | PP1 = P + 1st to 12th Floor PP2 = P + 1st to 14th Floor PP3 = P + 1st to 12th Floor PP7 = P + 1st to 14th Floor |  |  |  | QQ9 = P + 1st to 12th Floor QQ12 = P + 1st to 14th Floor QQ13 = P + 1st to 12th Floor QQ16 = P + 1st to 14th Floor QQ17 = P + 1st to 12th Floor QQ21 = P + 1st to 14th Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building No- PP1 = P + 1st to 12th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% |  | 10% |  | 45% |  | Excavation in process | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed | 12
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 12
Construction details: |  | Building No- QQ17 = P + 1st to 12th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% |  | 16.15% |  | 49.62% |  | Excavation in process | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed | 12
RCC |  | 2 | 15.38% | [5 empty] | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 12
Construction details: |  | Building No- PP2 & PP7 = P + 1st to 14th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% |  | 10% |  | 45% |  | Excavation in process | 7
Plinth |  | 14 | 100% | [5 empty] | Excavation Completed | 14
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 10.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 14
Construction details: |  | Building No - PP3 = P + 1st to 12th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% |  | 28.46% |  | 58.85% |  | Excavation in process | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed | 12
RCC |  | 6 | 46.15% | [5 empty] | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 12
Construction details: |  | Building No- QQ9 = P + 1st to 12th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% |  | 29.71% |  | 59.68% |  | Excavation in process | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed | 12
RCC |  | 6 | 46.15% | [5 empty] | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 2 | 16.67% | [5 empty] | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 12
Construction details: |  | Building No- QQ12 & QQ21 = P + 1st to 14th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 7 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 7 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% |  | 37.75% |  | 65.5% |  | Excavation in process | 7
Plinth |  | 14 | 100% | [5 empty] | Excavation Completed | 14
RCC |  | 9 | 60% | [5 empty] | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 50% | [5 empty] | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 10.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 14
Construction details: |  | Building No- QQ13 = P + 1st to 12th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% |  | 51.86% |  | 74.52% |  | Excavation in process | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed | 12
RCC |  | 9 | 69.23% | [5 empty] | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 8 | 66.67% | [5 empty] | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 8 | 66.67% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 41.67% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 9
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 12
Construction details: |  | Building No- QQ16 = P + 1st to 14th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% |  | 34.55% |  | 63.14% |  | Excavation in process | 7
Plinth |  | 14 | 100% | [5 empty] | Excavation Completed | 14
RCC |  | 8 | 53.33% | [5 empty] | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 6 | 42.86% | [5 empty] | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 10.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 14
Construction details: |  | Building No- PP4 To PP6 & QQ10, QQ11, QQ14, QQ15, QQ18 to QQ20, QQ22, QQ23 = Gr + 1st to 7th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Carpet area) | [5 empty] | 5200
Floor rise rate Per Sq. Ft. | [5 empty] | Rs. 75 from 2nd floor
Society formation charges | [5 empty] | 1,20,000/-
Recommended rate of Parking | [5 empty] | 50000/-
Development charges | [5 empty] | 500000
Valuation as per Government reckoners rates | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 4160
Building details floor wise
Details of Flats in Building
Sr. | Flat No. | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | PLC Y/N
Building No- PP1 To PP7
Typical Duplex Floors( Gr.-1st, 2nd-3rd, 4th-5th & 6th-7th)
1 | 1 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA | 98000
2 | 2 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
3 | 3 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
4 | 4 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
5 | 5 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
6 | 6 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
7 | 7 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
8 | 8 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
9 | 9 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
10 | 10 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
11 | 11 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
12 | 12 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
13 | 13 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
14 | 14 | 2BHK Duplex | 621 | 0 | 621 | 80 | 980.45 | NA
Building No- QQ9 To QQ23
Duplex Floor (Gr.-1st)
15 | 1 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
16 | 2 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
17 | 3 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
18 | 4 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
19 | 5 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
20 | 6 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
21 | 7 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
22 | 8 | 3 BHK Duplex | 828 | 0 | 828 | 159 | 1280.1 | NA
Typical Duplex Floors( 2nd-3rd, 4th-5th & 6th-7th)
23 | 1 | 3 BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
24 | 2 | 3 BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
25 | 3 | 3 BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
26 | 4 | 3 BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
27 | 5 | 3 BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
28 | 6 | 3 BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
29 | 7 | 3BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
30 | 8 | 3BHK Duplex | 807 | 0 | 807 | 106 | 1223.15 | NA
Remark :
Building QQ17 |  |  |  |  | Construction work was same as visit (14/03/2023).
Building QQ13 |  |  |  |  | Construction work was same as visit (13/06/2023).
Building QQ12 |  |  |  |  | Construction work was stopped. Construction work was same as visit (13/06/2023).
Building QQ16 |  |  |  |  | Construction work was stopped. Construction work was same as visit (20/12/2022).
Building PP3 |  |  |  |  | Construction work was stopped. Construction work was same as visit (20/12/2022).
Building PP1, PP2, PP7, QQ9 & QQ21 |  |  |  |  | Construction work was stopped. Construction work was same as visit (23/02/2021).
Building PP4 To PP6 & QQ10, QQ11, QQ14, QQ15, QQ18 to QQ20, QQ22, QQ23 |  |  |  |  | Work not yet Started.
2. We considered saleable area as per our calculation. 3. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 4. We considered construction percentage as per proposed no of Floor. Please provide revised plan. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. Please provide revised CC. 9. As per RERA, completion period of project Xrbia Express City is expired on 30/03/2023 but still project is under construction. 10. Since the project has received first CC on 30/10/2014., But construction work of Xrbia Express City is under construction. 11. The Project is not available on Rera site. (checked on Date 11/06/2025) 8. On Site, we meet Mr. Mohit : 8237985177. | [9 empty] | 2023-03-30
Proposed no of Floors |  | PP1 = P + 12 PP2 = P + 14 PP3 = P + 12 PP7 = P + 14 |  |  |  | QQ9 = P + 12 QQ12 = P + 14 QQ13 = P + 12 QQ16 = P + 14 QQ17 = P + 12 QQ21 = P + 14
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area. | [9 empty] | Phase 4 (PP1, PP2)
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency | [9 empty] | Phase 1 (PP3, QQ12, QQ16, QQ21) - P52000007138
Phase 2 (PP7, QQ13, QQ17, QQ9) - P52000011789
Phase 4 (PP1, PP2)
PHOTOGRAPHS OF PROPERTY : Xrbia Express City Phase I
Google Map :
PP3
PP3
QQ12
QQ16
PP7
QQ13
QQ09
QQ17

## PP3
Particulars | totaL floor | 12
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 23.0769 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 13 | 3 | 0 | Progress |  |  | 10 | 9.2308 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 6.9231 | 0 | 0 | 0 | 0 | 0
| 12 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 12 | 0 | 0
Flooring | Total Floor | completed Floor
| 12 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 12 | 0 |  | RCC | 9.2308 | 6.9231
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 12 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 19.2308 | 36.9231

## QQ12, QQ21
Particulars | totaL floor | 14
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 60 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 15 | 9 | 42.8571 | Progress |  |  | 10 | 24 | 6.4286 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 18 | 6.4286 | 0 | 0 | 0 | 0
| 14 | 6 | 0
plaster | Total Floor | completed Floor | 0
| 14 | 0 | 0
Flooring | Total Floor | completed Floor
| 14 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 14 | 0 |  | RCC | 24 | 18
Finishing | Total Floor | completed Floor |  | Bricks | 6.4286 | 6.4286
| 14 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 40.4286 | 54.4286

## QQ13
Particulars | totaL floor | 12
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 69.2308 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 13 | 9 | 58.3333 | Progress |  |  | 10 | 27.6923 | 8.75 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 20.7692 | 8.75 | 0 | 0 | 0 | 0
| 12 | 7 | 0
plaster | Total Floor | completed Floor | 0
| 12 | 0 | 0
Flooring | Total Floor | completed Floor
| 12 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 12 | 0 |  | RCC | 27.6923 | 20.7692
Finishing | Total Floor | completed Floor |  | Bricks | 8.75 | 8.75
| 12 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 46.4423 | 59.5192

## QQ16
Particulars | totaL floor | 14
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 33.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 15 | 5 | 21.4286 | Progress |  |  | 10 | 13.3333 | 3.2143 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 10 | 3.2143 | 0 | 0 | 0 | 0
| 14 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 14 | 0 | 0
Flooring | Total Floor | completed Floor
| 14 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 14 | 0 |  | RCC | 13.3333 | 10
Finishing | Total Floor | completed Floor |  | Bricks | 3.2143 | 3.2143
| 14 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 26.5476 | 43.2143

## QQ9
Particulars | totaL floor | 12
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 46.1538 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 13 | 6 | 16.6667 | Progress |  |  | 10 | 18.4615 | 2.5 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 13.8462 | 2.5 | 0 | 0 | 0 | 0
| 12 | 2 | 0
plaster | Total Floor | completed Floor | 0
| 12 | 0 | 0
Flooring | Total Floor | completed Floor
| 12 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 12 | 0 |  | RCC | 18.4615 | 13.8462
Finishing | Total Floor | completed Floor |  | Bricks | 2.5 | 2.5
| 12 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 30.9615 | 46.3462

## Note
12/10/2020. | Pratiksha

## Valuation
12/10/2020. | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing | Xrbia Express City | 2BHK (Duplex) | 666 | 999 | 4504.5045 | 4500000
| Housing | Xrbia Express City | 2BHK (Duplex) | 614 | 921 | 4800.2172 | 4421000
| 99Acres | Xrbia Express City | 2BHK (Duplex) | 630 | 945 | 4539.6825 | 4290000
| 99Acres | Xrbia Express City | 3BHK | 842.6667 | 1264 | 4459.6519 | 5637000
| Average |  |  |  |  | 4576.014
| Valuation Adopted |  |  |  |  | 4600

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0