## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | Lodha Group
Name of the builder company |  |  |  | M/s. Macrotech Developers Limited
Name of the Project |  |  |  | Lodha Woods Tower 6, 7, 8 & 9
Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Name / No of the Building |  |  |  | Tower 6 (Wing 6) Tower 7 (Wing 7) Tower 8 (Wing 8) Tower 9 (Wing 9)
Docouments Provided |  |  |  | Approved Plans, CC & EC
RERA Name & No. |  |  |  | Lodha Woods - Tower 6 (P51800046327) |  | Tower 6
|  |  |  | Lodha Woods - Tower 7 (P51800046118) |  | Tower 7
|  |  |  | Lodha Woods- Tower 8 (P51800046114) |  | Tower 8
|  |  |  | Kandivali Project (P51800056457) |  | Tower 9
Project location details |  | Lodha Woods Tower 6, 7, 8 & 9, Old CTS. No.174C & New CTS No. 174/C1, 174/C/2, 174/C/3 & 174/C/4, near White City, Akurli Road, Akurli, Kandivali East, Borivali, Mumbai - 400101.
Old CTS. No |  | 174C & New CTS No. 174/C1, 174/C/2, 174/C/3 & 174/C/4
Road |  | Akurli Road |  | Locality/Village |  | Akurli
City |  | Kandivali East |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400101
Nearby Landmark |  | White City |  | Distance from city centre: |  | 4.3 KM from Kandivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | MLCP Wing |  |  | Open Plot
West | NA | Wing A & B |  |  | White City
North | NA | Amenity Space |  |  | Open Plot
South | NA | Wing 5, R.G & Fiteness Center |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.201436,72.878226
Location Link |  | https://goo.gl/maps/Pkde9rMC5bdWgVLu5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 34911.01 |  |  |  | 35947.58
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 2.5229
Total FSI availaible for the project |  |  |  | 3.5229
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 122987.61 |  |  |  | 117516.65
Total number of Buildings |  |  |  | 04 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM)
Layout Approval No |  | CHE/A-4300/BP(WS)/AR/337/9/Amend |  |  | Dated | 2025-03-07
Approved Floor plan No. (Tower 6 & 9) |  | CHE/A-4300/BP(WS)/AR/337/9/Amend |  |  | Dated | 2025-03-07
Approved Floor plan No. (Tower 7 & 8) |  | CHE/A-4300/BP(WS)/AR/337/7/Amend |  |  | Dated | 2024-06-19
Commencement Certificate No. Valid Up to: |  | CHE/A-4300/BP(WS)/AR/FCC/13/Amend |  |  | Dated | 2025-06-03
[5 empty] | Valid Upto Date | 2025-12-19
This C.C. is granted for work upto Plinth level of Wing 9, extension of FCC for Wing 6 comprising of Ground + 1st to 22nd upper floors + LMR + OHT & to re-endorse FCC for Wing 1 comprising of Ground + 1st to 40th upper floors + LMR & OHT, Wing 8 comprising of 1st to 21st + 22nd (Pt) upper floors + LMR + OHT, Multi-level car parking (MLCP) Wing - comprising of 2 level basements + LG for parking + UG for parking + 1st to 10th floors for parking + LMR & OHT and for Fitness Center for entire work, Wing 5 & 7 comprising of Gr + 1st to 22nd (Pt) upper floors + LMR & OHT as per approved amended plans dtd. 07.03.2025.
Fire NOC No. Valid Up to: |  | CHE/A-4300/BP(WS)/AR/CFO/1/New |  |  | Dated | 2024-12-26
Wing 6, 7 & 8 = Gr + 1st to 22nd Floor (Total Height = 69.90 mtrs.)
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/INFRA2/402907/2022 |  |  | Dated | 2023-02-23
CTS No. 174/C1, 174/C/2, 174/C/3 & 174/C/4 Proposed BUA = 232966.96 Sq.m Wing 6 to 9 = Gr +1st to 22nd Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved Builtup Area of Tower 6, 7 & 8 (Sq.Mt) |  |  | 21734.04
Approved no of units |  |  | Flats - 315
Approved no of Floors |  |  | Tower 6 (Wing 6) = Gr +1st to 22nd Floor Tower 7 (Wing 7) = Gr + 1st to 22nd Floor Tower 8 (Wing 8) = Gr + 1st to 22nd Floor Tower 9 (Wing 9) = Gr + Service Floor + 1st to 18th Floor
Proposed no of Floors |  |  | Tower 6 (Wing 6) = Gr + 1st to 22nd Floor
Tower 7 (Wing 7) = Gr + 1st to 22nd Floor
Tower 8 (Wing 8) = Gr + 1st to 22nd Floor
Tower 9 (Wing 9) = Gr + Service Floor + 1st to 18th Floor
Expected Completion |  |  | As per RERA -Tower 6 = 30/11/2026 Tower 7 = 31/07/2027 Tower 8 = 30/11/2027 Tower 9 = 31/12/2028 |  |  |  |  | https://housing.com/in/buy/projects/page/279759-lodha-woods-tower-7-by-lodha-group-in-kandivali-west
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Parking, Swimming Pool, Gym, CCTV System, Designer Floor Lobby, 2/3 No. High Speed Lifts, Fire Fighting System, Kid's Play Area/Creche, Library Lounge/ Café, Jogging Track, Internal Road etc.
Violations Observed if any : |  |  | NA |  |  |  |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab Completed, Brickwork upto 18 Floor Completed, Internal Plaster upto 17.1 Floor Completed, External Plaster upto 15.3 Floor Completed.
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | All work Completed. OC Received.
Construction details: |  | Tower 6 (Wing 6) = Gr + 1st to 22nd Floor | [5 empty] | Piling Work in process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation in process | 11
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab Completed, Brickwork upto 18 Floor Completed, Internal Plaster upto 17.1 Floor Completed, External Plaster upto 15.3 Floor Completed. | [5 empty] | Excavation Completed | 22
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing in Process | 5.5
Excavation |  | 22 | 100% | 61.96% |  | 81.24% |  | Footing Completed | 11
Plinth |  | 22 | 100% |  |  |  |  | Basement 1 | 0
RCC (Including podiums) |  | 19 | 82.61% |  |  |  |  | Basement 2 | 0
Brickwork | Brickwork & Internal Plaster | 18 | 81.82% |  |  |  |  | Basement 3 | 0
Internal Plaster | Brickwork & Internal Plaster | 17.1 | 77.73% |  |  |  |  | Basement 4 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15.3 | 69.55% |  |  |  |  | Plinth in process | 16.5
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Plinth completed | 22
Painting & Wooden |  | 0 | 0% |  |  |  |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 15 Floor Completed, Painting upto 15 Floor Completed.
Building Common Amenities | Building Common Amenities | 0 | 0%
Possession |  | 0 | 0% |  |  |  |  | All work Completed. OC Received.
Construction details: |  | Tower 7 (Wing 7) = Gr + 1st to 22nd Floor | [5 empty] | Piling Work in process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation in process | 11
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 15 Floor Completed, Painting upto 15 Floor Completed. | [5 empty] | Excavation Completed | 22
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing in Process | 5.5
Excavation |  | 22 | 100% | 85.23% |  | 93.41% |  | Footing Completed | 11
Plinth |  | 22 | 100% |  |  |  |  | Basement 1 | 0
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Basement 2 | 0
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 3 | 0
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 4 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Plinth in process | 16.5
Flooring & Fitting | Flooring & Fitting | 15 | 68.18% |  |  |  |  | Plinth completed | 22
Painting & Wooden |  | 15 | 68.18% |  |  |  |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed, Brickwork upto 9 Floor Completed.
Building Common Amenities | Building Common Amenities | 0 | 0%
Possession |  | 0 | 0% |  |  |  |  | All work Completed. OC Received.
Construction details: |  | Tower 8 (Wing 8) = Gr + 1st to 22nd Floor | [5 empty] | Piling Work in process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation in process | 11
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed, Brickwork upto 9 Floor Completed. | [5 empty] | Excavation Completed | 22
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing in Process | 5.5
Excavation |  | 22 | 100% | 30.46% |  | 60.09% |  | Footing Completed | 11
Plinth |  | 22 | 100% |  |  |  |  | Basement 1 | 0
RCC (Including podiums) |  | 10 | 43.48% |  |  |  |  | Basement 2 | 0 |  | 1.15
Brickwork | Brickwork & Internal Plaster | 9 | 40.91% |  |  |  |  | Basement 3 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 4 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Plinth completed | 22
Painting & Wooden |  | 0 | 0% |  |  |  |  | Excavation work in process
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0% |  |  |  |  | All work Completed. OC Received.
Construction details: |  | Tower 9 (Wing 9) = Gr + Service Floor + 1st to 18th Floor | [5 empty] | Piling Work in process | 4.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 18 | Excavation in process | 9
Stage of construction: |  | Excavation work in process | [5 empty] | Excavation Completed | 18 |  | smith sir
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing in Process | 4.5
Excavation |  | 9 | 50% | 0% |  | 10% |  | Footing Completed | 9
Plinth |  | 0 | 0% |  |  |  |  | Basement 1 | 0
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Basement 2 | 0
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 3 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 4 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Plinth in process | 13.5
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Plinth completed | 18
Painting & Wooden |  | 0 | 0% | [7 empty] | 66.4587
Building Common Amenities | Building Common Amenities | 0 | 0%
Possession |  | 0 | 0%
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 16500 |  |  | 760000
Floor Rise Rate Per Sq.ft | [8 empty] | 16000 to 16500 | 2024-01-05
Development Charges
Provisional Building Common Area Maintenance (CAM) Charges for 18 months* |  |  |  |  | 70000 |  |  | Other Charges add by | smith | 2024-01-02
Provisional Federation Common Area Maintenance (CAM) Charges for 60 months* |  |  |  |  | 300000
Building protection deposit* |  |  |  |  | 40000
Utility/Infrastructure/Other charges |  |  |  |  | 350000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 13200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 6 (Wing 6) |  | 111 |  | 72857.9337 |  | 116572.694
Tower 7 (Wing 7) |  | 86 |  | 67277.2325 |  | 107643.5719
Tower 8 (Wing 8) |  | 86 |  | 68374.6976 |  | 109399.5162
Tower 9 (Wing 9) |  | 32 |  | 62959.6801 |  | 100735.4882
Total |  | 315 |  | 271469.5439 |  | 434351.2702 |  |  |  |  | 5.2237
Building Details Floor Wise | [10 empty] | 6.394
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor |  | 1
[5 empty] | 60% |  |  | 57.5595 | 2.5704 | 60.1299
Tower 6 (Wing 6) | [7 empty] | 10.764 | 14
Ground Floor For Entrance Lobby, Society Office, Meter Room & Parking | [7 empty] | 57.5595 | 2.5704 | 60.1299
1 |  | 2BHK | 651.7645 | 0 | 1042.8232 | Ground Floor For Entrance Lobby, Society Office, Meter Room & Parking
1st to 6th, 8th, 10th, 12th Floor 14th, 16th, 18th, 20th & 22nd Floor (15th, 17th, 19th, 21st & 23rd Floor As per Builder)
1 |  | 2BHK | 651.7645 | 0 | 1042.8232 | 1st to 6th, 8th, 10th, 12th Floor 14th, 16th, 18th, 20th & 22nd Floor (15th, 17th, 19th, 21st & 23rd Floor As per Builder) |  | 57.1835 | 2.6316 | 59.8151
2 |  | 2BHK | 654.3479 | 0 | 1046.9566
3 |  | 2BHK | 654.3479 | 0 | 1046.9566 |  |  | 8
4 |  | 2BHK | 660.8192 | 0 | 1057.3107
5 |  | 2BHK | 660.8192 | 0 | 1057.3107
7th, 9th, 11th Floor 13th, 15th, 17th, 19th & 21st Floor (14th, 16th, 18th, 20th & 22nd Floor as per Builder) (For Refuge Area at Mid Landing) | [9 empty] | 77.2163
1 |  | 2BHK | 651.7645 | 0 | 1042.8232 | 7th, 9th, 11th Floor 13th, 15th, 17th, 19th & 21st Floor (14th, 16th, 18th, 20th & 22nd Floor as per Builder) (For Refuge Area at Mid Landing) |  |  | 1st | 60.0647
2 |  | 2BHK | 654.3479 | 0 | 1046.9566
3 |  | 2BHK | 654.3479 | 0 | 1046.9566
4 |  | 2BHK | 660.8192 | 0 | 1057.3107
5 |  | 2BHK | 660.8192 | 0 | 1057.3107 |  |  | 77.3963 | 8.9315
Tower 7 (Wing 7) | [7 empty] | 59.7761
Ground Floor For Residential, Parking, Entrance Lobby, Meter & Panel Room
4 |  | 3BHK | 983.5228 | 0 | 1573.6365 | Ground Floor For Residential, Parking, Entrance Lobby, Meter & Panel Room
1st to 7th, 9th to 12th 13th 14th, 16th to 21st Floor (14th, 15th, 17th to 22nd Floor as per Builder)
1 |  | 2BHK | 780.1101 | 0 | 1248.1762 | 1st to 7th, 9th to 12th 13th 14th, 16th to 21st Floor (14th, 15th, 17th to 22nd Floor as per Builder)
2 |  | 2BHK | 780.1101 | 0 | 1248.1762 |  |  | 59.7761
3 |  | 2BHK | 775.9875 | 0 | 1241.58
4 |  | 2BHK | 775.9875 | 0 | 1241.58
8th Floor 15th Floor (16th Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 780.1101 | 0 | 1248.1762 | 8th Floor 15th Floor (16th Floor as per Builder) (Part Refuge Area)
2 |  | Refuge Area | [5 empty] | 59.7761
3 |  | 2BHK | 775.9875 | 0 | 1241.58
4 |  | 2BHK | 775.9875 | 0 | 1241.58
22nd Floor (23rd Floor as per Builder) (Part Refuge Area)
1 |  | 2.5BHK | 945.8531 | 0 | 1513.365 | 22nd Floor (23rd Floor as per Builder) (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 775.9875 | 0 | 1241.58
4 |  | 2BHK | 775.9875 | 0 | 1241.58
Tower 8 (Wing 8)
Ground Floor For Residential, Parking, Society Office, Meter & Panel Room
1 |  | 3BHK | 984.1364 | 0 | 1574.6182 | Ground Floor For Residential, Parking, Society Office, Meter & Panel Room
1st Floor For Residential
1 |  | 2BHK | 808.0373 | 0 | 1292.8597 | 1st Floor For Residential
2 |  | 2BHK | 808.0373 | 0 | 1292.8597
3 |  | 2BHK | 772.4677 | 0 | 1235.9483
4 |  | 2BHK | 772.4677 | 0 | 1235.9483
1st to 7th, 9th to 12th 13th 14th, 16th to 21st Floor (14th, 15th, 17th to 22nd Floor as per Builder)
1 |  | 2BHK | 808.0373 | 0 | 1292.8597 | 1st to 7th, 9th to 12th 13th 14th, 16th to 21st Floor (14th, 15th, 17th to 22nd Floor as per Builder)
2 |  | 2BHK | 808.0373 | 0 | 1292.8597
3 |  | 2BHK | 772.4677 | 0 | 1235.9483
4 |  | 2BHK | 772.4677 | 0 | 1235.9483
8th Floor 15th Floor (16th Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 808.0373 | 0 | 1292.8597 | 8th Floor 15th Floor (16th Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 808.0373 | 0 | 1292.8597
3 |  | Refuge Area
4 |  | 2BHK | 772.4677 | 0 | 1235.9483
22nd Floor (23rd Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 808.0373 | 0 | 1292.8597 | 22nd Floor (23rd Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 808.0373 | 0 | 1292.8597
3 |  | Refuge Area
4 |  | 2.5BHK | 938.2107 | 0 | 1501.1371
Tower 9 (Wing 9)
Ground Floor For Double Height Entrance Looby, Meter Room, Substation & Service Lobby
Service Floor Between Ground & 1st Floor
1st to 4th, 6th to 11th Floor 13th to 16th Floor (14th to 17th Floor As per Builder) For Residential | [7 empty] | 14
1 |  | 4BHK | 1859.7501 | 0 | 2975.6002 | 1st to 4th, 6th to 11th Floor 13th to 16th Floor (14th to 17th Floor As per Builder) For Residential
2 |  | 4BHK | 1858.7813 | 0 | 2974.0501
5th & 12th Floor (Part Refuge Area)
1 |  | 5BHK | 2689.4769 | 0 | 4303.163 | 5th & 12th Floor (Part Refuge Area)
2 |  | Refuge Area
17th Floor (18th Floor As per Builder)
1 |  | 5BHK Duplex With 18th Floor | 2760.6969 | 0 | 4417.115 | 17th Floor (18th Floor As per Builder)
2 |  | 5BHK Duplex With 18th Floor | 2760.5893 | 0 | 4416.9428 |  |  | 242.99
18th Floor (19th Floor As per Builder)
1 |  | 5BHK Duplex With 17th Floor |  |  |  | 18th Floor (19th Floor As per Builder)
2 |  | 5BHK Duplex With 17th Floor
Remarks:
* | Tower 6, 7 & 8 = Construction work is process at the time of Visit. Internal Visit not allowed. Tower 9 = Construction Stage is same as last visit dtd.21/03/2025. Construction Details taken from Mr. Rajendra Giri.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Verandah + Deck Area + Utility Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated latest approved floor plans & CC for Tower 7 & 8 (On 23/12/2023).
* | Recommended Rates/Other Charges of the Property have been revised on 05/01/2024.
* | We have added Tower 6 & updated approved latest approved CC on 10/05/2024
* | We have updated latest approved layout plan & floor plan for Tower 6 on 21/06/2024
* | We have updated latest approved floor plans for Tower 7 & 8 from MCGM site on 21/06/2024
* | We have updated CC from MCGM site on 15/01/2025. | [6 empty] | We have updated latest approved floor plans for Tower 6 from MCGM site on 13/03/2025.
* | We have updated revised CC on 28/02/2025.
* | As per the approved latest floor plan dtd.07/03/2025 of Wing 6, all flat (i.e 110 Nos.) are "I to R" flats. Please check from your end.
* | We have updated latest approved floor plans for Tower 6 from MCGM site on 13/03/2025.
* | We have added Tower 9 on 25/03/2025
* | We have updated approved Environmental Clearance Certificate on 29/03/2025
* | We have updated latest CC (On 20/06/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Rahul Salve |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Lodha Woods Tower 6, 7, 8 & 9
Layout :
Google Map :
Wing 1
Wing 2
Wing 3
Wing 6
Wing 5
Wing 4
Wing 8
Wing 7
Wing 9
Lodha Woods Tower 6, 7 & 8
Lodha Woods Tower 9
Wing 6
Wing 6
Wing 7
Wing 8
Wing 6

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted