## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-07 |  |  |  | 2025-05-28
Name of the builder group |  |  |  | Magus Infratech Private Limited
Name of the builder company |  |  |  | Magus Infratech Private Limited
Name of the Project |  |  |  | Magus City & Magus City Tower 2 Lunar
Contact Details ( Name & Contact No.) |  |  |  | Mr. Samarth Mokal (8369482733)
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Amit : 9867816059
Name / No of the Building |  |  |  | Building No.ESQ-2 |  | Selene -Tower 1
|  |  |  | Building No.ESQ-3 |  | Lunar -Tower 2
Docouments Provided |  |  |  | Approved Plans, CC, Fire Noc,
RERA No. |  |  |  | Magus City (P51700045444) |  | Building No.ESQ-2
|  |  |  | Magus City Tower 2 Lunar (P51700077802) |  | Building No.ESQ-3
Project location details |  | Magus City & Magus City Tower 2 Lunar, Plot No.1, near Chhatrapati Shivaji Maharaj Kridangan, Bhiwandi-Murbad Road, Asmeeta Textile Park, Kone, Kalyan West, Bhiwandi, Thane - 421311.
Plot No |  | 1
Locality |  | Asmeeta Textile Park
Road |  | Bhiwandi-Murbad Road |  | Village |  | Kone
City |  | Kalyan West |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421311
Nearby Landmark |  | Chhatrapati Shivaji Maharaj Kridangan |  | Distance from city centre: |  | 4.7KM from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Brown Associates
West | NA | Other Plot |  |  | Omkar plastic industries
North | NA | 22.00 M. Wide Internal Road |  |  | Internal Road
South | NA | Other Plot |  |  | Ravaria Industrial Complex
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.255279,73.10501
Location Link |  | https://goo.gl/maps/yhiGXtYHNK9kZSJh6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 230673.3 |  |  |  | 218532
Permissible FSI |  |  |  | 1 |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.25367 |  |  |  | -0.015409
Total FSI availaible for the project |  |  |  | 1.2537 |  |  |  | 0.98459
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 289189.182 |  |  |  | 215164.69
Total number of Buildings |  |  |  | 02 Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Industrial Development Corporation
Magus City
Layout Approval No |  | EE/SPA/KBI/B21851/2022 |  |  | Dated | 2022-04-07
Approved Floor plan No. |  | EE/SPA/KBI/B21851/2022 |  |  | Dated | 2022-04-07
Commencement-CC No Valid Up to: |  | EE/SPA/KBI/B21851/2022 |  |  | Dated | 2022-04-07
G + 1st to 14th Floor
Fire Noc No Valid Up to: |  | MIDC/Fire/B-10814 |  |  | Dated | 2022-03-30
Building No.ESQ-2 = G + 1st to 14th Floor (Height = 44.4 Mtrs)
Magus City Tower 2 Lunar
Layout Approval No. |  | EE/SPA/DOM/Plot No. 1/I/79540/2024 |  |  | Dated | 2024-10-09
Approved Floor plan No. |  | EE/SPA/DOM/Plot No. 1/I/79540/2024 |  |  | Dated | 2024-10-09
Commencement-CC No Valid Up to: |  | EE/SPA/DOM/Plot No. 1/I/79540/2024 |  |  | Dated | 2024-10-09
Building No.ESQ-3 = G + 1st to 19th Floor
Fire Noc No Valid Up to: |  | MIDC/Fire/P-303564 |  |  | Dated | 2024-08-28
Building No.ESQ-3 = G + 1st to 19th Floor (Height = 58.9 Mtrs)
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA |  | manually added esq 2 & 3bua only
NA
Building wise Construction details
Approved Buitup Area of Building No. ESQ-2 & 3(Sq.Mt) |  |  | 30060.53 |  |  |  |  | Doubt here
Approved no of units |  |  | Flats - 725
Approved no of Floors |  |  | Building No. ESQ-2 = G + 1st to 14th Floor Building No. ESQ-3 = G + 1st to 19th Floor |  |  |  |  | Doubt here
Proposed no of Floors |  |  | Building No. ESQ-2 = G + 1st to 15th Floor
Proposed no of Floors |  |  | Building No. ESQ-3 = G + 1st to 19th Floor
Expected Completion |  |  | As per RERA - 30/04/2027
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | https://housing-is-01.s3.amazonaws.com/6a32315a/9689f6a5c7e8c2da096b5b0ec7475399/original.pdf
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Natur Park, Cricket Turf, Multipurpose Court,Jogging Track,Kids Play Area, Gymnasium, Cricket Turf, Club House etc.
Violations Observed if any : |  |  | NA |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 12 Floor, Painting upto 12 Floor Completed | , Flooring upto 12 Floor, Painting upto 12 Floor
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | Completed | Completed
Construction details: |  | Building No. ESQ-2 = G + 1st to 15th Floor | [5 empty] | Piling Work in process | 3.75
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation in process | 7.5
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 12 Floor, Painting upto 12 Floor Completed | [5 empty] | Excavation Completed | 15
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing in Process | 3.75
Excavation |  | 15 | 100% | 87% |  | 94% |  | Footing Completed | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Basement 1 | 0
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Basement 2 | 0
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 3 | 0
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 4 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Plinth in process | 11.25
Flooring & Fitting | Flooring & Fitting | 12 | 80% |  |  |  |  | Plinth completed | 15
Painting & Wooden |  | 12 | 80% |  |  |  |  | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 2 Floor Completed | , RCC upto 4 Slab, Brickwork upto 2 Floor
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Excavation, Plinth
Possession |  | 0 | 0% |  |  |  |  | Completed | Completed
Construction details: |  | Building No. ESQ-3 = G + 1st to 19th Floor | [5 empty] | Piling Work in process | 4.75
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation in process | 9.5
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 2 Floor Completed | [5 empty] | Excavation Completed | 19
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Footing in Process | 4.75
Excavation |  | 19 | 100% | 18.79% |  | 51.53% |  | Footing Completed | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Basement 1 | 0
RCC (Including podiums) |  | 4 | 20% |  |  |  |  | Basement 2 | 0
Brickwork | Brickwork & Internal Plaster | 2 | 10.53% |  |  |  |  | Basement 3 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 4 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Plinth completed | 19
Painting & Wooden |  | 0 | 0%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | mis | visitor | market
Possession |  | 0 | 0%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6200
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection | [8 empty] | 5500-7000 | 5500 | 5500
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 4960
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details : | [7 empty] | Doubt in Count
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | 323
Building No. ESQ-2 |  | 402 |  | 106370.7629 |  | 159556.1444
Building No.ESQ-3 |  | 323 |  | 136412.172 |  | 204618.258 |  | 323
Total |  | 725 |  | 242782.9349 |  | 364174.4024
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor |  | 340
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 50% |  |  |  | 10.764
Magus City
Building No. ESQ-2
Ground Floor For Parking
1st to 6th, 8th to 12th & 14th Floor
1 |  | 0 | 230.4841 | 0 | 345.7262 | 1st to 6th, 8th to 12th & 14th Floor |  | 6074.1704
2 |  | 0 | 230.4841 | 0 | 345.7262 |  |  | 5999.9268
3 |  | 0 | 230.4841 | 0 | 345.7262
4 |  | 0 | 230.4841 | 0 | 345.7262
5 |  | 1 | 277.7812 | 0 | 416.6717
6 |  | 1 | 277.7812 | 0 | 416.6717
7 |  | 1 | 277.7812 | 0 | 416.6717
8 |  | 1 | 277.7812 | 0 | 416.6717
9 |  | 1 | 277.7812 | 0 | 416.6717
10 |  | 1 | 277.7812 | 0 | 416.6717
11 |  | 1 | 277.7812 | 0 | 416.6717
12 |  | 1 | 277.7812 | 0 | 416.6717
13 |  | 1 | 277.7812 | 0 | 416.6717
14 |  | 1 | 277.7812 | 0 | 416.6717
15 |  | 1 | 277.7812 | 0 | 416.6717
16 |  | 1 | 277.7812 | 0 | 416.6717
17 |  | 1 | 277.7812 | 0 | 416.6717
18 |  | 1 | 277.7812 | 0 | 416.6717
19 |  | 1 | 277.7812 | 0 | 416.6717
20 |  | 1 | 277.7812 | 0 | 416.6717
21 |  | 1 | 277.7812 | 0 | 416.6717
22 |  | 1 | 277.7812 | 0 | 416.6717
23 |  | 0 | 230.4841 | 0 | 345.7262
24 |  | 0 | 230.4841 | 0 | 345.7262
25 |  | 0 | 230.4841 | 0 | 345.7262
26 |  | 0 | 230.4841 | 0 | 345.7262
27 |  | 1 | 277.7812 | 0 | 416.6717
28 |  | 1 | 277.7812 | 0 | 416.6717
29 |  | 1 | 277.7812 | 0 | 416.6717
7th & 13th Floor (Part Refuge Area)
1 |  | 0 | 230.4841 | 0 | 345.7262 | 7th & 13th Floor (Part Refuge Area)
2 |  | 0 | 230.4841 | 0 | 345.7262
3 |  | 0 | 230.4841 | 0 | 345.7262
4 |  | 0 | 230.4841 | 0 | 345.7262
5 |  | 1 | 277.7812 | 0 | 416.6717
6 |  | 1 | 277.7812 | 0 | 416.6717
7 |  | 1 | 277.7812 | 0 | 416.6717
8 |  | 1 | 277.7812 | 0 | 416.6717
9 |  | 1 | 277.7812 | 0 | 416.6717
10 |  | 1 | 277.7812 | 0 | 416.6717
11 |  | 1 | 277.7812 | 0 | 416.6717
12 |  | 1 | 277.7812 | 0 | 416.6717
13 |  | 1 | 277.7812 | 0 | 416.6717
14 |  | 1 | 277.7812 | 0 | 416.6717
15 |  | 1 | 277.7812 | 0 | 416.6717
16 |  | 1 | 277.7812 | 0 | 416.6717
17 |  | 1 | 277.7812 | 0 | 416.6717
18 |  | 1 | 277.7812 | 0 | 416.6717
19 |  | 1 | 277.7812 | 0 | 416.6717
20 |  | 1 | 277.7812 | 0 | 416.6717
21 |  | 0 | 230.4841 | 0 | 345.7262
22 |  | 0 | 230.4841 | 0 | 345.7262
23 |  | 0 | 230.4841 | 0 | 345.7262
24 |  | 0 | 230.4841 | 0 | 345.7262
25 |  | 1 | 277.7812 | 0 | 416.6717
26 |  | 1 | 277.7812 | 0 | 416.6717 |  |  | 10.764
27 |  | 1 | 277.7812 | 0 | 416.6717
Magus City Tower 2 Lunar
Building No.ESQ-3
Ground Floor For Parking, Entrance Lobby, Society Office, Meter Room, Data Room, & Fire Tower | [7 empty] | 44.39
1st to 6th & 8th to 11th Floor For Residential
1 |  | 2BHK | 509.783 | 0 | 764.6746 | 1st to 6th & 8th to 11th Floor For Residential
2 |  | 2BHK | 509.783 | 0 | 764.6746
3 |  | 2BHK | 490.6231 | 0 | 735.9347 |  |  | 5524.0942
4 |  | 2BHK | 490.6231 | 0 | 735.9347
5 |  | 1BHK | 410.3237 | 0 | 615.4855
6 |  | 2BHK | 490.6231 | 0 | 735.9347
7 |  | 2BHK | 490.6231 | 0 | 735.9347
8 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 3128000
9 |  | 1BHK | 410.3237 | 0 | 615.4855
10 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  | 6841.4058
11 |  | 1BHK | 331.3159 | 0 | 496.9739
12 |  | 1BHK | 331.3159 | 0 | 496.9739
13 |  | 1BHK | 331.3159 | 0 | 496.9739
14 |  | 1BHK | 331.3159 | 0 | 496.9739
15 |  | 1BHK | 410.3237 | 0 | 615.4855
16 |  | 1BHK | 410.3237 | 0 | 615.4855
17 |  | 1BHK | 410.3237 | 0 | 615.4855
7th Floor For Residential (Part Refuge Area @ Mid Landing)
1 |  | 2BHK | 509.783 | 0 | 764.6746 | 7th Floor For Residential (Part Refuge Area @ Mid Landing)
2 |  | 2BHK | 509.783 | 0 | 764.6746
3 |  | 2BHK | 490.6231 | 0 | 735.9347
4 |  | 2BHK | 490.6231 | 0 | 735.9347
5 |  | 1BHK | 410.3237 | 0 | 615.4855
6 |  | 2BHK | 490.6231 | 0 | 735.9347
7 |  | 2BHK | 490.6231 | 0 | 735.9347
- |  | Refuge Area @ Mid Landing
8 |  | 1BHK | 410.3237 | 0 | 615.4855
9 |  | 1BHK | 410.3237 | 0 | 615.4855
10 |  | 1BHK | 410.3237 | 0 | 615.4855
11 |  | 1BHK | 331.3159 | 0 | 496.9739
12 |  | 1BHK | 331.3159 | 0 | 496.9739
13 |  | 1BHK | 331.3159 | 0 | 496.9739
14 |  | 1BHK | 331.3159 | 0 | 496.9739
15 |  | 1BHK | 410.3237 | 0 | 615.4855
16 |  | 1BHK | 410.3237 | 0 | 615.4855
17 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 6200
- |  | Refuge Area @ Mid Landing | [5 empty] | 6277.1802 | 4740982.272
12th & 17th Floor For Residential (Part Refuge Area) | [8 empty] | 4740982.272
1 |  | 2BHK | 509.783 | 0 | 764.6746 | 12th & 17th Floor For Residential (Part Refuge Area) |  |  | 4562795.016
2 |  | 2BHK | 509.783 | 0 | 764.6746 |  |  |  | 4562795.016
3 |  | 2BHK | 490.6231 | 0 | 735.9347 |  |  |  | 3816010.224
4 |  | 2BHK | 490.6231 | 0 | 735.9347 |  |  |  | 4562795.016
5 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 4562795.016
6 |  | 2BHK | 490.6231 | 0 | 735.9347 |  |  |  | 0
7 |  | 2BHK | 490.6231 | 0 | 735.9347 |  |  | 3899.3606 | 3816010.224
- |  | Refuge Area @ Mid Landing | [6 empty] | 3816010.224
8 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 3816010.224
9 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  | 6841.4058 | 3081238.056
10 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 3081238.056
11 |  | 1BHK | 331.3159 | 0 | 496.9739 |  |  |  | 3081238.056
12 |  | 1BHK | 331.3159 | 0 | 496.9739 |  |  |  | 3081238.056
13 |  | 1BHK | 331.3159 | 0 | 496.9739 |  |  |  | 3816010.224
14 |  | 1BHK | 331.3159 | 0 | 496.9739 |  |  |  | 3816010.224
15 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 3816010.224
16 |  | 1BHK | 410.3237 | 0 | 615.4855 |  |  |  | 0
17 |  | 1BHK | 410.3237 | 0 | 615.4855
- |  | Refuge Area
13th to 16th, 18th to 19th Floor
1 |  | 2BHK | 509.783 | 0 | 764.6746 | 13th to 16th, 18th to 19th Floor
2 |  | 2BHK | 509.783 | 0 | 764.6746
3 |  | 2BHK | 490.6231 | 0 | 735.9347
4 |  | 2BHK | 490.6231 | 0 | 735.9347
5 |  | 1BHK | 410.3237 | 0 | 615.4855
6 |  | 2BHK | 490.6231 | 0 | 735.9347
7 |  | 2BHK | 490.6231 | 0 | 735.9347
8 |  | 1BHK | 410.3237 | 0 | 615.4855
9 |  | 1BHK | 410.3237 | 0 | 615.4855
10 |  | 1BHK | 410.3237 | 0 | 615.4855
11 |  | 1BHK | 331.3159 | 0 | 496.9739
12 |  | 1BHK | 331.3159 | 0 | 496.9739
13 |  | 1BHK | 331.3159 | 0 | 496.9739
14 |  | 1BHK | 331.3159 | 0 | 496.9739
15 |  | 1BHK | 410.3237 | 0 | 615.4855
16 |  | 1BHK | 410.3237 | 0 | 615.4855
17 |  | 1BHK | 410.3237 | 0 | 615.4855
Remarks:
* | Construction work is in process at the time of Visit. Internal photo was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = RERA carpet Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised as per market inquiry on 13/06/2025
* | We have refered Approved CC & Layout plan from RERA Portal on 13/06/2025
* | We have added Magus City Tower 2 Lunar on 12/06/2025.
* | We have updated Fire Noc for Building No. ESQ-2 on 16/06/2025
* | We have updated Fire Noc for Building No. ESQ-3 on 19/06/2025
* | Please check for Environment Clearance Certificate.
* | Please provide revised CC & approved floor plans for Building No. ESQ-2.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Magus City & Magus City Tower 2 Lunar
Layout :
Google Map :
Formulas:
Selene -Tower 1 = [Selene -Tower 1, row above]
ESQ-2
ESQ-3
ESQ-2
ESQ-3

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted