## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 13/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/s. Shree Yashomati Builders & Developers
Name of the builder company |  |  |  |  | M/s. Shree Yashomati Builders & Developers
Name of the Project |  |  |  |  | Shaligram Township (Gut No.137)
Name & No. of the Building |  |  |  |  | Building No.1 (C wing ) - Type B3 Building No.3 (A, B wing) Building No.4 (A, B wing)
Contect Details ( Name & Contect No.) |  |  |  |  | 9225077199
RERA No. |  |  |  |  | Building No.1 (A, B, C wing ) = P99000025137
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | “Shaligram Township (Gut No.137)” Proposed Residential & Comm. Bldg On Land Bearing G. No.137 At. Village:Padgha, Tal. Palghar, Dist. Thane-401404
CTS No | 753 |  |  | Plot No. | NA | Locality | Padgha
Road | Padghe Road |  |  |  | District | Thane
City | Umroli West |  |  |  | Pin Code | 401404
Near by Landmark |  | Adore Homes |  |  | Distance from city centre: |  | About 2Km Distance From Umroli Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Buiding U/C |  | Road |  | Buiding U/C |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.750151,72.769759
Location Link |  | https://goo.gl/maps/XYrREZ6z7b2eHY1x7?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | NA
Permissible FSI |  |  |  |  | NA
Permissible TDR/Paid FSI |  |  |  |  | NA
Total FSI availaible for the project |  |  |  |  | NA
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | NA
Total number of Buildings |  |  |  |  | 03 Buildings (05 wings)
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  |  | Dated | NA
Building plan approval No |  | NA |  |  |  | Dated | NA
C.certificate No |  | NA Valid Up to: NA |  |  |  | Dated | NA
O. Certificate No.: NA |  |  |  |  | Date of approval: NA |  |  | Expiry date: NA
Commencement date of construction |  |  | NA |  | Expected Completion |  | 30/12/2024.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | NA |  | Approved no of units residential |  |  | NA
Approved no of Floors |  | Building No.1 (C wing ) - Type B3 = Ground (pt) + Stilt (pt) + 2nd Floor Building No.3 (A, B wing) = Stilt + 1st to 3rd Floor Building No.4 (A, B wing) = Stilt + 1st to 2nd Floor
Proposed no of Floors |  | Building No.1 (C wing ) - Type B3 = Ground (pt) + Stilt (pt) + 3rd Floor Building No.3 (A, B wing) = Stilt + 1st to 3rd Floor Building No.4 (A, B wing) = Stilt + 1st to 3rd Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: Building No.1 (C wing ) = Ground (pt) + Stilt (pt) +1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 73.33% |  | 88.33%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process | 1.5
Brickwork | Brickwork & Internal Plaster | 2 | 66.67% | [5 empty] | Excavation Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 2 | 66.67%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 66.67% | [5 empty] | Footing in Process | 0.75
Flooring & Fitting | Flooring & Fitting | 2 | 66.67% | [5 empty] | Footing Completed | 1.5
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process | 2.25
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 3
Possession |  | 0 | 0%
Construction details: Building No.3 (A, B wing) = Stilt + 1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed, Finishing upto 3 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 100% |  | 100%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process | 1.5
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Excavation Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 3 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Footing in Process | 0.75
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Footing Completed | 1.5
Painting & Wooden |  | 3 | 100% | [5 empty] | Plinth in process | 2.25
Building Common Amenities | Building Common Amenities | 3 | 100% | [5 empty] | Plinth completed | 3
Possession |  | 3 | 100%
Construction details: Building No.4 (A, B wing) = Stilt + 1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 60% |  | 81.67%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process | 1.5
Brickwork | Brickwork & Internal Plaster | 2 | 66.67% | [5 empty] | Excavation Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 2 | 66.67%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process | 0.75
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed | 1.5
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process | 2.25
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 3
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : NA
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 2400
Distress valuation of the property Per Sq. Ft. | [5 empty] | 1920
Remarks: 1. Bldg No. 3 (A & B) - All work completed. Please provide OC. Bldg No.4 (B) - Construction work was same as last visit (22/05/2023). Bldg No.1 (C) & 4 (A) - Construction work was same as last visit (07/04/2022). 2. Construction percentage given as per proposed no of Floors. 3. Notice we found on Site - Construction Should complete till March 2020, if not then Developer's agreement will get canceled. Still if any bank or customer is dealing with that project then it's there own responsibility. 4. As per RERA, completion period of project is expired on 30/12/2024 but still project is under construction. 4. Please provide revised approved CC of Building No. 1 & 4
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shaligram Township (Gut No.137)
Google Map :
Building No.3
Bldg No. 4
A Wing
Bldg No. 1
C Wing
Bldg No. 3
Bldg No. 4
B Wing

## B1
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 2
Particulars | total floor | 2
plinth | 10 | 10 | 100%
slab | 3 | 3 | 100% |  | Parking |  | Rate
Bricks | 2 | 2 | 100% |  | Palghar |  | 100000/-
plaster | 2 | 2 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 2 | 2 | 100% |  | Panvel |  | 300000/-
Wood & painting | 2 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 2 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 85% | 90% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B4
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 1.5 | 50% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 5 | 5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 70% | 80% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Adore Homes | 1RK | 230 | 333.5 | 2122.9385 | 708000
housing | Adore Homes | 1BHK | 325 | 471.25 | 2124.1379 | 1001000
housing | Adore Homes | 1BHK | 333 | 482.85 | 2124.8835 | 1026000
housing | Adore Homes | 2BHK | 499 | 723.55 | 2124.2485 | 1537000
Average |  |  |  |  | 2124.0521
Valuation Adopted |  |  |  |  | 2100