## Final Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-06
Name of the builder group |  |  |  | M/s. Jigar Enterprises
Name of the builder company |  |  |  | M/s. Jigar Enterprises
Name of the Project |  |  |  | Umiya Nakshtra Heights
Contect Details ( Name & Contect No.) |  |  |  | 8237202013/8369181294
Name / No of the Building |  |  |  | Phase II - Wing A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | Wing A = P51700021530 Wing B & C = P51700033734
Project location details |  | Umiya Nakshtra Heights, Survey/Hissa No.64/1/4 & Old S.No/Hissa no. 64/2, Proposed Panvel Highway, Katrap, Badlapur, Ambernath, Thane.
Survey/Hissa No |  | 64/1/4 & Old S.No/Hissa no. 64/2
Road |  | Proposed Panvel Highway |  | Locality/Village |  | Katrap
City |  | Badlapur |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Near by Landmark |  | Katrap Lake |  | Distance from city centre: |  | 2.1km from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.171752,73.22323
Location Link |  | https://goo.gl/maps/jN64RgBmCUcCDdpc8?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 8504.24
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.7382
Total FSI availaible for the project |  |  |  | 2.8382
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 24137.12
Total number of Buildings |  |  |  | 3 Wing
Approval Detail : Plan approval
Layout Approval No |  | KBNP/NRV/BD/1420-202 |  |  | Dated | 2022-02-16
Approved Floor plan No. (Wing A) |  | KBNP/NRV/BP/7351-92 |  |  | Dated | 05/10/2018.
Commencement Certificate No. (Wing A) |  | KBNP/NRV/BP/7351-92 |  |  | Dated | 05/10/2018.
Valid Up to: Wing A = St + Gr + 1st to 18th Floor
Approved Floor plan No. (Wing B & C) |  | KBNP/NRV/BD/1420-202 |  |  | Dated | 2022-02-16
Commencement Certificate No. Valid Up to: |  | KBNP/NRV/BP/1420/2021-2022 Unique No.202 |  |  | Dated | 2022-02-16
Wing B & C = St + Gr + 1st to 17th Floor
O. Certificate No.: |  | JVK/KBNP/NRV/2551/2023-2024 Approved upto : Wing A = Gr/St + 1st to 18th Floor Total Flats = 105 Nos. |  | Date of approval: | Dated | 2023-11-08
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 24137.12
Approved no of units |  |  | Flats - 275
Approved no of Floors |  |  | Wing A = St/Gr + 1st to 18th Floor Wing B & C =St/Gr + 1st to 17th Floor
Proposed no of Floors |  |  | Wing A = St/Gr + 1st to 18th Floor Wing B & C = St/Gr + 1st to 17th Floor
Expected Completion |  |  | Wing A & B = Completed As per RERA - Wing C = 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel
Construction details: |  | Wing A = (St/Gr + 1st to 18th Floor) | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 18 Floor completed, Internal Plaster upto 18 Floor completed, External Plaster upto 18 Floor completed, Flooring upto 18 Floor completed, Painting upto 18 Floor completed, Finishing upto 18 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 18 | All work Completed. Provide OC.
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 4.5
Excavation |  | 18 | 100% | 100% |  | 100% |  | Excavation in process |  | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed |  | 18
RCC (Including podiums) |  | 19 | 100% |  |  |  |  | Footing in Process |  | 4.5
Brickwork | Brickwork & Internal Plaster | 18 | 100% |  |  |  |  | Footing Completed |  | 9
Internal Plaster | Brickwork & Internal Plaster | 18 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 100% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 18 | 100% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 18 | 100% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 18 | 100% |  |  |  |  | Plinth in process |  | 13.5
Possession |  | 18 | 100% |  |  |  |  | Plinth completed |  | 18
Construction details: |  | Wing B = St/Gr + 1st to 17th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 18 Slab completed, Brickwork upto 17 Floor completed, Internal Plaster upto 17 Floor completed, External Plaster upto 17 Floor completed, Flooring upto 17 Floor completed, Painting upto 17 Floor completed, Finishing upto 17 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 17 | All work Completed. Provide OC.
Stage of construction: |  | All work Completed. Provide OC. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 4.25
Excavation |  | 17 | 100% | 100% |  | 100% |  | Excavation in process |  | 8.5
Plinth |  | 17 | 100% |  |  |  |  | Excavation Completed |  | 17
RCC (Including podiums) |  | 18 | 100% |  |  |  |  | Footing in Process |  | 4.25
Brickwork | Brickwork & Internal Plaster | 17 | 100% |  |  |  |  | Footing Completed |  | 8.5
Internal Plaster | Brickwork & Internal Plaster | 17 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 100% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 17 | 100% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 17 | 100% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 17 | 100% |  |  |  |  | Plinth in process |  | 12.75
Possession |  | 17 | 100% |  |  |  |  | Plinth completed |  | 17
Construction details: |  | Wing C = St/Gr + 1st to 17th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 18 Slab completed, Brickwork upto 17 Floor completed, Internal Plaster upto 17 Floor completed, External Plaster upto 17 Floor completed, Flooring upto 15 Floor completed, Painting upto 12 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 17 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 18 Slab completed, Brickwork upto 17 Floor completed, Internal Plaster upto 17 Floor completed, External Plaster upto 17 Floor completed, Flooring upto 15 Floor completed, Painting upto 12 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 4.25
Excavation |  | 17 | 100% | 87.35% |  | 94.41% |  | Excavation in process |  | 8.5
Plinth |  | 17 | 100% |  |  |  |  | Excavation Completed |  | 17
RCC (Including podiums) |  | 18 | 100% |  |  |  |  | Footing in Process |  | 4.25
Brickwork | Brickwork & Internal Plaster | 17 | 100% |  |  |  |  | Footing Completed |  | 8.5
Internal Plaster | Brickwork & Internal Plaster | 17 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 100% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 15 | 88.24% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 12 | 70.59% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 12.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 17
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5200
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
MIDC Water Charges |  |  |  |  | 80000/-
Recommended rate of Parking |  |  |  |  | 2,00,000/-
Distressed valuation of the Property |  |  |  |  | 4160
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A |  | 105 | 53541.6796 |  | 88590.8157
Wing B |  | 102 | 54736.5901 |  | 93237.5791
Wing C |  | 68 | 44921.7779 |  | 76604.9069
Total |  | 275 | 153200.0476 |  | 258433.3017
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Phase II
Wing A
Ground/Stilt Floor for Parking
1st Floor for Residential
1 |  | 2BHK | 617.9246 | 82.5868 | 1009.4738 | 1st for Residential |  | 5225.4949
2 |  | 2BHK | 617.9246 | 69.8584 | 996.7453 |  |  | 5292.2245
3 |  | 1BHK | 436.8225 | 76.1553 | 731.389 |  |  | 4751.2333
4 |  | 1BHK | 436.8225 | 76.1553 | 731.389 |  |  | 4751.2333
5 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
6 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
2nd, 4th, 10th, 12th & 16th Floor for Residential
1 |  | 2BHK | 662.2454 | 127.2305 | 1056.9834 | 2nd, 4th, 10th, 12th & 16th Floor for Residential |  | 4990.6178
2 |  | 2BHK | 662.2454 | 127.2305 | 1056.9834 |  |  | 4990.6178
3 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
4 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
5 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
6 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
3rd, 7th, 9th, 11th, 15th, 17th Floor for Residential
1 |  | 2BHK | 640.0447 | 126.1003 | 1023.1171 | 3rd, 7th, 9th, 11th, 15th, 17th Floor for Residential |  | 5155.8124
2 |  | 2BHK | 640.0447 | 126.1003 | 1023.1171 |  |  | 5155.8124
3 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
4 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
5 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
6 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
5th Floor
1 |  | 2BHK | 640.0447 | 126.1003 | 1023.1171 | 5th Floor |  | 5155.8124
2 |  | 2BHK | 640.0447 | 126.1003 | 1023.1171 |  |  | 5155.8124
3 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
4 |  | 1RK | 300.786 | 91.494 | 542.673 |  |  | 6403.4882
5 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
6 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
6th & 14th Floor for Residential
1 |  | 2BHK | 662.2454 | 127.2305 | 1056.9834 | 6th & 14th Floor for Residential |  | 4990.6178
2 |  | 2BHK | 662.2454 | 127.2305 | 1056.9834 |  |  | 4990.6178
3 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
4 |  | 1RK | 320.9685 | 0 | 481.4527 |  |  | 7217.7387
5 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
6 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
8th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 662.2454 | 127.2305 | 1056.9834 | 8th & 18th Floor (Part Refuge Area) |  | 4990.6178
2 |  | 2BHK | 662.2454 | 127.2305 | 1056.9834 |  |  | 4990.6178
3 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
4 |  | 1BHK | 434.885 | 87.5113 | 739.8388 |  |  | 4696.9692
5 |  | 2BHK | 631.4948 | 87.5113 | 1034.7535 |  |  | 5097.8323
6 |  | Refuge Area
13th Floor (Part Refuge Area)
1 |  | 2BHK | 640.0447 | 126.1003 | 1023.1171 | 13th Floor (Part Refuge Area) |  | 5155.8124
2 |  | 2BHK | 640.0447 | 126.1003 | 1023.1171 |  |  | 5155.8124
3 |  | 1BHK | 436.8225 | 91.494 | 746.7277 |  |  | 4653.6372
4 |  | 1RK | 300.786 | 91.494 | 542.673 |  |  | 6403.4882
5 |  | 2BHK | 613.3306 | 182.988 | 1011.4899 |  |  | 5215.0795
6 |  | Refuge Area
Wing B
Ground Floor for Parking
1st Floor for Residential
1 |  | 1BHK | 410.8673 | 116.0897 | 732.3906 | 1St Floor for Residential
2 |  | 1BHK | 410.638 | 116.0897 | 732.0467
3 |  | 1BHK | 410.638 | 116.0897 | 732.0467
4 |  | 3BHK | 756.4627 | 175.0226 | 1309.7167
5 |  | 2BHK | 619.5468 | 150.0502 | 1079.3703
6 |  | 2BHK | 594.204 | 93.001 | 984.307
2nd, 4th, 6th, 10th, 12th, 14th & 16th Floor |  |  |  | .
1 |  | 1BHK | 410.8673 | 116.0897 | 732.3906 | 2nd, 4th, 6th & 10th Floor for Residential
2 |  | 1BHK | 410.638 | 116.0897 | 732.0467
3 |  | 1BHK | 410.638 | 116.0897 | 732.0467
4 |  | 3BHK | 756.4627 | 175.0226 | 1309.7167
5 |  | 2BHK | 619.5468 | 150.0502 | 1079.3703
6 |  | 2BHK | 594.4839 | 93.001 | 984.7268
3rd, 5th, 7th, 9th, 11th, 15th & 17th Floor |  |  |  | .
1 |  | 1BHK | 433.5115 | 69.9929 | 720.2601 | 3rd, 5th, 7th, 9th Floor for Residential
2 |  | 1BHK | 433.5115 | 74.1101 | 724.3774
3 |  | 1BHK | 433.5115 | 74.1101 | 724.3774
4 |  | 3BHK | 762.7403 | 158.8766 | 1302.987
5 |  | 2BHK | 619.5468 | 101.6122 | 1030.9323
6 |  | 2BHK | 594.4839 | 93.001 | 984.7268
8th Floor(Part Refuge Area)
1 |  | 1BHK | 410.8673 | 69.9929 | 686.2938 | 8th Floor for Residential
2 |  | 1BHK | 410.638 | 74.1101 | 690.0671
3 |  | 1BHK | 410.638 | 74.1101 | 690.0671
4 |  | 2BHK | 604.0681 | 87.1884 | 993.2906
5 |  | 2BHK | 619.5468 | 101.6122 | 1030.9323
6 |  | 2BHK | 594.4839 | 93.001 | 984.7268
13th Floor(Part Refuge Area)
1 |  | 1BHK | 433.5115 | 69.9929 | 720.2601 | 8th Floor for Residential
2 |  | 1BHK | 433.5115 | 74.1101 | 724.3774
3 |  | 1BHK | 433.5115 | 74.1101 | 724.3774
4 |  | 2BHK | 609.8323 | 87.1884 | 1001.9368
5 |  | 2BHK | 619.5468 | 101.6122 | 1030.9323
6 |  | 2BHK | 594.4839 | 93.001 | 984.7268
Wing C
Ground Floor for Entrance Lobby, Meter Room, Drivers Room & Parking
1st Floor for Residential | [8 empty] | 10.764
1 |  | 3BHK | 729.2804 | 115.713 | 1209.6336 | 1st Floor for Residential |  | 67.7518
2 |  | 3BHK | 729.2804 | 164.3555 | 1258.2761
3 |  | 2BHK | 602.9046 | 156.9391 | 1061.296
4 |  | 2BHK | 574.606 | 189.877 | 1051.786
2nd, 4th, 6th, 10th, 12th, 14th & 16th Floor
1 |  | 3BHK | 729.2804 | 158.1232 | 1252.0437 | 2nd, 4th, 6th, 10th, 12th, 14th & 16th Floor
2 |  | 3BHK | 729.2804 | 158.1232 | 1252.0437
3 |  | 2BHK | 602.9046 | 128.6944 | 1033.0512
4 |  | 2BHK | 574.606 | 138.6403 | 1000.5493
3rd, 5th, 7th, 9th, 11th, 15th & 17th Floor
1 |  | 3BHK | 729.2804 | 115.713 | 1209.6336 | 3rd, 5th, 7th, 9th, 11th, 15th & 17th Floor
2 |  | 3BHK | 729.2804 | 115.713 | 1209.6336
3 |  | 2BHK | 625.0246 | 116.3588 | 1053.8957
4 |  | 2BHK | 596.726 | 150.696 | 1045.785
8th Floor(Part Refuge Area)
1 |  | 3BHK | 729.2804 | 158.1232 | 1252.0437 | 8th Floor(Part Refuge Area)
2 |  | 3BHK | 729.2804 | 158.1232 | 1252.0437
3 |  | 1BHK | 480.2272 | 111.2567 | 831.5976
4 |  | 2BHK | 574.606 | 138.6403 | 1000.5493
13th Floor (Part Refuge Area)
1 |  | 3BHK | 729.2804 | 115.713 | 1209.6336 | 13th Floor (Part Refuge Area)
2 |  | 3BHK | 729.2804 | 115.713 | 1209.6336
3 |  | 1BHK | 502.3473 | 72.657 | 826.1779
4 |  | 2BHK | 596.726 | 150.696 | 1045.785
Remarks:
1. Wing A = All work Completed. OC Received. Wing B = All work Completed. Please provide OC. Wing C = Construction work is in process at the time of Visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + A.P Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Car parking is subjected to authentic documentation. 8. Wing B - We have updated latest approved floor plans & CC (on 27/05/2022). 9. Wing C - We have updated latest approved layout plan, floor plan and CC (on 07/10/2023). 10. We have updated OC from rera for Wing A (On 12/03/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Umiya Nakshtra Heights
Layout :
Google Map :
A Wing
B Wing
C Wing
B Wing
B Wing
C Wing
C Wing
C Wing

## Report
1302-ELLORA FIESTA, PLOT NO. 8, SECTOR 11, OPP. JUINAGAR RAILWAY STATION, SANPADA, NAVI MUMBAI 400 706. TEL: 022-27758396/95. FAX :022-27758394. E mail : axisbank@vsjadon.com. vsjcvaluer@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 28/12/2020.
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 21/12/2020.
Name of the builder group |  |  |  | M/s. Jigar Enterprises
Name of the builder company |  |  |  | M/s. Jigar Enterprises
Name of the Project |  |  |  | Umiya Nakshtra Heights
Contect Details ( Name & Contect No.) |  |  |  | 8237202013/8369181294
Name / No of the Building |  |  |  | Phase II(Wing A, B, C)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | Wing A = P51700021530 Wing B & C = Not on Rera
Project location details |  | Umiya Nakshtra Heights, Survey/Hissa No.64/1/4 & Old S.No/Hissa no. 64/2, Proposed Panvel Highway, Katrap, Badlapur, Ambernath, Thane.
Survey/Hissa No |  | 64/1/4 & Old S.No/Hissa no. 64/2
Road |  | Proposed Panvel Highway |  | Locality/Village |  | Katrap
City |  | Badlapur |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Near by Landmark |  | Katrap Lake |  | Distance from city centre: |  | 2.1km from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1718 |  | Longitude |  | 73.2232
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7653.82
Permissible FSI |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  | 0.2
Total FSI availaible for the project |  |  |  | 1.4
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10715.34
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Layout Approval No |  | KBNP/NRV/BP/7351-92 |  |  | Dated | 05/10/2018.
Approved Floor plan No. |  | KBNP/NRV/BP/7351-92 |  |  | Dated | 05/10/2018.
Commencement Certificate No. |  | KBNP/NRV/BP/7351-92 |  |  | Dated | 05/10/2018.
Valid Up to: Wing A = St + Gr + 18th Floor Wing B = St + Gr + 10th Floor Wing C = St + Gr + 1st Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10715.34
Approved no of units |  |  | Flats -
Approved no of Floors |  |  | Wing A = St + Gr + 18th Floor Wing B = St + Gr + 10th Floor Wing C = St + Gr + 1st Floor
Proposed no of Floors |  |  | Wing A = St + Gr + 18th Floor Wing B = St + Gr + 18th Floor Wing C = St + Gr + 18th Floor
Expected Completion |  |  | As per RERA - 03/06/2024.
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel
Construction details: Wing A (Gr + 18th Floor) | [7 empty] | Plinth work completed, RCC upto 14 Slab completed, Brickwork upto 9 Floor completed, Plaster upto 3 Floor completed, Flooring upto 1 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 18 | All work Completed. Wait For OC.
Stage of construction: |  | Plinth work completed, RCC upto 14 Slab completed, Brickwork upto 9 Floor completed, Plaster upto 3 Floor completed, Flooring upto 1 Floor completed | [5 empty] | All work Completed. Part OC Received.
Type of Work |  | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth |  | 10 | 100% | 49.2% |  | 61.55%
RCC Slab |  | 14 | 73.68% |  |  |  |  | Excavation in process | 1% | 2%
Brick |  | 9 | 50% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster |  | 3 | 16.67% |  |  |  |  | Footing in Process | 4% | 8%
Flooring |  | 1 | 5.556% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing |  | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
Construction details: Wing B = Gr + 18th Floor | [7 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 18 | All work Completed. Wait For OC.
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. Part OC Received.
Type of Work |  | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth |  | 0 | 0% | 0% |  | 0%
RCC Slab |  | 0 | 0% |  |  |  |  | Excavation in process | 1% | 2%
Brick |  | 0 | 0% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster |  | 0 | 0% |  |  |  |  | Footing in Process | 4% | 8%
Flooring |  | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing |  | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
Construction details: Wing C = Gr + 18th Floor | [7 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 18 | All work Completed. Wait For OC.
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. Part OC Received.
Type of Work |  | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth |  | 0 | 0% | 0% |  | 0%
RCC Slab |  | 0 | 0% |  |  |  |  | Excavation in process | 1% | 2%
Brick |  | 0 | 0% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster |  | 0 | 0% |  |  |  |  | Footing in Process | 4% | 8%
Flooring |  | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing |  | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area)
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking
Distressed valuation of the Property |  |  |  |  | 0
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A |  | 105 | 52060.3669 |  | 89482.1185
Wing B |  | 60 | 31173.2885 |  | 53089.9183
Wing C |  | 4 | 426.3534 |  | 3771.9504
Total |  | 169 | 83660.0089 |  | 146343.9872
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Phase II
Wing A
Ground/Stilt Floor for Parking
1st Floor for Residential
1 |  | 2BHK | 617.9246 | 82.5868 | 1009.4738 | 1st for Residential
2 |  | 2BHK | 521.7784 | 69.8584 | 852.526
3 |  | 1BHK | 427.5116 | 78.3619 | 719.6294
4 |  | 1BHK | 438.6104 | 76.1553 | 734.0709
5 |  | 1BHK | 426.2802 | 111.6227 | 751.043
6 |  | 1BHK | 426.2802 | 111.6227 | 751.043
2nd, 4th, 10th, 12th & 16th Floor for Residential
1 |  | 2BHK | 626.2129 | 127.2305 | 1066.5499
2 |  | 2BHK | 626.2129 | 127.2305 | 1066.5499 | 2nd, 4th, 10th,12th & 16th Floor for Residential
3 |  | 1BHK | 436.6729 | 96.876 | 751.8853
4 |  | 1BHK | 436.6729 | 96.876 | 751.8853
5 |  | 1BHK | 436.6729 | 96.876 | 751.8853
6 |  | 1BHK | 436.6729 | 96.876 | 751.8853
3rd, 7th, 9th, 11th, 15th, 17th Floor for Residential
1 |  | 2BHK | 633.6401 | 126.1003 | 1076.5604 | 3rd, 7th, 9th, 11th, 15th, 17th Floor for Residential
2 |  | 2BHK | 633.6401 | 126.1003 | 1076.5604
3 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
4 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
5 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
6 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
5th Floor for Residential
1 |  | 2BHK | 633.6401 | 126.1003 | 1076.5604 | 5th Floor for Residential
2 |  | 2BHK | 633.6401 | 126.1003 | 1076.5604
3 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
4 |  | 1RK | 300.786 | 111.6227 | 562.8017
5 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
6 |  | 1BHK | 440.3865 | 111.6227 | 772.2024
6th & 14th Floor for Residential
1 |  | 2BHK | 551.5161 | 127.2305 | 954.5047 | 6th & 14th Floor for Residential
2 |  | 2BHK | 551.5161 | 127.2305 | 954.5047
3 |  | 1BHK | 435.8333 | 93.6468 | 747.3967
4 |  | 1RK | 300.786 | 0 | 451.179
5 |  | 1BHK | 440.3865 | 96.876 | 757.4557
6 |  | 1BHK | 440.3865 | 96.876 | 757.4557
8th & 18th Floor for Residential
1 |  | 2BHK | 551.5161 | 127.2305 | 954.5047 | 8th & 18th Floor for Residential |  | 27.1253
2 |  | 2BHK | 551.5161 | 127.2305 | 954.5047
3 |  | 1BHK | 435.8333 | 93.6468 | 747.3967
4 |  | 1BHK | 435.8333 | 93.6468 | 747.3967
5 |  | 2BHK | 640.3224 | 96.876 | 1057.3596
13th Floor for Residential
1 |  | 2BHK | 551.5161 | 126.1003 | 953.3745 | 13th Floor for Residential
2 |  | 2BHK | 551.5161 | 118.404 | 945.6782
3 |  | 1BHK | 435.8333 | 88.803 | 742.5529
4 |  | 1RK | 294.1338 | 88.803 | 530.0038
5 |  | 2BHK | 640.3224 | 177.606 | 1138.0896
Wing B
1st Floor for Residential
1 |  | 2BHK | 609.815 | 75.348 | 990.0706 | 1St Floor for Residential
2 |  | 1BHK | 440.7905 | 67.275 | 728.4608
3 |  | 1BHK | 449.1944 | 67.275 | 741.0666
4 |  | 1BHK | 461.2285 | 64.584 | 756.4268
5 |  | 1BHK | 470.1411 | 64.584 | 769.7957
6 |  | 3BHK | 813.2826 | 134.3347 | 1354.2587
2nd, 4th, 6th & 10th Floor for Residential |  |  |  | .
1 |  | 2BHK | 601.8335 | 123.786 | 1026.5363 | 2nd, 4th, 6th & 10th Floor for Residential
2 |  | 1BHK | 435.8537 | 93.6468 | 747.4274
3 |  | 1BHK | 437.6836 | 93.6468 | 750.1722
4 |  | 1BHK | 437.6836 | 93.6468 | 750.1722
5 |  | 1BHK | 436.9086 | 93.6468 | 749.0097
6 |  | 3BHK | 769.9252 | 131.1055 | 1285.9934
3rd, 5th, 7th, 9th Floor for Residential |  |  |  | .
1 |  | 2BHK | 613.2972 | 126.5846 | 1046.5304 | 3rd, 5th, 7th, 9th Floor for Residential
2 |  | 1BHK | 437.7913 | 74.9174 | 731.6043
3 |  | 1BHK | 441.2357 | 77.5008 | 739.3544
4 |  | 1BHK | 441.2357 | 92.3013 | 754.1549
5 |  | 1BHK | 440.4607 | 92.3013 | 752.9924
6 |  | 3BHK | 732.7894 | 207.9605 | 1307.1446
8th Floor for Residential
1 |  | 2BHK | 627.6671 | 146.7133 | 1088.214 | 8th Floor for Residential
2 |  | 1BHK | 438.0065 | 93.6468 | 750.6566
3 |  | 1BHK | 437.6836 | 93.6468 | 750.1722
4 |  | 1BHK | 437.6836 | 93.6468 | 750.1722
5 |  | 1BHK | 437.6836 | 93.6468 | 750.1722
6 |  | 2BHK | 643.318 | 131.1055 | 1096.0825
Wing C
1st Floor for Residential
1 |  | 2BHK | 529.535 | 116.3588 | 910.6613 | 1st Floor for Residential
2 |  | 2BHK | 571.9372 | 130.2444 | 988.1502
3 |  | 2BHK | 571.9372 | 75.2727 | 933.1785
4 |  | 2BHK | 556.9886 | 104.4775 | 939.9604
Remarks:
1.Construction work is in process at the time of Visit (labour found). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + F.B Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr........(........).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Harshada
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Umiya Nakshtra Heights
Google Map :

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Suraj Palette - 500m | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick | Mangrish Apartment sea side - 1.1KM | 4BHK | 2274 | 3638.4 | 32981.5303 | 120000000
Magic Brick | Suraj Palette - 500m | 3BHK | 1466 | 2345.6 | 32528.9905 | 76300000
Magic Brick | Mangrish Apartment sea side - 1.1KM | 4BHK | 2275 | 3640 | 32554.9451 | 118500000
Magic Brick | Suvidha Emerald - 1.1KM | 4BHK | 2700 | 4320 | 32175.9259 | 139000000
99 Acres | Suraj Palette - 500m | 3BHK | 1466 | 2345.6 | 32997.9536 | 77400000
99 Acres | Kings Krest - 350m | 4BHK | 1725 | 2760 | 31268.1159 | 86300000
Average |  |  |  |  | 32291.4302
Valuation Adopted |  |  |  |  | 32000