## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/s. Panika Infrastructure Pvt Ltd.
Name of the builder company |  |  |  |  | M/s. Panika Infrastructure Pvt Ltd.
Name of the Project |  |  |  |  | Vangani Darshan
Name & No. of the Building |  |  |  |  | Wing/Type A1, A2, A3, B & C
Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Pramod Shetty - 9172753440
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr.Jagdish : 9373144033
RERA No. |  |  |  |  | P51700003380
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | Vangani Darshan, Revised Residential Building Plan In G. No. 2/1 + 2 At Village - Karav, Near Gandhkuti, Pashane Road, Vangani, Tal - Ambernath, Dist - Thane - 421503.
Gut No |  | 2/1 + 2 |  |  | Locality |  | Karav
Road |  | Internal Road |  |  | District |  | Thane
City |  | Vangani |  |  | Pin Code |  | 421503
Near by Landmark |  | Karav Water Tank |  |  | Distance from city centre: |  | About 3.8Km Distance From Vangani Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Open Plot |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.11613512,73.31681082
Location Link |  | https://goo.gl/maps/JdVDfJTj1PexTe337
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 9115
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | NA
Total FSI availaible for the project |  |  |  |  | NA
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 6936.65
Total number of Buildings |  |  |  |  | 05 Wings
Approval Detail : Plan approval
Layout Approval No |  | NA/BP/Village - Karav/Tal - Ambernath/SSThane/525 |  |  |  | Dated | 11/03/2015.
Building plan approval No |  | NA/BP/Village - Karav/Tal - Ambernath/SSThane/525 |  |  |  | Dated | 11/03/2015.
NA Cum C.C No. |  | NA/BP/Village - Karav/Tal - Ambernath/SSThane/525 Valid Up to: Type A1, A2, A3, B & C = G + 1st to 3rd Floor |  |  |  | Dated | 11/03/2015.
O. Certificate No.: NA |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 11/03/2015. |  | Expected Completion |  | 2024-12-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 6936.65 |  | Approved no of units residential |  |  | NA
Approved no of Floors |  | Type A1, A2, A3, B & C = G + 1st to 3rd Floor
Proposed no of Floors |  | Type A1, A2, A3, B & C = G + 1st to 3rd Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: : Bricks, Cement & Steel etc.
Construction details: |  | Type A1 = G + 1st to 3rd Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process |  | 1.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed |  | 3
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Construction details: |  | Type A2 = G + 1st to 3rd Floor | [6 empty] | Excavation work completed, Footing work Completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Footing work Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 3 | 100% |  | 5% |  | 32.5% |  | Excavation in process |  | 1.5
Plinth |  | 1.5 | 50% | [5 empty] | Excavation Completed |  | 3
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Construction details: |  | Type A3 = G + 1st to 3rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 3 | 100% |  | 40% |  | 67.5% |  | Excavation in process |  | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed |  | 3
RCC (Including podiums) |  | 3 | 75% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Construction details: |  | Type B = G + 1st to 3rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 0.5 Floor completed, External Plaster upto 1 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 0.5 Floor completed, External Plaster upto 1 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 3 | 100% |  | 62.08% |  | 82.5% |  | Excavation in process |  | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed |  | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0.5 | 16.67% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 33.33% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Construction details: |  | Type C = G + 1st to 3rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 3 | 100% |  | 90% |  | 95% |  | Excavation in process |  | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed |  | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 3 | 100% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Builder's Saleable area) | [5 empty] | 2250
Other Charges | [5 empty] | 2,50,000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 1800
Remarks: 1. Type A1 = Work not yet started. Work is same as last visit (14/08/2020). Type A2 = Construction work is same as last visit (14/08/2020). Type B = Construction work is same as last visit (20/03/2024). Type C = Construction work is same as last visit (18/12/2023). Type A3 = Construction work is same as last visit (21/09/2024). 2. We have given rate verify by market inquire. 3. We have considered rate by verifying it from market inquire. 4. We have considered Other charges from cost sheet. 5. Project has received first CC on 11/03/2015, But Type A1 building constuction not started yet and Type A2, A3, B & C construction work is not yet completed. 6. As per RERA, completion period of project is expired on 31/12/2024 but still project is under construction. 7. As checked on RERA portal on date 19/09/2025, we have observed that above project "Vangani Darshan" is kept under abeyance. Please check from your end. | [9 empty] | As per Info from site inqury Area of plot has been undertaken by mhada authority.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vangani Darshan
Google Map :
Type A2
Type A3
Type B
Type C
Type C
Type A2
Type A3
Type B
Type C
Type A2
Type A3
Type B
Type B
Type C

## A2
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## A3
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 1 | 20% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 8 | 0 | 0 | 0 | 0 | 0
RCC | 8 | 6 |  | Recommended |  | 30 | 6 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 18% | 36% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B.
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 2 | 40% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 16 | 0 | 0 | 0 | 0 | 0
RCC | 16 | 12 |  | Recommended |  | 30 | 12 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 26% | 42% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 4 | 80% |  | Parking |  | Rate
Bricks | 4 | 3 | 75% |  | Palghar |  | 100000/-
plaster | 4 | 3 | 75% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 3 | 75% |  | Panvel |  | 300000/-
Wood & painting | 4 | 2 | 50% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 32 | 11.25 | 7.5 | 7.5 | 2.5 | 0
RCC | 32 | 24 |  | Recommended |  | 30 | 24 | 11.25 | 7.5 | 3.75 | 2.5 | 0
Bricks | 11.25 | 11.25
Plaster | 7.5 | 7.5
Flooring | 7.5 | 3.75
Wood & painting | 2.5 | 2.5
Finishing | 0 | 0
total | 70.75% | 79% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
proptiger | Vangani Darshan | 1BHK | 237 | 379.2 | 2362.8692 | 896000
proptiger | Vangani Darshan | 1BHK | 271 | 433.6 | 2361.6236 | 1024000
commonfloor. | Vangani Darshan | 1BHK | 368 | 588.8 | 2374.3207 | 1398000
commonfloor. | Vangani Darshan | 1BHK | 408 | 652.8 | 2374.3873 | 1550000
commonfloor. | Vangani Darshan | 1RK | 232 | 371.2 | 2373.3836 | 881000
commonfloor. | Vangani Darshan | 1RK | 271 | 433.6 | 2373.155 | 1029000
Average |  |  |  |  | 2369.9566
Valuation Adopted |  |  |  |  | 2400

## NOTE
11/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.