## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-05
Name of the builder group |  |  |  | Bonzer Orbit
Name of the builder company |  |  |  | Bonzer Orbit
Name of the Project |  |  |  | Viraj Iconic
Contact Details ( Name & Contact No.) |  |  |  | Miss. Smita Gaikwad - 8097813081 Miss. Nigeeta Sawant - 8484053268
Name / No of the Building |  |  |  | Wing A & B
Documents Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700045521
Project location details |  | Viraj Iconic, Gut No.53 H.No. 5, P.No. 1..Gut No.53, H.No. 11, P.No. 9, near Madhubala Apartment, St Anthony School Road, Ganesh Chowk, Manjarli, Badlapur (West), Ambernath, Thane - 421503.
Gut No |  | 53 H.No. 5, P.No. 1..Gut No.53, H.No. 11, P.No. 9
Locality |  | Ganesh Chowk
Road |  | St Anthony School Road |  | Village |  | Manjarli
City |  | Badlapur (West) |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Nearby Landmark |  | Madhubala Apartment |  | Distance from city centre: |  | 1.1KM from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Gaondev Mandir
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Madhubala Apartment
South | NA | NA |  |  | St Anthony School Rd
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.1742001,73.2349198
Location Link |  | https://goo.gl/maps/UCeSXfQBZZW5MZnk6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3016.32
Permissible FSI |  |  |  | 1 |  |  |  |  | 2.3618 | 3016.32
Permissible TDR/Paid FSI |  |  |  | 1.3618 | [5 empty] | 3016.32 | 1
Total FSI availaible for the project |  |  |  | 2.3618 | [5 empty] | 7123.83 | 2.3618
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7123.83 | [6 empty] | 1.3618
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgoan Badlapur Municipal Council
Layout Approval No |  | KBNP/NRV/BP/1090-196 |  |  | Dated | 2022-02-04
Approved Floor plan No. |  | KBNP/NRV/BP/1090-196 |  |  | Dated | 2022-02-04
Commencement-CC No Valid Up to: |  | KBNP/NRV/BP/1090/2021-2022/Unique No. 196 |  |  | Dated | 2022-02-04
Wing A = Gr/Stilt + 1st to 13th Floor Wing B = Gr/Stilt + 1st to 6th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7123.83
Approved no of units |  |  | Flats -118, Shops -19, Offices -6
Approved no of Floors |  |  | Wing A = Gr/Stilt + 1st to 13th Floor Wing B = Gr/Stilt + 1st to 6th Floor
Proposed no of Floors |  |  | Wing A = Gr/Stilt + 1st to 13th Floor
Wing B = Gr/Stilt + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr/Stilt + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 12 Floor, Painting upto 10 Floor, Finishing upto 1 Floor Completed | , Flooring upto 12 Floor, Painting upto 10 Floor, Finishing upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 12 Floor, Painting upto 10 Floor, Finishing upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 88.46% |  | 94.62% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 92.31% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 76.92% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 7.692% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | Wing B = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 6 Floor Completed | , External Plaster upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 73.57% |  | 89.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4800
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 12000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 8000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 3840
Commercial Area Details : | [8 empty] | rate sheet
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | builder | visitor
Wing A | Shop | 19 |  | 2939.9713 |  | 4703.9541 |  | shop | 20000
| Office | 6 |  | 3527.1475 |  | 5855.616 |  | office
Total |  | 25 |  | 6467.1188 |  | 10559.5701 |  | flat | 4500 | 4800
Residential Area Details : | [9 empty] | 5500
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 94 |  | 45100.6487 |  | 68109.8424
Wing B |  | 24 |  | 12286.7831 |  | 18430.1746
Total |  | 118 |  | 57387.4318 |  | 86540.017 |  |  | 63854.5506 | 97099.5871
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing A
Ground Floor For Commercial & Parking
1 |  | Shop | 142.0848 | 0 | 227.3357 | Ground Floor For Commercial & Parking |  |  | 13.2
2 |  | Shop | 144.7758 | 0 | 231.6413 |  |  |  | 13.455
3 |  | Shop | 173.0851 | 0 | 276.9362
4 |  | Shop | 173.0851 | 0 | 276.9362
5 |  | Shop | 182.4498 | 0 | 291.9197
6 |  | Shop | 143.5918 | 0 | 229.7468
7 |  | Shop | 143.5918 | 0 | 229.7468
8 |  | Shop | 213.1272 | 0 | 341.0035
9 |  | Shop | 197.627 | 0 | 316.2033
10 |  | Shop | 146.498 | 0 | 234.3969
11 |  | Shop | 213.1272 | 0 | 341.0035
12 |  | Shop | 113.022 | 0 | 180.8352
13 |  | Shop | 110.2234 | 0 | 176.3574
14 |  | Shop | 155.4322 | 0 | 248.6915
15 |  | Shop | 133.6889 | 0 | 213.9022
16 |  | Shop | 165.7656 | 0 | 265.225
17 |  | Shop | 135.6264 | 0 | 217.0022
18 |  | Shop | 126.5846 | 0 | 202.5354
19 |  | Shop | 126.5846 | 0 | 202.5354 |  |  |  | 11.76
1st Floor
1 |  | Office | 414.5485 | 0 | 663.2777 | 1st Floor |  |  | 31.405
2 |  | Office | 525.6061 | 0 | 840.9698
3 |  | Office | 721.0535 | 0 | 1153.6855
4 |  | Office | 785.9873 | 0 | 1257.5796
5 |  | Office | 592.3967 | 0 | 947.8348
6 |  | Office | 487.5554 | 132.6125 | 992.2686 |  |  |  | 40.88
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A
2nd Floor For Residential
201 |  | 1 | 422.4332 | 0 | 633.6498 | 2nd Floor For Residential |  | 3041518.896 | 29.215 | 8.675
202 |  | 1 | 379.9154 | 94.4541 | 664.3272 |  |  | 3188770.416 | visitor
203 |  | 2 | 576.17 | 47.9536 | 912.2086 |  |  | 4378601.448
204 |  | 2 | 584.8888 | 78.4696 | 955.8028 |  |  | 4587853.608 | visitor
205 |  | 2 | 540.6219 | 55.2193 | 866.1522 |  |  | 4157530.416
206 |  | 1 | 406.4217 | 36.3285 | 645.9611 |  |  | 3100613.256
207 |  | 1 | 381.7991 | 73.2221 | 645.9207 |  |  | 3100419.504
208 |  | 1 | 381.7991 | 73.2221 | 645.9207 |  |  | 3100419.504
3rd, 4th, 5th, 6th, 7th, 9th, 10th, 11th & 12th Floor | [7 empty] | 0
301 ,.., 1201 |  | 1 | 422.4332 | 0 | 633.6498 | 3rd, 4th, 5th, 6th, 7th, 9th, 10th, 11th & 12th Floor |  | 2851423.965
302 ,.., 1202 |  | 1 | 424.3169 | 0 | 636.4753 |  |  | 2864138.94
303 ,.., 1203 |  | 2 | 598.3708 | 0 | 897.5561 |  |  | 4039002.63
304 ,.., 1204 |  | 2 | 607.0896 | 0 | 910.6344 |  |  | 4097854.8 | visitor
305 ,.., 1205 |  | 2 | 555.1533 | 0 | 832.7299 |  |  | 3747284.775
306 ,.., 1206 |  | 1 | 428.6225 | 0 | 642.9337 |  |  | 2893201.74 | MB
307 ,.., 1207 |  | 1 | 403.9998 | 0 | 605.9997 |  |  | 2726998.8525 | visitor
308 ,.., 1208 |  | 1 | 403.9998 | 0 | 605.9997 |  |  | 2726998.8525
8th & 13th Floor (Part Refuge Area) | [7 empty] | 0
801 & 1301 |  | 1 | 422.4332 | 0 | 633.6498 | 8th & 13th Floor (Part Refuge Area) |  | 2851423.965
802 & 1302 |  | 1 | 424.3169 | 0 | 636.4753 |  |  | 2864138.94 | visitor
803 & 1303 |  | 2 | 598.3708 | 0 | 897.5561 |  |  | 4039002.63
804 & 1304 |  | 2 | 607.0896 | 0 | 910.6344 |  |  | 4097854.8
805 & 1305 |  | 2 | 555.1533 | 0 | 832.7299 |  |  | 3747284.775
806 & 1306 |  | Refuge Area | [5 empty] | 0
807 & 1307 |  | 1 | 403.9998 | 0 | 605.9997 |  |  | 2726998.8525
808 & 1308 |  | 1 | 403.9998 | 0 | 605.9997 |  |  | 2726998.8525
Wing B | [7 empty] | 0
Ground Floor For Parking | [7 empty] | 0
1st to 6th Floor For Residential | [7 empty] | 0
101 to 601 |  | 1 | 424.1016 | 0 | 636.1524 | 1st to 6th Floor For Residential |  | 2862685.8 | 31.52
102 to 602 |  | 2 | 599.797 | 0 | 899.6955 |  |  | 4048629.6825
103 to 603 |  | 2 | 599.797 | 0 | 899.6955 |  |  | 4048629.6825
104 to 604 |  | 1 | 424.1016 | 0 | 636.1524 |  |  | 2862685.8
Remarks:
* | Wing A = Construction work is in process at the time of Visit. Wing B = Work is same as last visit but work is in process (Slow Speed).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + E.P. Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the construction goes beyond approved plan & CC for Wing B, Please provide latest Approved plan & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Sudhir Bhosale |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Viraj Iconic
Google Map :
Formulas:
Manjarli = [Manjarli, row above]
A Wing
A Wing
A Wing
B Wing
B Wing
Wing A
Wing A
Wing B
Wing B
Wing B
A Wing
A Wing
A Wing
B Wing
B Wing
B Wing
B Wing
B Wing
A Wing
A Wing
A Wing
A Wing
A Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted