## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | Shivalik Ventures Pvt.Ltd.
Name of the builder company |  |  |  | Shivalik Ventures Pvt.Ltd.
Name of the Project As per RERA |  |  |  | Bandra North Gulmohar Avenue
Name of the Project As per Builder |  |  |  | Gulmohar Avenue (Sale Building-S6 Bandra North)
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Danyeshwar Shedge 9892326630
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Shashikant Gaikwad (Sales) 8291969922 |  |  |  | Mr.Danyeshwar Shedge 9892326630
Name / No of the Building |  |  |  | Building S-6 (A to P Wing) |  |  |  | Mr. Vishwas Gawad- 7506399363
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800014036
Project location details |  | Gulmohar Avenue (Sale Building-S6 Bandra North), CTS No.30(pt), near Vishwashanti Buddha Vihar Hindu temple, Golibar Road, Bandra, Bandra, Bandra(East), Andheri, Mumbai - 400055.
CTS No |  | 30(pt)
Locality |  | Bandra
Road |  | Golibar Road |  | Locality/Village |  | Bandra
City |  | Bandra(East) |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400055
Nearby Landmark |  | Vishwashanti Buddha Vihar Hindu temple |  | Distance from city centre: |  | 0.8 KM from Bandra Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Golibar Rd
West | NA | NA |  |  | Slum
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Vishwashanti Buddha Vihar Hindu temple
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.071430, 72.844062
Location Link |  | https://goo.gl/maps/6SRXinSB9ZB229KT9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 118840.51
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 0.095034
Total FSI availaible for the project |  |  |  | 3.095
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 367815.44
Total number of Buildings |  |  |  | 18 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No A to L Wing |  | HE/MHADA/0028/2006082/AP/S6 |  |  | Dated | 2022-06-02
Approved Floor plan No. A to L Wing |  | HE/MHADA/0028/2006082/AP/S6 |  |  | Dated | 2022-06-02
Layout Approval No M to R Wings |  | HE/MHADA/0028/20060821/AP/S6 |  |  | Dated | 2017-09-29
Approved Floor plan No. M to R Wings |  | HE/MHADA/0028/20060821/AP/S6 |  |  | Dated | 2017-09-29
Commencement-CC No Valid Up to: A to R Wings |  | HE/MHADA/0028/20060821/AP/S6 |  |  | Dated | 18/12/2017.
Plinth Level (Top of Basement)
Commencement-CC No Valid Up to: D, E & F Wings |  | HE/MHADA/0028/2006082/AP/S6 |  |  | Dated | 2022-06-02
This CC is reendorsed for bldg S6 and this further CC is issued for Gr + 15th upper floors + LMR + OHT for Wing D, E & F of sale building S6 as per amended approved plans dated 02/06/2022.
Part O. Certificate No.: |  | HE/MHADA/0028/20060821/AP/S6 Approved upto : Wing D = Gr/St + 1st to 15th Floor 58 nos. of 1BHK flats & 1 Society Office Wing E = Gr/St + 1st to 15th Floor 59 nos. of 1BHK flats Wing F = Gr/St + 1st to 15th Floor 59 nos. of 1BHK flats |  |  | Dated | 2024-09-27
Part O. Certificate No.: |  | HE/MHADA/0028/20060821/AP/S6 Approved Upto : Building No. S-6 (Wing B) = G + 1st to 15th Floor & 59 Nos. of 1BHK Flats in Wing B Building No. S-6 (Wing C) = G + 1st to 15th Floor & 58 Nos. of 1BHK Flats + 1 Society Office in Wing C |  |  | Dated | 2025-05-15
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 367815.44
Approved no of units |  |  | Flats - 1055
Approved no of Floors |  |  | Building S-6 (A to P Wing) = 3B+ Stilt +1st to 15th Floor
Proposed no of Floors |  |  | Building S-6 (A, G & H Wing) = 3B + Stilt+1st to 15th Floor
Building S-6 (B & C Wing) = 3B+ Stilt +1st to 15th Floor
Building S-6 (D & E Wing) = 3B+ Stilt +1st to 15th Floor
Building S-6 (F Wing) = 3B+ Stilt +1st to 15th Floor
Building S-6 (I, J, K & L Wing) = 3B+ Stilt +1st to 15th Floor
Building S-6 (M to R) = 3B+ Stilt +1st to 15th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities :
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building S-6 (A Wing) = 3B + Stilt+1st to 15th Floor | [5 empty] | Excavation Completed
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation
Stage of construction: |  | Excavation Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 0% |  | 20% |  | Excavation in process | 7.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (G Wing) = 3B + Stilt+1st to 15th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 20% |  | 52.5% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 4 | 25% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 ( H Wing) = 3B + Stilt+1st to 15th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 15% |  | 48.75% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 2 | 12.5% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (B & C Wing) = 3B+ Stilt +1st to 15th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 100% |  | 100% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 15 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 15 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 15 | 100% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (D & E Wing) = 3B+ Stilt +1st to 15th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 100% |  | 100% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 15 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 15 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 15 | 100% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (F Wing) = 3B+ Stilt +1st to 15th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 100% |  | 100% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 15 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 15 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 15 | 100% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (J, K & L Wing) = 3B+ Stilt +1st to 15th Floor | [5 empty] | Work not yet Started.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 7.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (I Wing) = 3B+ Stilt +1st to 15th Floor | [5 empty] | Excavation Completed, Footing work Completed
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation | , Footing work Completed
Stage of construction: |  | Excavation Completed, Footing work Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 4% |  | 30% |  | Excavation in process | 7.5
Plinth |  | 6 | 40% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Building S-6 (M to R) = 3B+ Stilt +1st to 15th Floor | [5 empty] | Work not yet Started.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 15 |  | Work not yet Started.
Stage of construction: |  | Not Yet Launched.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 7.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 12
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the flat Per Sq. Ft. ( on Saleable Area) |  |  |  |  | 21000
PLC - Western Express Highway Facing |  |  |  |  | 400000
Advance maintenance Charges/Psf of Carpet Area - for 12 Months |  |  |  |  | 70000
Advance Proportionate shares of taxes and Other Charges - for 12 Months |  |  |  |  | 50000
Electrical, mahanagar and water Meter Charges |  |  |  |  | 50000
Legal Charges including society legal entry formation Charges |  |  |  |  | 40000
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 16800
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 59 |  | 19026.877 |  | 27588.9716
Wing B |  | 59 |  | 19026.877 |  | 27588.9716
Wing C |  | 58 |  | 18704.3875 |  | 27121.3619
Wing D |  | 58 |  | 18704.3875 |  | 27121.3619
Wing E |  | 59 |  | 19026.877 |  | 27588.9716
Wing F |  | 59 |  | 19026.877 |  | 27588.9716
Wing G |  | 59 |  | 37708.7677 |  | 54677.7132
Wing H |  | 59 |  | 37708.7677 |  | 54677.7132
Wing I |  | 59 |  | 19026.877 |  | 27588.9716
Wing J |  | 58 |  | 18704.3875 |  | 27121.3619
Wing K |  | 59 |  | 19026.877 |  | 27588.9716
Wing L |  | 58 |  | 18704.3875 |  | 27121.3619
Wing M |  | 59 |  | 19026.877 |  | 27588.9716
Wing N |  | 58 |  | 18704.3875 |  | 27121.3619
Wing O |  | 59 |  | 19026.877 |  | 27588.9716
Wing P |  | 59 |  | 19026.877 |  | 27588.9716
Wing Q |  | 58 |  | 18704.3875 |  | 27121.3619
Wing R |  | 58 |  | 18704.3875 |  | 27121.3619
Total |  | 1055 |  | 377590.1407 |  | 547505.704
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Wing A
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing B
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing C
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 9th Floor (Part Refuge Area)
2 |  | Society Office
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing D
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | Society Office |  |  |  | 9th Floor (Part Refuge Area)
2 |  | Refuge Area |  | 0 | 0
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing E
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing F
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing G
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 1st Floor For Residential
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | 2BHK | 641.2115 | 0 | 929.7566
2nd Floor
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 2nd Floor
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | 2BHK | 641.2115 | 0 | 929.7566
3rd to 8th & 10th to 15th Floor
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 3rd to 8th & 10th to 15th Floor
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | 2BHK | 641.2115 | 0 | 929.7566
9th Floor (Part Refuge Area)
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 9th Floor (Part Refuge Area)
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | Refuge Area
Wing H
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 1st Floor For Residential
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | 2BHK | 641.2115 | 0 | 929.7566
2nd Floor
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 2nd Floor
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | 2BHK | 641.2115 | 0 | 929.7566
3rd to 8th & 10th to 15th Floor
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 3rd to 8th & 10th to 15th Floor
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | 2BHK | 641.2115 | 0 | 929.7566
9th Floor (Part Refuge Area)
1 |  | 2BHK | 633.0308 | 0 | 917.8947 | 9th Floor (Part Refuge Area)
2 |  | 2BHK | 641.2115 | 0 | 929.7566
3 |  | 2BHK | 641.2115 | 0 | 929.7566
4 |  | Refuge Area
Wing I
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | Refuge Area
Wing J
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | Refuge Area
4 |  | Society Office |  | 0 | 0
Wing K
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
3 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
4 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | Refuge Area
Wing L
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
3 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
4 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | Refuge Area
4 |  | Society Office |  | 0 | 0
Wing M to R
1st to 3rd Basement For Parking
Ground Floor Parking & Commercial
Wing M
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor
2 |  | Parapet Wall
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing N
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor (Part Refuge Area)
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | Refuge Area & Society Office
4
Wing O
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | Parapet Wall
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing P
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 9th Floor
2 |  | Parapet Wall
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing Q
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | Refuge Area & Society Office |  |  |  | 9th Floor (Part Refuge Area)
2
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Wing R
1st Floor For Residential
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 1st Floor For Residential
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
2nd Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 2nd Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
3rd to 8th & 10th to 15th Floor
1 |  | 1BHK | 322.4894 | 0 | 467.6097 | 3rd to 8th & 10th to 15th Floor
2 |  | 1BHK | 322.4894 | 0 | 467.6097
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
9th Floor (Part Refuge Area)
1 |  | Refuge Area & Society Office |  |  |  | 9th Floor (Part Refuge Area)
2
3 |  | 1BHK | 322.4894 | 0 | 467.6097
4 |  | 1BHK | 322.4894 | 0 | 467.6097
Remarks:
* | Wing B, C = All work completed. Part OC Received. Wing D, E & F = All work completed. OC Received. Wing G, H & I = Construction work is in process at the time of visit. Wing A = Work same as last visit dtd.18/05/2023 Wing J to L = Work not yet Started.. Wing M to R = Not Yet Launched. | [8 empty] | Wing G & I = Work same as last visit dtd.16/12/2024 Wing H =Work same as last visit dtd. 10/03/2025
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | The Project Approved is Approved by SRA (Slum Rehabilitation Authority) vide CC No.HE/MHADA/0028/20060821/AP/S6.
* | On RERA site only Wing A to L are registered. Wing M to R not yet Launched.
* | Ground floor plan is not legible & it consists of Shop. Please Provide legible approved Ground floor plan.
* | We have updated Approved Floor plan of Gulmohar Avenue Sale Building-S6 Wing A to L on (22/06/2023)
* | Construction work goes beyong C.C for Wing B, C, G, & H.
* | Please provide revised approved C.C.
* | Since Wing J, K & L have received CC on 18/12/2017, but as of construction work is not completed yet.
* | As per RERA, completion period of Gulmohar Avenue (Sale Building-S6 Bandra North) name is expired on 26/08/2024 but still project is under construction.
* | We have updated part OC for wing D, E & F (On 09/10/2024).
* | We have updated part OC for wing B & C (On 19/09/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Tushar Bhuwad |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Gulmohar Avenue (Sale Building-S6 Bandra North)
Layout :
Google Map :
Sale Building-S6
Wing A
Wing A
B
C
D
E
F
B
F
E
D
C
G
H
I Wing
J
I
G
H
B
C
D
E
F
Wing
B to E
Wing G
Wing H
Wing H
Wing I
Wing J, K & L
Wing J, K & L

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted