## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-07 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Megaplex Properties LLP | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Megaplex Properties LLP | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Commanders Heera Siddhi Homes Phase III | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Prashant Wani 9823553830
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Pratik 9764377264
Name / No of the Building |  |  |  | Wing B5 to B12
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC Cum NA Order, Sale Plans, & Cost Sheet. | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000023450 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Commanders Heera Siddhi Homes Phase III, Gut No.16, Hissa No. 02, near Vista Harmony, Savroli - Kharpada Road, Karade, Karade Khurd, Rasayani, Panvel, Raigad - 410220. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Gut No |  | 16, Hissa No. 02 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Karade | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Savroli - Kharpada Road |  | Locality/Village |  | Karade Khurd | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Rasayani |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410220 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Vista Harmony |  | Distance from city centre: |  | 5.00 KM from Rasayani Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Major District Road 89 |  |  | Internal Road
West | NA | Heera Siddhi Homes Phase I |  |  | Heera Siddhi Homes Phase I
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.880557,73.161596
Location Link |  | https://maps.app.goo.gl/XGrfibseCshQAw7b7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 12507.172
Permissible FSI |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  | 0.20725
Total FSI availaible for the project |  |  |  | 1.4072 |  |  |  | 1.4072
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 17600.689
Total number of Buildings |  |  |  | 08 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector Of Raigad | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | MS/LNA-1/S.R./236/2018 |  |  | Dated | 2019-10-22 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | MS/LNA-1/S.R./236/2018 |  |  | Dated | 2019-10-22 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
CC Cum NA Order No. Valid Up to: |  | MS/L.N.A.1(B)/S.R.236/2018 |  |  | Dated | 2019-10-22 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Wing B5 to B12 = Ground + 1st to 7th Floor Built Up Area = 176000.689 Sqm | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Wing B5 to B12 = Ground + 1st to 7th Floor Built Up Area = 176000.689 Sqm |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 17600.689
Approved no of units |  |  | Flats - 462, Shops - 18
Approved no of Floors |  |  | Wing B5 to B12 = Ground + 1st to 7th Floor
Proposed no of Floors |  |  | Wing B5 & B7 = Ground + 1st to 7th Floor
Wing B6 = Ground + 1st to 7th Floor
Wing B7 = Ground + 1st to 7th Floor
Wing B8 = Ground + 1st to 7th Floor
Wing B9, B10, B11 = Ground + 1st to 7th Floor
Wing B10 = Ground + 1st to 7th Floor
Wing B11 = Ground + 1st to 7th Floor
Wing B12 = Ground + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 30/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Swimming Pool, Landscape Garden, Children play area, Toddlers Park, Study Room, Library, Multi Purpose Hall, Yoga & Meditation Area, Senior Citizen Park, etc. |  |  |  |  | SALE PLAN
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing B5 & B7 = Ground + 1st to 7th Floor | [5 empty] | Excavation Completed, Footing work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation | , Footing work is process
Stage of construction: |  | Excavation Completed, Footing work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 2.5% |  | 26.25% |  | Excavation in process | 3.5
Plinth |  | 1.75 | 25% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B6 = Ground + 1st to 7th Floor | [5 empty] | Excavation Completed, Plinth work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation | , Plinth work is process
Stage of construction: |  | Excavation Completed, Plinth work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 3.5
Plinth |  | 5.25 | 75% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B7 = Ground + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 50% |  | 75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B8 = Ground + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 20% |  | 52.5% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 2 | 25% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B9 = Ground + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 15% |  | 48.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 1 | 12.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B10 = Ground + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed | , RCC upto 3 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 25% |  | 56.25% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 3 | 37.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B11 = Ground + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 30% |  | 60% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 4 | 50% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B12 = Ground + 1st to 7th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4300 | [11 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 200000 | [11 empty] | 1500000 | 600000 | 500000
Society Formation Charges |  |  |  |  | 20000 | [11 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 150000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 3440 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing B5 |  | 12 |  | 1874.7659 |  | 2812.1488
Wing B5 |  | 6 |  | 1983.5899 |  | 2975.3849
Total |  | 18 |  | 3858.3558 |  | 5787.5337
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing B5 |  | 70 |  | 31269.8721 |  | 46876.8637
Wing B6 |  | 70 |  | 29341.297 |  | 43987.0844
Wing B7 |  | 56 |  | 24025.6786 |  | 36414.4613
Wing B8 |  | 63 |  | 25330.4153 |  | 37931.2687
Wing B9 |  | 35 |  | 14220.6433 |  | 21154.9897
Wing B10 |  | 35 |  | 14220.6433 |  | 21154.9897
Wing B11 |  | 63 |  | 25330.4153 |  | 37931.2687
Wing B12 |  | 70 |  | 30855.3397 |  | 46454.022
Total |  | 462 |  | 194594.3045 |  | 291904.9484
Grand Total |  | 480 |  | 198452.6603 |  | 297692.4821
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Phase III
Wing B5
Ground Floor For Commercial, Entrance Lobby & Parking | [12 empty] | 10.764
7 |  | Shop | 129.6524 | 0 | 129.6524 | 0 | 194.4786
8 |  | Shop | 165.1198 | 0 | 165.1198 | 0 | 247.6796
9 |  | Shop | 168.2951 | 0 | 168.2951 | 0 | 252.4427
10 |  | Shop | 168.2951 | 0 | 168.2951 | 0 | 252.4427 | 15.635
11 |  | Shop | 165.1198 | 0 | 165.1198 | 0 | 247.6796
12 |  | Shop | 140.9008 | 0 | 140.9008 | 0 | 211.3511 | 13.09
13 |  | Shop | 140.9008 | 0 | 140.9008 | 0 | 211.3511
14 |  | Shop | 165.1198 | 0 | 165.1198 | 0 | 247.6796
15 |  | Shop | 168.2951 | 0 | 168.2951 | 0 | 252.4427
16 |  | Shop | 168.2951 | 0 | 168.2951 | 0 | 252.4427
17 |  | Shop | 165.1198 | 0 | 165.1198 | 0 | 247.6796
18 |  | Shop | 129.6524 | 0 | 129.6524 | 0 | 194.4786 | 11.99
Wing B12
Ground Floor For Commercial, Entrance Lobby & Parking | [12 empty] | 10.764
1 |  | Shop | 347.8064 | 0 | 347.8064 | 0 | 521.7096 | 32.0925
2 |  | Shop | 325.8263 | 0 | 325.8263 | 0 | 488.7394
3 |  | Shop | 318.1623 | 0 | 318.1623 | 0 | 477.2435
4 |  | Shop | 318.1623 | 0 | 318.1623 | 0 | 477.2435
5 |  | Shop | 325.8263 | 0 | 325.8263 | 0 | 488.7394
6 |  | Shop | 347.8064 | 0 | 347.8064 | 0 | 521.7096
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet + CB area | Encl Bal + WS Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 45% |  |  |  | 10.764
Phase III
Wing B5
Ground Floor For Commercial, Entrance Lobby & Parking | [12 empty] | 10.764
1st Floor For Residential
1 |  | 1BHK | 246.065 | 141.5358 | 387.6009 | 0 | 562.0213
2 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834 | 31.115 | 5.3625 | 6 |  |  | 6.95
3 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
4 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047 |  |  | 5800
5 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
6 |  | 1BHK | 246.065 | 141.5358 | 387.6009 | 0 | 562.0213 | 22.2225 | 6.95 | 5.2125
7 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
8 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
9 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
10 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
2nd, 4th & 6th Floor
1 |  | 1BHK | 246.065 | 142.7522 | 388.8172 | 0 | 563.785
2 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
3 |  | 1BHK | 349.5071 | 125.1207 | 474.6278 | 0 | 688.2103
4 |  | 1BHK | 349.5071 | 125.1207 | 474.6278 | 0 | 688.2103
5 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
6 |  | 1BHK | 246.065 | 142.7522 | 388.8172 | 0 | 563.785
7 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
8 |  | 1BHK | 349.5071 | 125.1207 | 474.6278 | 0 | 688.2103
9 |  | 1BHK | 349.5071 | 125.1207 | 474.6278 | 0 | 688.2103
10 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
3rd, 5th & 7th Floor
1 |  | 1BHK | 246.065 | 142.7522 | 388.8172 | 0 | 563.785
2 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
3 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
4 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
5 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
6 |  | 1BHK | 246.065 | 142.7522 | 388.8172 | 0 | 563.785
7 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
8 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
9 |  | 1BHK | 349.5071 | 100.299 | 449.806 | 47.9859 | 700.2047
10 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
Wing B6
Ground Floor For Entrance Lobby & Parking
1st , 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 269.1 | 128.8451 | 397.9451 | 0 | 577.0204 |  |  | 10.764
2 |  | 1BHK | 285.1168 | 95.8642 | 380.981 | 32.4104 | 584.8329
3 |  | 1BHK | 285.1168 | 96.4777 | 381.5946 | 32.4104 | 585.7225 | 24.495 | 4.95 | 3.7125
4 |  | 1BHK | 322.9523 | 96.4777 | 419.43 | 50.6231 | 658.7966
5 |  | 1BHK | 322.9523 | 95.8642 | 418.8165 | 47.9536 | 655.2375
6 |  | 1BHK | 322.9523 | 95.8642 | 418.8165 | 49.2884 | 656.5722
7 |  | 1BHK | 322.9523 | 96.4777 | 419.43 | 49.2884 | 657.4619
8 |  | 1BHK | 322.9523 | 96.4777 | 419.43 | 49.2884 | 657.4619
9 |  | 1BHK | 322.9523 | 96.4777 | 419.43 | 49.2884 | 657.4619
10 |  | 1BHK | 289.5193 | 156.0457 | 445.565 | 0 | 646.0693
2nd, 4th & 6th Floor
1 |  | 1BHK | 269.1 | 128.8343 | 397.9343 | 0 | 577.0048 |  |  | 10.764
2 |  | 1BHK | 285.1168 | 110.6001 | 395.7169 | 0 | 573.7896
3 |  | 1BHK | 285.1168 | 111.2029 | 396.3197 | 0 | 574.6636
4 |  | 1BHK | 322.9523 | 119.4804 | 442.4327 | 0 | 641.5274
5 |  | 1BHK | 322.9523 | 117.6613 | 440.6136 | 0 | 638.8897
6 |  | 1BHK | 322.9523 | 118.2641 | 441.2164 | 0 | 639.7637
7 |  | 1BHK | 322.9523 | 118.8776 | 441.8299 | 0 | 640.6534
8 |  | 1BHK | 322.9523 | 118.8776 | 441.8299 | 0 | 640.6534
9 |  | 1BHK | 322.9523 | 118.8776 | 441.8299 | 0 | 640.6534
10 |  | 1BHK | 289.5193 | 155.9381 | 445.4574 | 0 | 645.9132
Wing B7
Ground Floor For Entrance Lobby & Parking
1st, 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619 |  |  | 10.764
2 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
3 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
4 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
5 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
6 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
7 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
8 |  | 1BHK | 314.664 | 104.766 | 419.43 | 49.2884 | 657.4619
2nd, 4th & 6th Floor
1 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534 |  |  | 10.764
2 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
3 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
4 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
5 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
6 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
7 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
8 |  | 1BHK | 314.664 | 127.1659 | 441.8299 | 0 | 640.6534
Wing B8
Ground Floor For Entrance Lobby & Parking
1st , 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 269.1 | 130.4382 | 399.5382 | 0 | 579.3303 |  |  | 10.764
2 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 33.7451 | 586.152
3 |  | 1BHK | 285.1061 | 96.4885 | 381.5946 | 33.7451 | 587.0573
4 |  | 1BHK | 322.9415 | 96.4562 | 419.3977 | 50.6231 | 658.7498
5 |  | 1BHK | 322.9415 | 95.8642 | 418.8057 | 50.1279 | 657.3962
6 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 33.7451 | 586.152
7 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 49.2776 | 657.4199
8 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 49.2776 | 657.4199
9 |  | 1BHK | 269.1 | 129.4371 | 398.5371 | 0 | 577.8788
2nd, 4th & 6th Floor
1 |  | 1BHK | 269.1 | 130.4382 | 399.5382 | 0 | 579.3303 |  |  | 10.764
2 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 0 | 552.4069
3 |  | 1BHK | 285.1061 | 96.4885 | 381.5946 | 0 | 553.3121
4 |  | 1BHK | 322.9415 | 96.4562 | 419.3977 | 0 | 608.1267
5 |  | 1BHK | 322.9415 | 95.8642 | 418.8057 | 0 | 607.2683
6 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 0 | 552.4069
7 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 0 | 608.1423
8 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 0 | 608.1423
9 |  | 1BHK | 269.1 | 129.4371 | 398.5371 | 0 | 577.8788
Wing B9
Ground Floor For Entrance Lobby & Parking
1st , 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 285.1061 | 96.467 | 381.573 | 33.7451 | 587.026 |  |  | 10.764
2 |  | 1BHK | 285.1061 | 100.5035 | 385.6095 | 0 | 559.1338
3 |  | 1BHK | 269.1 | 130.6427 | 399.7427 | 0 | 579.6269
4 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 50.6123 | 658.7546
5 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 49.4068 | 657.5491
2nd, 4th & 6th Floor
1 |  | 1BHK | 285.1061 | 111.8057 | 396.9117 | 0 | 575.522 |  |  | 10.764
2 |  | 1BHK | 285.1061 | 100.5035 | 385.6095 | 0 | 559.1338
3 |  | 1BHK | 269.1 | 130.6427 | 399.7427 | 0 | 579.6269
4 |  | 1BHK | 322.9415 | 119.4804 | 442.4219 | 0 | 641.5118
5 |  | 1BHK | 322.9415 | 118.2641 | 441.2056 | 0 | 639.7481
Wing B10
Ground Floor For Entrance Lobby & Parking
1st , 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 285.1061 | 100.5035 | 385.6095 | 0 | 559.1338 |  |  | 10.764
2 |  | 1BHK | 285.1061 | 96.467 | 381.573 | 33.7451 | 587.026
3 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 49.4068 | 657.5491
4 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 50.6123 | 658.7546
5 |  | 1BHK | 269.1 | 130.6427 | 399.7427 | 0 | 579.6269
2nd, 4th & 6th Floor
1 |  | 1BHK | 285.1061 | 100.5035 | 385.6095 | 0 | 559.1338 |  |  | 10.764
2 |  | 1BHK | 285.1061 | 111.8057 | 396.9117 | 0 | 575.522
3 |  | 1BHK | 322.9415 | 118.2641 | 441.2056 | 0 | 639.7481
4 |  | 1BHK | 322.9415 | 119.4804 | 442.4219 | 0 | 641.5118
5 |  | 1BHK | 269.1 | 130.6427 | 399.7427 | 0 | 579.6269
Wing B11
Ground Floor For Entrance Lobby & Parking
1st , 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 269.1 | 129.4371 | 398.5371 | 0 | 577.8788 |  |  | 10.764
2 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 49.2776 | 657.4199
3 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 49.2776 | 657.4199
4 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 33.7451 | 586.152
5 |  | 1BHK | 322.9415 | 95.8642 | 418.8057 | 50.1279 | 657.3962
6 |  | 1BHK | 322.9415 | 96.4562 | 419.3977 | 50.6231 | 658.7498
7 |  | 1BHK | 285.1061 | 96.4885 | 381.5946 | 33.7451 | 587.0573
8 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 33.7451 | 586.152
9 |  | 1BHK | 269.1 | 130.4382 | 399.5382 | 0 | 579.3303
2nd, 4th & 6th Floor
1 |  | 1BHK | 269.1 | 129.4371 | 398.5371 | 0 | 577.8788 |  |  | 10.764
2 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 0 | 608.1423
3 |  | 1BHK | 322.9415 | 96.467 | 419.4085 | 0 | 608.1423
4 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 0 | 552.4069
5 |  | 1BHK | 322.9415 | 95.8642 | 418.8057 | 0 | 607.2683
6 |  | 1BHK | 322.9415 | 96.4562 | 419.3977 | 0 | 608.1267
7 |  | 1BHK | 285.1061 | 96.4885 | 381.5946 | 0 | 553.3121
8 |  | 1BHK | 285.1061 | 95.8642 | 380.9703 | 0 | 552.4069
9 |  | 1BHK | 269.1 | 130.4382 | 399.5382 | 0 | 579.3303
Wing B12
Ground Floor For Commercial, Entrance Lobby & Parking
1st Floor For Residential
1 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 0 | 654.4975 |  |  | 10.764
2 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 0 | 654.4975
3 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 0 | 654.4975
4 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 0 | 654.4975
5 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 0 | 606.8
6 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 49.4068 | 656.2068
7 |  | 1BHK | 315.5144 | 103.5712 | 419.0856 | 47.9536 | 655.6277
8 |  | 1BHK | 315.5144 | 103.5712 | 419.0856 | 49.2776 | 656.9517
9 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 49.2776 | 656.0776
10 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 50.6123 | 657.4124
3rd, 5th & 7th Floor
1 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
2 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
3 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
4 |  | 1BHK | 350.4758 | 100.9017 | 451.3776 | 47.9859 | 702.4834
5 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 50.6123 | 657.4124
6 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 49.4068 | 656.2068
7 |  | 1BHK | 315.5144 | 103.5712 | 419.0856 | 47.9536 | 655.6277
8 |  | 1BHK | 315.5144 | 103.5712 | 419.0856 | 49.2776 | 656.9517
9 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 49.2776 | 656.0776
10 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 50.6123 | 657.4124
2nd, 4th & 6th Floor
1 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
2 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
3 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
4 |  | 1BHK | 350.4758 | 125.7235 | 476.1994 | 0 | 690.4891
5 |  | 1BHK | 315.5144 | 125.9711 | 441.4855 | 0 | 640.1539
6 |  | 1BHK | 315.5144 | 124.7655 | 440.2799 | 0 | 638.4058
7 |  | 1BHK | 315.5144 | 125.3683 | 440.8827 | 0 | 639.2799
8 |  | 1BHK | 315.5144 | 125.9711 | 441.4855 | 0 | 640.1539
9 |  | 1BHK | 315.5144 | 125.3683 | 440.8827 | 0 | 639.2799
10 |  | 1BHK | 315.5144 | 102.9684 | 418.4828 | 0 | 606.8
Remarks:
* | Wing B5 to B7 = Construction work same as last visit dtd 15/03/2024. Wing B8 to B10 = Construction work ame as last visit dtd 13/06/2025 but work is in process at the time of Visit (Very Slow Speed). Wing B11 = Construction work is in process at the time of Visit (Slow Speed). Wing B12 = Work not started yet.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + CB Area + Encl Balcony + WS Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | As per the builder letter provided, there is a typing error in the CC where Buildings B10 and B11 are mentioned as ए10 and ए11. As per layout, the built-up area of buildings B5 to B12 is 176000.689 sq m. As per NA cum CC, the built-up area of Buildings B5 to B9, A10, A11, and B12 is 176000.689 sq m. As the builtup is same we have considered the CC for Buildings B10 and B11 . The builder letter is attached below.
* | The project has received first CC on 22/10/2019, But construction work is not yet Completed of Wing B5 to B11 And construction work is not yet started of Wing B12.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh patil |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Commanders Heera Siddhi Homes Phase III
Layout :
Builder Letter:
Google Map :
Formulas:
Karade Khurd = [Karade Khurd, row above]
WING B5
WING B6
WING B7
WING B8
WING B12
WING B11
WING B10
WING B9
Phase I
Phase III
Phase II
Commanders Heera Siddhi Homes
B5
B6
B7
B8
B9
B10
B11
B5
B6
B7
B8
B9
B10
B11
B12
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F197: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H251: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate