## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-13
Name of the builder group |  |  |  | Eco Luxuria Developers Private Limited
Name of the builder company |  |  |  | Eco Luxuria Developers Private Limited
Name of the Project |  |  |  | Eco Luxuria Pride
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr.Sadashiv Patil 7709142578
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Ms. Kaveri Patil 9172941188 |  |  |  | Miss. Lata Thorat 9623726402
Name / No of the Building |  |  |  | Wing A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P52000029150
Project location details |  | Eco Luxuria Pride, Survey No.19/2A, Plot No.1 & 2, near Gurukul Society, Guru Nagar Road, Guru Nagar, Mudre, Karjat East, Karjat, Raigad - 410201.
Survey No |  | 19/2A, Plot No.1 & 2
Locality |  | Guru Nagar
Road |  | Guru Nagar Road |  | Locality/Village |  | Mudre
City |  | Karjat East |  | District |  | Raigad
Taluka |  | Karjat |  | Pin Code |  | 410201
Nearby Landmark |  | Gurukul Society |  | Distance from city centre: |  | 1.7 KM from Karjat Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Gurukul Society
West | NA | NA |  |  | Bungalows
North | NA | NA |  |  | Houses
South | NA | NA |  |  | Gurunagar Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 18.91669,73.330398
Location Link |  | https://goo.gl/maps/fH32XAXZPrqSUohF7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1359
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1477
Total FSI availaible for the project |  |  |  | 2.2477
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3054.67
Total number of Buildings |  |  |  | 01 Building - 3 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Karjat Municipal Council
Layout Approval No |  | S.R-19/20-21 |  |  | Dated | 2021-03-31
Approved Floor plan No. |  | S.R-19/20-21 |  |  | Dated | 2021-03-31
Commencement-CC No Valid Up to: |  | BD/KT-1/S.R.19/2021 |  |  | Dated | 2021-03-31
A, B & C Wing = G + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3054.67
Approved no of units |  |  | Flats - 63, Shops - 10
Approved no of Floors |  |  | A, B & C Wing = G + 1st to 7th Floor
Proposed no of Floors |  |  | A, B & C Wing = G + 1st to 7th Floor
B Wing = G + 1st to 7th Floor
C Wing = G + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = G + 1st to 7th Floor C Wing = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 6 Floor Completed | , Finishing upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 94.29% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 85.71% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | B Wing = G + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | C Wing = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 6 Floor Completed | , Finishing upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 94.29% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 85.71% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3400
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 200000
Club Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation, Water, Electricity Connection Charges |  |  |  |  | 60000
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 2720
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops (Wing A + B) |  | 10 |  | 860.3665 |  | 1333.5681
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 21 |  | 10341.8897 |  | 15512.8346
Wing B |  | 28 |  | 12332.5839 |  | 18498.8758
Wing C |  | 14 |  | 6105.0717 |  | 9157.6076
Total |  | 63 |  | 28779.5453 |  | 43169.318
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Wing A + B
Ground Floor For Part Commercial & Part Parking
1 |  | Shop | 100.1052 | 0 | 155.1631 | Ground Floor For Part Commercial & Part Parking |  | 13211.9075
2 |  | Shop | 75.1327 | 0 | 116.4557 |  |  | 12410.2968
3 |  | Shop | 100.1052 | 0 | 155.1631
4 |  | Shop | 100.1052 | 0 | 155.1631
5 |  | Shop | 75.1327 | 0 | 116.4557
6 |  | Shop | 100.1052 | 0 | 155.1631
7 |  | Shop | 70.5042 | 0 | 109.2815
8 |  | Shop | 69.5354 | 0 | 107.7799
9 |  | Shop | 69.5354 | 0 | 107.7799
10 |  | Shop | 100.1052 | 0 | 155.1631
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A
1st to 7th Floor For Residential
101 to 701 |  | 2 | 608.3275 | 0 | 912.4912 | 1st to 7th Floor For Residential |  |  | 3324.0869
102 to 702 |  | 1 | 432.1208 | 0 | 648.1812 |  |  |  | 3395.9641
103 to 703 |  | 1 | 436.9646 | 0 | 655.4469 |  |  |  | 3480.3736
Wing B
1st to 7th Floor For Residential
101 to 701 |  | 1 | 436.0765 | 0 | 654.1148 | 1st to 7th Floor For Residential
102 to 702 |  | 1 | 436.0765 | 0 | 654.1148
103 to 703 |  | 1 | 452.68 | 0 | 679.02
104 to 704 |  | 1 | 436.9646 | 0 | 655.4469
Wing C
1st to 7th Floor For Residential
101 to 701 |  | 1 | 436.0765 | 0 | 654.1148 | 1st to 7th Floor For Residential
102 to 702 |  | 1 | 436.0765 | 0 | 654.1148
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0
3 |  |  |  | 0 | 0
4 |  |  |  | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0
203 |  |  |  | 0 | 0
204 |  |  |  | 0 | 0
205 |  |  |  | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0
203 to 503 |  |  |  | 0 | 0
204 to 504 |  |  |  | 0 | 0
205 to 505 |  |  |  | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0
203 & 503 |  |  |  | 0 | 0
204 & 504 |  |  |  | 0 | 0
205 & 505 |  |  |  | 0 | 0
Remarks:
* | Wing A & C = Finishing work is in process at the time of Visit. Wing B = All work completed. Provide OC.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Eco Luxuria Pride
Layout :
Google Map :
Formulas:
Mudre = [Mudre, row above]
WING A
WING B
WING C
Wing A
Wing B
Wing C
Wing B
Wing B
Wing C
Wing B
Wing A
Wing C
Wing B
Wing A
Wing A
Wing B
Wing C
Wing C
Wing A
Wing A
Wing B
Wing C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted