## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Techcons Constructional Engineering Co
Name of the builder company |  |  |  | Techcons Constructional Engineering Co
Name of the Project |  |  |  | Techcons Basera
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Rahul 9096911385
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Nitesh Gaikwad 9822954320 |  |  |  | Mr. Mohit 9834959928
Name / No of the Building |  |  |  | Wing A, B & C
Docouments Provided |  |  |  | Approved Plans & CC
RERA No. |  |  |  | P51700031861
Project location details |  | Techcons Basera, Survey No.287/2, near Hari Rup Appartment, Internal Road, Dyandeep Nagar, Murbad, Murbad, Murbad, Thane - 421401.
Survey No |  | 287/2
Locality |  | Dyandeep Nagar
Road |  | Internal Road |  | Locality/Village |  | Murbad
City |  | Murbad |  | District |  | Thane
Taluka |  | Murbad |  | Pin Code |  | 421401
Nearby Landmark |  | Hari Rup Appartment |  | Distance from city centre: |  | 0.950KM from Murbad Bus Depot
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Proposed 7.5 M Internal Road |  |  | Row Houses
West | NA | Hiss No.1 |  |  | Saduru Krupa Building
North | NA | 4.5 M Pathway/Wing E |  |  | Internal Road
South | NA | Other Plot |  |  | Vaishya Samaj Hall
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.252417,73.389361
Location Link |  | https://maps.app.goo.gl/SXrxzzW8v3DEN8jQ9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4800
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.256
Total FSI availaible for the project |  |  |  | 2.356
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 11308.76
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Murbad Nagarpanchayat, Murbad
Layout Approval No |  | MNP/PRV/10/2024-25 |  |  | Dated | 2024-04-23
Approved Floor plan No. (Wing A) |  | BS/Rekhakan/BP/M. Murbad/T. Murbad/SSTN/122 |  |  | Dated | 2021-01-12
Approved Floor plan No. (Wing B & C) |  | MNP/PRV/10/2024-25 |  |  | Dated | 2024-04-23
Commencement-CC No Valid Up to: |  | MNP/NRV/BP/10/2024-2025 |  |  | Dated | 2024-04-23
Wing A, B & C = Gr+ 1st to 7th Floor
O. Certificate No.: |  | M.N.P/NRV/72/2025 Approved upto : Wing B = Gr + 1st to 7th Floor |  |  | Dated | 2025-05-06
Building wise Construction details
Approved Builtup Area of Wing A, B & C (Sq.Mt) |  |  | 6536.26
Approved no of units |  |  | Flats -119
Approved no of Floors |  |  | Wing A, B & C = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Wing A = Gr + 1st to 7th Floor
Wing B = Gr + 1st to 7th Floor
Wing C = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work completed. Provide OC | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B = Gr + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work completed. Provide OC | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B = Gr + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing C = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 5 Floor Completed | , Flooring upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 82.14% |  | 93.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500 |  |  |  | 3400 to 3500 | 2023-12-19 | Rushikesh | Verbal
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 44 |  | 18833.4393 |  | 30199.5451
Wing B |  | 35 |  | 14524.0783 |  | 23406.4009
Wing C |  | 40 |  | 19816.017 |  | 31757.4054
Total |  | 119 |  | 53173.5346 |  | 85363.3514
Building Details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace/ Otla area | Saleable area Loading : | Floor
50%
Wing A
Ground Floor For Residential & Parking | [8 empty] | 10.764
1 |  | 1BHK | 391.4587 | 35.392 | 622.5801 | Ground Floor For Residential & Parking |  | 39.5464
2 |  | 1BHK | 391.4587 | 35.392 | 622.5801
1st, 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 391.4587 | 44.8299 | 632.0179 | 1st, 3rd, 5th & 7th Floor For Residential
2 |  | 2BHK | 506.5786 | 44.1755 | 804.0434 |  |  | 42.2683 | 5.355 | 47.6233
3 |  | 2BHK | 506.5786 | 44.1755 | 804.0434 |  |  | 2736.1709
4 |  | 1BHK | 391.4587 | 44.8299 | 632.0179
5 |  | 1BHK | 391.4587 | 44.8299 | 632.0179
6 |  | 1BHK | 391.4587 | 44.8299 | 632.0179
2nd, 4th & 6th Floor
1 |  | 1BHK | 391.4587 | 44.8299 | 632.0179 | 2nd, 4th & 6th Floor
2 |  | 2BHK | 506.1749 | 44.9935 | 804.2559
3 |  | 2BHK | 506.1749 | 44.9935 | 804.2559 |  |  | 3226.5848
4 |  | 1BHK | 391.4587 | 44.8299 | 632.0179
5 |  | 1BHK | 391.4587 | 44.8299 | 632.0179
6 |  | 1BHK | 391.4587 | 44.8299 | 632.0179
Wing B
Ground Floor For Meter Room & Parking | [8 empty] | 10.764
1st, 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 416.9554 | 44.8299 | 670.263 | 1st, 3rd, 5th & 7th Floor For Residential |  | 3282.2938 | 38.7361
2 |  | 1BHK | 416.9554 | 57.6391 | 683.0721
3 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 |  |  |  | 38.2564
4 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
5 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
2nd, 4th & 6th Floor
1 |  | 1BHK | 416.9554 | 44.8299 | 670.263 | 2nd, 4th & 6th Floor
2 |  | 1BHK | 429.9798 | 44.8299 | 689.7996
3 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
4 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
5 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
Wing C
Ground Floor For Meter Room & Parking | [8 empty] | 10.764
1st Floor For Residential
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 1st Floor For Residential
2 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
3 |  | 1RK | 304.4339 | 44.9935 | 501.6444
4 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
5 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
6 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
7 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
2nd Floor
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 2nd Floor
2 |  | 2.5BHK | 764.7639 | 44.8299 | 1191.9758 |  |  | 99.4594
3 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
4 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
5 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
6 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
3rd Floor
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 3rd Floor
2 |  | 2.5BHK | 737.827 | 89.8234 | 1196.5639 |  |  | 72.6708
3 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
4 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
5 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
6 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
4th Floor
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 4th Floor
2 |  | 2.5BHK | 764.7639 | 44.8299 | 1191.9758
3 |  | 2.5BHK | 832.4878 | 109.9478 | 1303.7055
5 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
6 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
5th Floor
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 5th Floor
2 |  | 2.5BHK | 737.827 | 89.8234 | 1196.5639
3 |  | 2.5BHK | 830.9205 | 92.2776 | 1338.6584
6 |  | 2.5BHK | 830.9205 | 92.2776 | 1338.6584
6th Floor
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 6th Floor
2 |  | 2.5BHK | 764.7639 | 44.8299 | 1191.9758
3 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
4 |  | 1BHK | 450.7231 | 44.8299 | 720.9146
5 |  | 1BHK | 450.7231 | 44.8299 | 720.9146
6 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
7th Floor
1 |  | 1BHK | 411.7919 | 44.8299 | 662.5177 | 7th Floor
2 |  | 2.5BHK | 737.827 | 89.8234 | 1196.5639
3 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
4 |  | 1BHK | 450.7231 | 44.8299 | 720.9146
5 |  | 1BHK | 450.7231 | 44.8299 | 720.9146
6 |  | 1BHK | 411.7919 | 44.8299 | 662.5177
Remarks:
1 | Wing A = All work completed. Provide OC Wing B = All work completed. OC Received. Wing C = Construction work is in process at the time of Visit. (Slow Speed)
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony Area + Otla Area.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | Recommended Rates of the Property have been revised on 19/12/2023.
11 | We have updated Revised approved CC & appoved plans for Wing B & C on 16/05/2024 | [8 empty] | Earlier approved plans & CC (dtd 12/01/2021) were provided of town planning thane authority, as now provided approved plans & CC are of Murbad Nagarpanchayat, Murbad for B & C Wings. Please check transfer authority letter.
12 | Earlier approved plans & CC (dtd 12/01/2021) were provided of town planning thane authority, as now provided approved plans & CC are of Murbad Nagarpanchayat, Murbad for B & C Wings. Please check transfer authority letter.
12 | The builder has provided architecture letter regarding transfer of authorities for the project Techcons Basera. (Document attached below) | [6 empty] | Remark changed on basis of mail |  | With ref to above remark, bank officials has sent document on whatsapp which is attached below on 06/07/2024.
13 | We have updated OC for Wing B (on 27/06/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Techcons Basera
Remark No. 12 Architecture Letter
Layout :
Google Map :
Wing B
Wing A
Wing C
Wing D
Wing E
Techcons Basera
Wing C
Wing A
Wing B
Wing C
Wing A
Wing B
Wing C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted