## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group |  |  |  |  | M/s. Balaji Construction Company.
Name of the builder company |  |  |  |  | M/s. Balaji Construction Company.
Name of the Project |  |  |  |  | Trinity Oasis
Contact Number |  |  |  |  | NA
Name & No of Buildings |  |  |  |  | Wing S1, S2, S3 & S4
Docouments Provided |  |  |  |  | Refer Data
RERA No. |  |  |  |  | Wing S1, S2, S3 =P51700016602 Wing S4 = P51700008216
Project location details |  | Trinity Oasis, S. No. 98 H. No. 3,A B,6, New S. No. 100 H. No. 16 & 34, Ghodbunder Road, Thane - 4000615
S. No. | 98 H. No. 3,A B,6, New S. No. 100 H. No. 16 & 34 |  |  |  |  | Locality | Bhayandarpada
Road | Ghodbunder Road |  |  |  | District | Thane
City | Thane |  |  |  | Pin Code | 400615
Near by Landmark |  | Ramah Bali |  |  | Distance from city centre: |  | About 11.6Km from Thane Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | G. B. Road |  | Vihang's Project |  | Road |  | Ramah Bali
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.2824972,72.9519517
Location Link |  | https://goo.gl/maps/1hrTLYFGusrosvMC8
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 11291.562
Permissible FSI |  |  |  |  | 1
Additional FSI |  |  |  |  | 3424.56
FSI Credit available by development |  |  |  |  | 1100
Total FSI availaible for the project |  |  |  |  | 14716.122
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 15753.388
Total number of Buildings |  |  |  |  | 04 Wing
Approval Detail : Plan approval
Layout Approval No |  | V. P. No. S06/0131/12/TMC/TD-DP/TPS/1128/14 |  |  |  | Dated | 14/04/2014.
Building plan approval No |  | V. P. No. S06/0131/12/TMC/TD-DP/TPS/1128/14 |  |  |  | Dated | 14/04/2014. | Expiry date:NA
C.certificate No |  | V. P. No. S06/0131/12/TMC/TDD/TPS/1128/14 Valid Up to: (Wing S1) = Basement + Stilt + 6th Floor (Wing S2) = Basement + ½ Stilt + ½ Ground + 3rd Floor (Wing S3) = Basement + ½ Stilt + ½ Ground + 29th Floor (Wing S4) = ½ Stilt + ½ Ground + 19th Floor |  |  |  | Dated | 14/04/2014. | Expiry date: One year from date of issue
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 14/04/2014. |  | Expected Completion |  | 30/12/2024.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 15753.388 |  | Approved no of units |  |  | NA
Approved no of Floors |  | (Wing S1) = Basement + Stilt + 6th Floor (Wing S2) = Basement + ½ Stilt + ½ Ground + 3rd Floor (Wing S3) = Basement + ½ Stilt + ½ Ground + 29th Floor (Wing S4) = ½ Stilt + ½ Ground + 19th Floor
Proposed no of Floors |  | (Wing S1) = Basement + Stilt + 1st to 19th Floor (Wing S2) = Basement + ½ Stilt + ½ Ground + 1st to 29th Floor (Wing S3) = Basement + ½ Stilt + ½ Ground + 1st to 29th Floor (Wing S4) = ½ Stilt + ½ Ground + 1st to 19th Floor
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | (Wing S1) = Basement + Stilt + 1st to 19th Floor | [6 empty] | Excavation work completed, Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 19 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% |  | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% | [5 empty] | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 14.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 19
Construction details: |  | (Wing S2) = Basement + ½ Stilt + ½ Ground + 1st to 29th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 29 | All work Completed. Provide OC.
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 14.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 29
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 29
Construction details: |  | (Wing S3) = Basement + ½ Stilt + ½ Ground + 1st to 29th Floor | [6 empty] | Excavation work completed, Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 29 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% |  | 10% |  | 45% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% | [5 empty] | Excavation Completed | 29
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 29
Construction details: |  | (Wing S4) = ½ Stilt + ½ Ground + 1st to 19th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 20 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 13 Floor completed, External Plaster upto 13 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 19 | All work Completed. Provide OC.
Stage of construction: |  | Plinth, RCC, Brickwork & Plaster upto 13th Floor Completed. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% |  | 69.47% |  | 86.84% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% | [5 empty] | Excavation Completed | 19
RCC (Including podiums) |  | 20 | 100% | [5 empty] | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 19 | 100% | [5 empty] | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 68.42% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 68.42% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 14.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 19
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Super builtup area) | [5 empty] | 7700
Floor rise rate Per Sq. Ft. (From 2nd Floor) | [5 empty] | 50/-
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 200000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 6160
Remarks: 1. We have release report on the basis of other vendor report. 2. Construction work was stopped at the time of visit. Work is same as last visit (06/02/2021) 3. Car parking is subjected to authentic documentation. 4. We have considered rate by verifying it from market inquire. 5. As per RERA, completion period of project is expired on 30/12/2024 but still project is under construction. The project is not available on RERA site (Checked on 13/06/2025).
Authorized Signatory Name & Seal of the agency
Photographs of Property : |  |  | Trinity Oasis
Google Map :

## S1 & S3 %
Particulars | totaL floor | 19
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 20 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 19 | 0 | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 19 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 19 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## S4 %
Particulars | totaL floor | 19
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 20 | 20 | 100 | Progress |  |  | 10 | 40 | 15 | 6.8421 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 68.4211 | Recommended |  |  | 30 | 30 | 15 | 6.8421 | 0 | 0 | 0
| 19 | 19 | 0
plaster | Total Floor | completed Floor | 0
| 19 | 13 | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 19 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 19 | 0 |  | Plaster | 6.8421 | 6.8421
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 71.8421 | 81.8421

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Trinity Oasis | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted