## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | M/s. Royal Realtors
Name of the builder company |  |  |  | M/s. Royal Realtors
Name of the Project |  |  |  | Royal Pristo
Contact Details ( Name & Contact No.) |  |  |  | Mr. Mitesh Gada 022-67193333/7710033007
Site Meet Person Details ( Name & Contect No.) |  |  |  | Ms Priti Gadige 9852301111 |  |  |  | Ms. Janvi Ambre 7400063333
Name / No of the Building |  |  |  | Wing A to D
Docouments Provided |  |  |  | Approved Plans,
RERA No. |  |  |  | P51800019529
Project location details |  | Royal Pristo, CTS No.712, 713, 714, 715, 716, 717/A, 717/1 to 7 & 13, 717/B, 719, 720, 720/1 to 2, 721, 721/1 to 6, 722, 723, 724, 724/1 to 2 & 725, near Lotus Apartment, Santoshi Mata Mandir Road, Kurar, Malad, Borivali, Mumbai.
CTS No |  | 712, 713, 714, 715, 716, 717/A, 717/1 to 7 & 13, 717/B, 719, 720, 720/1 to 2, 721, 721/1 to 6, 722, 723, 724, 724/1 to 2 & 725
Road |  | Santoshi Mata Mandir Road |  | Locality/Village |  | Kurar
City |  | Malad |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400097
Nearby Landmark |  | Lotus Apartment |  | Distance from city centre: |  | 2.8Km from Malad Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Lotus Apartment
West | NA | NA |  |  | Triveni Nagar Road
North | NA | NA |  |  | Slum
South | NA | NA |  |  | Royal Crystal
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.1843663,72.8638845
Location Link |  | https://goo.gl/maps/v1CcX64S7Fi7dU74A
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 12553.1
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 4
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 47665.31
Total number of Buildings |  |  |  | 04 Wings
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/PN/PVT/175/20160116/AP/S |  |  | Dated | 2020-12-11
Approved Floor plan No. |  | SRA/ENG/PN/PVT/175/20160116/AP/S |  |  | Dated | 2020-12-11
Commencement Certificate No. |  | PN/PVT/175/20160116/AP/Sale |  |  | Dated | 2021-10-07
Valid Up to:This CC is further extended for only RCC Framework to 15th to 18th floors of sale wing A to D as per approved amended plans dated 11/12/2020.
Commencement Certificate No. |  | PN/PVT/175/20160116/AP/Sale |  |  | Dated | 2022-12-20
Valid Up to: This further CC is extended to sale wing A & B for 1st to 4th upper floors (Including brickwork) & only RCC framework for 19th to 20th upper floors & for sale wing C & D only RCC framework 19th to 24th upper floor as per approved amended plans dated 11/12/2020.
Commencement Certificate No. |  | PN/PVT/175/20160116/AP/Sale |  |  | Dated | 2023-10-25
Valid Up to: This further CC is extended to sale wing A & B from 5th to 20th upper floor (including brickwork) along with LMR & OHWT as per approved plans dated 11/12/2020.
Commencement Certificate No. |  | PN/PVT/175/20160116/AP/Sale |  |  | Dated | 2024-02-15
Valid Up to: This further CC is extended to sale wing C & D from 5th to 18th upper floor (including brickwork) as per approved amended plans dated 11/12/2020.
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 47665.31
Approved no of units |  |  | Flats = 624
Approved no of Floors |  |  | Wing A & B = B + Gr/St + 3P + 1st to 20th Floor Wing C & D = B + Gr/St + 1st to 24th Floor
Proposed no of Floors |  |  | Wing A = B + Gr/St + 3P + 1st to 20th Floor
Wing B = B + Gr/St + 3P + 1st to 20th Floor
Wing C & D = B + Gr/St + 1st to 24th Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A & B = B + Gr/St + 3P + 1st to 20th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 20
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 92.75% |  | 95% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5 |  | 23
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 19 | 95% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 60% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | Wing B = B + Gr/St + 3P + 1st to 20th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 14 Floor Completed, Painting upto 14 Floor Completed.
1 | 0 | Ground | 1 | Podium | 3 | Floors | 20
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 14 Floor Completed, Painting upto 14 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 85.5% |  | 93.5% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5 |  | 23
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 14 | 70% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 14 | 70% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | Wing C = B + Gr/St + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 22 Floor Completed, Painting upto 18 Floor Completed.
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 22 Floor Completed, Painting upto 18 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 87.92% |  | 94.58% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 91.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Construction details: |  | Wing D = B + Gr/St + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 18 Floor Completed, Painting upto 9 Floor Completed.
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 18 Floor Completed, Painting upto 9 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 84.38% |  | 93.75% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 9 | 37.5% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Carpet area) |  |  |  |  | 21000 |  |  | 17000 to 18500 | Market inquiry |  | 2022-07-05
Floor Rise Rate Per Sq.ft (From 2nd Floor) |  |  |  |  | 80/- |  |  | 18500 to 21000 | Shailesh | Verbal | 2024-12-11
Development Charges |  |  |  |  | 3,00,000/-
Club Charges |  |  |  |  | NA
Society Formation |  |  |  |  | 5000/-
Electrical Meter Charges |  |  |  |  | 10000/-
One Time Membership Fee for Gym |  |  |  |  | 50,000/-
Maintenance Charges for 18th months |  |  |  |  | 50,000/-
Recommended rate of Parking |  |  |  |  | 7,00,000/-
Distressed valuation of the Property |  |  |  |  | 16800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 120 |  | 66589.3332 |  | 99883.9998
Wing B |  | 120 |  | 66296.5524 |  | 99444.8286
Wing C |  | 168 |  | 54250.56 |  | 81375.84
Wing D |  | 216 |  | 69750.72 |  | 104626.08
Total |  | 624 |  | 256887.1656 |  | 385330.7484
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Wing A & B
Basement Floor for Parking
Ground Floor for Commercial and Entrance Lobby
1st Podium Floor for Commercial and Parking
2nd & 3rd Podium Floor for Commercial and Parking
Wing C
Lower Ground Floor for Parking & Tanks
Upper Ground Floor for Part Fitness Area and Entrance Lobby
1st Podium Floor for Parking
2nd & 3rd Podium Floor for Parking
Wing D
Lower Ground Floor for Commercial and Entrance Lobby
Upper Ground Floor for Residential and Entrance Lobby
1st Podium Floor for Parking
2nd & 3rd Podium Floor for Parking
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Sale Wing A
Basement Floor for Parking
Ground Floor for Commercial and Entrance Lobby
1st Podium Floor for Commercial and Parking
2nd & 3rd Podium Floor for Commercial and Parking
1st to 15th Floor Refuge Area prrovided alternate Midlanding area from forth Floor
101 to 1501 |  | 2BHK | 645.7324 | 0 | 645.7324 | 0 | 968.5985 |  |  |  |  | 101 to 1501 | 101 | 1501
102 to 1502 |  | 2BHK | 645.7324 | 0 | 645.7324 | 0 | 968.5985 |  |  |  |  | 102 to 1502 | 102 | 1502
103 to 1503 |  | 2BHK | 641.965 | 0 | 641.965 | 0 | 962.9474 |  |  |  |  | 103 to 1503 | 103 | 1503
104 to 1504 |  | 1BHK | 455.2096 | 0 | 455.2096 | 0 | 682.8143 |  |  |  |  | 104 to 1504 | 104 | 1504
105 to 1505 |  | 1BHK | 451.6574 | 0 | 451.6574 | 0 | 677.4862 |  |  |  |  | 105 to 1505 | 105 | 1505
106 to 1506 |  | 1BHK | 437.126 | 0 | 437.126 | 0 | 655.6891 |  |  |  |  | 106 to 1506 | 106 | 1506
16th to 20th Floor Refuge Area provided alternate Midlanding area from forth Floor
1601 to 2001 |  | 2BHK | 645.7324 | 34.4448 | 680.1772 | 0 | 1020.2657 |  |  |  |  | 1601 to 2001 | 1601 | 2001
1602 to 2002 |  | 2BHK | 645.7324 | 34.4448 | 680.1772 | 0 | 1020.2657 |  |  |  |  | 1602 to 2002 | 1602 | 2002
1603 to 2003 |  | 2BHK | 641.965 | 35.1983 | 677.1632 | 0 | 1015.7449 |  |  |  |  | 1603 to 2003 | 1603 | 2003
1604 to 2004 |  | 1BHK | 455.2096 | 35.1983 | 490.4078 | 0 | 735.6118 |  |  |  |  | 1604 to 2004 | 1604 | 2004
1605 to 2005 |  | 1BHK | 451.6574 | 34.4448 | 486.1022 | 0 | 729.1534 |  |  |  |  | 1605 to 2005 | 1605 | 2005
1606 to 2006 |  | 1BHK | 437.126 | 34.4448 | 471.5708 | 0 | 707.3563 |  |  |  |  | 1606 to 2006 | 1606 | 2006
Sale Wing B
Basement Floor for Parking
Ground Floor for Commercial and Entrance Lobby
1st Podium Floor for Commercial and Parking
2nd & 3rd Podium Floor for Commercial and Parking
1st to 15th Floor Refuge Area prrovided alternate Midlanding area from forth Floor
101 to 1501 |  | 1BHK | 435.2962 | 0 | 435.2962 | 0 | 652.9442 |  |  |  |  | 101 to 1501 | 101 | 1501
102 to 1502 |  | 1BHK | 451.6574 | 0 | 451.6574 | 0 | 677.4862 |  |  |  |  | 102 to 1502 | 102 | 1502
103 to 1503 |  | 1BHK | 455.2096 | 0 | 455.2096 | 0 | 682.8143 |  |  |  |  | 103 to 1503 | 103 | 1503
104 to 1504 |  | 2BHK | 641.965 | 0 | 641.965 | 0 | 962.9474 |  |  |  |  | 104 to 1504 | 104 | 1504
105 to 1505 |  | 2BHK | 632.9232 | 0 | 632.9232 | 0 | 949.3848 |  |  |  |  | 105 to 1505 | 105 | 1505
106 to 1506 |  | 2BHK | 645.7324 | 0 | 645.7324 | 0 | 968.5985 |  |  |  |  | 106 to 1506 | 106 | 1506
16th to 20th Floor Refuge Area provided alternate Midlanding area from forth Floor
1601 to 2001 |  | 1BHK | 435.2962 | 34.4448 | 469.741 | 0 | 704.6114 |  |  |  |  | 1601 to 2001 | 1601 | 2001
1602 to 2002 |  | 1BHK | 451.6574 | 34.4448 | 486.1022 | 0 | 729.1534 |  |  |  |  | 1602 to 2002 | 1602 | 2002
1603 to 2003 |  | 1BHK | 455.2096 | 35.1983 | 490.4078 | 0 | 735.6118 |  |  |  |  | 1603 to 2003 | 1603 | 2003
1604 to 2004 |  | 2BHK | 641.965 | 35.1983 | 677.1632 | 0 | 1015.7449 |  |  |  |  | 1604 to 2004 | 1604 | 2004
1605 to 2005 |  | 2BHK | 632.9232 | 34.4448 | 667.368 | 0 | 1001.052 |  |  |  |  | 1605 to 2005 | 1605 | 2005
1606 to 2006 |  | 2BHK | 645.7324 | 34.4448 | 680.1772 | 0 | 1020.2657 |  |  |  |  | 1606 to 2006 | 1606 | 2006
Wing C
Lower Ground Floor for Parking & Tanks
Upper Ground Floor for Part Fitness Area and Entrance Lobby
1st Floor for Residential
101 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
102 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
103 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
104 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
105 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
106 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
107 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
2nd to 24th Floor Refuge Area provided alternate Midlanding area from Seventh Floor
201 to 2401 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 201 to 2401 | 201 | 2401
202 to 2402 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 202 to 2402 | 202 | 2402
203 to 2403 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 203 to 2403 | 203 | 2403
204 to 2404 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 204 to 2404 | 204 | 2404
205 to 2405 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 205 to 2405 | 205 | 2405
206 to 2406 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 206 to 2406 | 206 | 2406
207 to 2407 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 207 to 2407 | 207 | 2407
Wing D
Lower Ground Floor for Commercial and Entrance Lobby
Upper Ground Floor for Residential and Entrance Lobby
1st Floor for Residential
101 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
102 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
103 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
104 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
105 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
106 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
107 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
108 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
109 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
2nd to 24th Floor Refuge Area provided alternate Midlanding area from Seventh Floor
201 to 2401 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 201 to 2401 | 201 | 2401
202 to 2402 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 202 to 2402 | 202 | 2402
203 to 2403 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 203 to 2403 | 203 | 2403
204 to 2404 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 204 to 2404 | 204 | 2404
205 to 2405 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 205 to 2405 | 205 | 2405
206 to 2406 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 206 to 2406 | 206 | 2406
207 to 2407 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 207 to 2407 | 207 | 2407
208 to 2408 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 208 to 2408 | 208 | 2408
209 to 2409 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  |  | 209 to 2409 | 209 | 2409
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
#VALUE! | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 11/12/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Royal Pristo
Google Map :
Formulas:
Kurar = [Kurar, row above]
A
B
C
D
A
C
D
B
C
D
A
B
D
A
B
C
D
Note on H176: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted