## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-16
Name of the builder group |  |  |  | M/s.Suchita Orange Project Royale
Name of the builder company |  |  |  | M/s.Suchita Orange Project Royale
Name of the Project |  |  |  | O and S Royale
Contect Details ( Name & Contect No.) |  |  |  | Kunal Gupta - 9664877660
Name / No of the Building |  |  |  | 01 Building (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, Sale Plans
RERA No. |  |  |  | P51800027371
Project location details |  | O and S Royale, Proposed S.R. Scheme on Plot Bearing CTS No. 150(Pt), 151, 151/1 to 7, 152, 152/1 to 7, 153, 153/6(Pt), 7(Pt), 8 & 9, 154(Pt), 154/11(Pt) & 12, 162(B)/16 to 27 & 351(Pt) of Village Asalfa, Andheri Ghatkopar Link Road ,Dist. Kurla, Ghatkopar(W), Mumbai-400084. Known As "Suchita Co-Op. Housing Society Ltd."
CTS No |  | 150(Pt), 151, 151/1 to 7, 152, 152/1 to 7, 153, 153/6(Pt), 7(Pt), 8 & 9, 154(Pt), 154/11(Pt) & 12, 162(B)/16 to 27 & 351(Pt)
Road |  | Andheri-Ghatkopar Road |  | Locality/Village |  | Asalpha
City |  | Ghatkopar |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400084
Near by Landmark |  | Disha Hospital |  | Distance from city centre: |  | 0.75Km from Asalpha Metro Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Other Plot |  |  | Slum
West | NA | Other Plot |  |  | Disha Hospital
North | NA | 45.70 M W Road |  |  | Andheri-Ghatkopar Road
South | NA | Other Plot |  |  | Slum
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.0939 |  | Longitude |  | 72.8978
Location Link |  | https://maps.app.goo.gl/HFjQFMx3kJtMYMd16
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1272.21
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.0101
Total FSI availaible for the project |  |  |  | 2.1101
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2684.55
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/3133/L/PL-STGL/AP |  |  | Dated | 05/04/2023.
Approved Floor plan No. |  | SRA/ENG/3133/L/PL-STGL/AP |  |  | Dated | 05/04/2023.
Commencement Certificate No. |  | L/PVT & STGOVT/0003/20110729 |  |  | Dated | 02/07/2021.
Valid Up to: This full CC is granted for Rehab wing 'B' of composite bldg from Ground Floor to 8th (Pt) upper floors i.e.upto top of lift machine room & OHWT as per approved plans dtd 23/10/2020 marked as A-B-C-D-E-F-G-H-I-J on plan as at page 1019.
|  | L/PVT & STGOVT/0003/20110729 |  |  | Dated | 21/01/2022.
Valid Up to: This further CC is granted for Sale Wing 'A' of composite bldg from Ground floor to 5th upper floors only for RCC frame work as per approved plan dtd 23/10/2020.
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2684.55
Approved no of units |  |  | Sale Flats - 59, Sale Shops - 06 Rehab Flats - 57 , PAP Flats - 05
Approved no of Floors |  |  | A & B Wing = Gr + 1st to 8th Floor
Proposed no of Floors |  |  | A & B Wing = Gr + 1st to 8th Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | A & B Wing = Gr + 8th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 94.38% |  | 95% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 87.5% |  |  |  |  | Plinth in process | 6
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 8
Construction details: |  | B Wing = Gr + 8th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 50.24% |  | 74.79% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 8 | 88.89% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 5 | 62.5% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 8
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 14000
Recommended rate of the shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 22000
Recommended rate of the Office Per Sq. Ft. (on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 6,00,000/-
Distressed valuation of the Property |  |  |  |  | 11200
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shop |  | 6 | 7603.4765 |  | 11405.2147
Residential Area Details : Sale
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A |  | 47 | 19359.4846 |  | 28071.2526
Wing B |  | 12 | 3607.6622 |  | 5411.4934
Total |  | 59 | 22967.1468 |  | 33482.746 |  |  |  | #VALUE! | 22967.1468
Residential Area Details : PAP
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing B |  | 5 | 1503.1926 |  | 2254.7889
Total |  | 5 | 1503.1926 |  | 2254.7889
Residential Area Details : Rehab
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing B |  | 57 | 17136.3956 |  | 25644.4658
Total |  | 57 | 17136.3956 |  | 25644.4658
Grand Total |  | 127 | 49210.2115 |  | 72787.2153
Details of Flats in Building
Flat/Shop No. | Sale/ Rehab | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
A & B Wing
Basement, Ground, 1st Floor for Commercial & Parking
1 | Sale | Bank Locker (Triplex Basement Floor) | 3069.6904 | 0 | 4604.5357 | Basement + Ground + 1st Floor
2 | Sale | Bank Locker (Triplex Basement Floor) | 2300.4939 | 0 | 3450.7409 | Basement + Ground + 1st Floor
1 | Sale | Nursing home Unit 1 (Duplex to 1st Floor) | 1666.687 | 0 | 2500.0305 | Ground + 1st Floor
1 | Sale | Commercial | 215.491 | 0 | 323.2365 | Ground Floor
2 | Sale | Commercial | 118.883 | 0 | 178.3245 | Ground Floor
3 | Sale | Commercial | 232.2311 | 0 | 348.3467 | Ground Floor
39 | Rehab | Shop | 62.4312 | 0 | 93.6468 | Ground Floor
52 | Rehab | Shop | 93.2162 | 0 | 139.8244 | Ground Floor
53 | Rehab | Shop | 93.2162 | 0 | 139.8244 | Ground Floor
55 | Rehab | Shop | 166.4114 | 0 | 249.6172 | Ground Floor
61 | Rehab | Shop | 21.5172 | 0 | 32.2759 | Ground Floor
Sale Wing A
1st Floor for Residential
1 | Sale | 1RK | 218.9398 | 0 | 317.4627 | 2nd Floor |  | 19.6883 | 1.45
2 | Sale | 1BHK | 415.921 | 0 | 603.0854 |  |  | 36.8703
3 | Sale | 1RK | 305.1594 | 0 | 442.4811
4 | Sale | 1BHK | 463.8208 | 0 | 672.5401
5 | Sale | 1BHK | 405.5875 | 0 | 588.1019
2nd Floor for Residential
1 | Sale | 1BHK | 374.1566 | 0 | 542.5271 | 2nd Floor |  |  | 1.45
2 | Sale | 1BHK | 275.1278 | 0 | 398.9354
3 | Sale | 1BHK | 416.1362 | 0 | 603.3975
4 | Sale | 1BHK | 422.3794 | 0 | 612.4501
5 | Sale | 2BHK | 637.8746 | 0 | 924.9182
6 | Sale | 1BHK | 381.4762 | 0 | 553.1404
3rd to 6th Floor
1 | Sale | 1BHK | 374.1566 | 0 | 542.5271 | 3rd to 6th Floor
2 | Sale | 1BHK | 275.1278 | 0 | 398.9354
3 | Sale | 1BHK | 416.1362 | 0 | 603.3975
4 | Sale | 1BHK | 422.3794 | 0 | 612.4501
5 | Sale | 2BHK | 637.8746 | 0 | 924.9182
6 | Sale | 1BHK | 381.4762 | 0 | 553.1404
7th Floor
1 | Sale | 1BHK | 374.1566 | 0 | 542.5271 | 7th Floor
2 | Sale | 1BHK | 275.1278 | 0 | 398.9354
3 | Sale | 1BHK | 416.1362 | 0 | 603.3975
4 | Sale | 1BHK | 422.3794 | 0 | 612.4501
5 | Sale | 2BHK | 637.8746 | 0 | 924.9182
6 | Sale | 1BHK | 381.4762 | 0 | 553.1404
8th Floor
1 | Sale | 1BHK | 374.1566 | 0 | 542.5271 | 8th Floor
2 | Sale | 1BHK | 275.1278 | 0 | 398.9354
3 | Sale | 1BHK | 416.1362 | 0 | 603.3975
4 | Sale | 1BHK | 422.3794 | 0 | 612.4501
5 | Sale | 2BHK | 637.8746 | 0 | 924.9182
6 | Sale | 1BHK | 381.4762 | 0 | 553.1404
Rehab Wing B
1st Floor for Commercial & Amenities
4 | Welfare Centre |  |  |  |  | 1st Floor for Commercial & Amenities
5 | Balwadi
6 | Yoga Centre
7 | Rehab | 1BHK (Skill Development Room) | 300.6385 | 0 | 435.9259 |  |  | 4
8 | Rehab | 1BHK | 300.6385 | 0 | 435.9259
9 | Rehab | 1BHK | 300.6385 | 0 | 435.9259
10 | Rehab | 1BHK | 300.6385 | 0 | 435.9259
2nd Floor for Residential
1 | Rehab | 1BHK | 300.6385 | 0 | 450.9578 | 2nd Floor
2 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
3 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
4 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
5 | Rehab | 1BHK | 300.6385 | 0 | 450.9578 |  |  | 10
6 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
7 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
8 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
9 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
10 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
3rd to 6th Floor
1 | Rehab | 1BHK | 300.6385 | 0 | 450.9578 | 3rd to 6th Floor
2 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
3 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
4 | Rehab | 1BHK | 300.6385 | 0 | 450.9578 |  |  | 40
5 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
6 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
7 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
8 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
9 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
10 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
7th Floor
1 | PAP | 1BHK | 300.6385 | 0 | 450.9578 | 7th Floor
2 | PAP | 1BHK | 300.6385 | 0 | 450.9578
3 | Sale | 1BHK | 300.6385 | 0 | 450.9578
4 | Sale | 1BHK | 300.6385 | 0 | 450.9578
5 | Rehab | 1BHK | 300.6385 | 0 | 450.9578 |  |  | 5
6 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
7 | Rehab | 1BHK | 300.6385 | 0 | 450.9578
8 | PAP | 1BHK | 300.6385 | 0 | 450.9578
9 | PAP | 1BHK | 300.6385 | 0 | 450.9578
10 | PAP | 1BHK | 300.6385 | 0 | 450.9578
8th Floor
1 | Sale | 1BHK | 300.6385 | 0 | 450.9578 | 8th Floor
2 | Sale | 1BHK | 300.6385 | 0 | 450.9578
3 | Sale | 1BHK | 300.6385 | 0 | 450.9578
4 | Sale | 1BHK | 300.6385 | 0 | 450.9578
5 | Sale | 1BHK | 300.6385 | 0 | 450.9578
6 | Sale | 1BHK | 300.6385 | 0 | 450.9578
7 | Sale | 1BHK | 300.6385 | 0 | 450.9578
8 | Sale | 1BHK | 300.6385 | 0 | 450.9578
9 | Sale | 1BHK | 300.6385 | 0 | 450.9578
10 | Sale | 1BHK | 300.6385 | 0 | 450.9578
Remarks:
1. Finishing Work is in process. Internal photographs was not allowed. (Slow Speed) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated latest CC from Rera (dtd.22/04/2024). 8. We have updated Approved Pland & C.C (on 06/06/2024). 9. Please provide revised CC for Wing A. 7. On Site, we meet Mr.Farukh - 9820665033.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sagar Naresh katale |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | O and S Royale
Layout :
Google Map :
…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………..
Wing A
Wing B

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted