## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 10/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-06
Name of the builder group |  |  |  |  | M/s.Peer Realty Private Limited
Name of the builder company |  |  |  |  | M/s.Peer Realty Private Limited
Name of the Project |  |  |  |  | Opulus
Contect Details ( Name & Contect No.) |  |  |  |  | 2226590078
Name / No of the Building |  |  |  |  | Building No. R1, R2 & R3 Building No. S1 & S2
Docouments Provided |  |  |  |  | Approved Plans, CC, Cost sheet.
RERA No. |  |  |  |  | P51700022773
Project location details |  | Opulus, Survey No/H No.56/5A2 & 56/6B, North Ave Road, Chitalsar-Manpada, Thane.
Survey No/H No |  | 56/5A2 & 56/6B
Road |  | North Ave Road |  |  | Village |  | Chitalsar-Manpada
City |  | Thane |  |  | District |  | Thane
Taluka |  | Thane |  |  | Pin Code |  | 400610
Near by Landmark |  | Gemini A&B CHS Hiranandani Meadows |  |  | Distance from city centre: |  | 5.3 Km from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Hiranandani Meadows |  | Meridian CHS Ltd. |  | Open Land |  | Celio Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.229590,72.972672
Location Link |  | https://goo.gl/maps/bFs544to6q7iR9U88
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 19599
Permissible FSI |  |  |  |  | 2.5
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 2.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 48997.5
Total number of Buildings |  |  |  |  | 05 Buildings
Approval Detail : Plan approval
Layout Approval No |  | VP.S04/0103/17/TMC/TD-DP/TPS/3081/19 |  |  |  | Dated | 23/05/2019.
Approved Floor plan No. |  | VP.S04/0103/17/TMC/TD-DP/TPS/3081/19 |  |  |  | Dated | 23/05/2019.
Commencement Certificate No. Valid Up to: |  | 90/403(Old)S04/0103/17/TMCB/TDD/ 0070/(P/C)/2024/AutoDCR |  |  |  | Dated | 12/01/2024.
Building No. R1 - Gr/Stilt + 1st to 2nd Floor Podium + 3rd to 10th Floor Building No. R2 - Gr/Stilt + 1st to 2nd Floor Podium + 3rd to 22nd + 23rd(Pt) to 28th(Pt) Floor Building No. R3 - Gr/Stilt + 1st to 2nd Floor Podium + 3rd to 19th Floor Building No. S1 - Gr/Stilt + 1st to 2nd Podium + 3rd to 24th Floor Building No. S2 - Gr/Stilt + 1st to 2nd Podium + 3rd to 12th Floor
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 12/01/2024. |  | Expected Completion |  | 2028-09-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 48997.5 |  | Approved no of units |  | Flats = 793
Approved no of Floors |  | Building No. R1 & R3 = Gr. + 1st to 2nd Floors Podium + 3rd to 28th Floors Building No. R2 - Gr. + 1st to 2nd Floors Podium + 3rd to 29th Floors Building No. S1 - Gr. + 1st to 2nd Floors Podium + 3rd to 28th Floors Building No. S2 - Gr. + 1st to 2nd Floors Podium + 3rd to 27th Floors
Quality of construction: NA |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Steel, Sand, Cement etc.
Construction details:
Construction details: |  | Building No. R1 = Gr. + 1st to 2nd Floor Podium + 3rd to 28th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 28
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 14
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 28
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 28
Construction details: |  | Building No. R2 = Gr. + 1st to 2nd Floor Podium + 3rd to 29th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 29
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% |  | 16.67% |  | 50% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% | [5 empty] | Excavation Completed | 29
RCC (Including podiums) |  | 5 | 16.67% | [5 empty] | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 29
Construction details: |  | Building No.R3 = Gr. + 1st to 2nd Floor Podium + 3rd to 28th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% |  | 14.14% |  | 48.1% |  | Excavation in process | 14
Plinth |  | 28 | 100% | [5 empty] | Excavation Completed | 28
RCC (Including podiums) |  | 3 | 10.34% | [5 empty] | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 28
Construction details: |  | Building No. S1 = Gr. + 1st to 2nd Floor Podium + 3rd to 28th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% |  | 14.14% |  | 48.1% |  | Excavation in process | 14
Plinth |  | 28 | 100% | [5 empty] | Excavation Completed | 28
RCC (Including podiums) |  | 3 | 10.34% | [5 empty] | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 28
Construction details: |  | Building No. S2 = Gr. + 1st to 2nd Floor Podium + 3rd to 28th Floor | [6 empty] | Excavation work in process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 28
Stage of construction: |  | Excavation work in process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 14 | 50% |  | 0% |  | 10% |  | Excavation in process | 14
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 28
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 21
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 28
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 16000 |  |  | 13500 TO 16000 | Viraj | 2024-04-06 | Cost sheet
Recommended rate of Parking | [5 empty] | 800000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 12800
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
R1 |  | 114 | 93155.9821 |  |  | 139733.9731
R2 |  | 162 | 109340.9042 |  |  | 164011.3563
R3 |  | 145 | 91948.3054 |  |  | 137922.4581
S1 |  | 188 | 132812.8357 |  |  | 199219.2536
S2 |  | 184 | 129714.2687 |  |  | 194571.403
Total |  | 793 | 556972.296 |  |  | 835458.444
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No. R1
Ground Floor is for Parking
1st Podium Floor is for Parking
2nd Podium (E-DECK) Floor (Fitness Centre)
3rd to 6th & 8th to 10th Floors
1 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N | 3rd to 6th & 8th to 10th Floors
2 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N
3 |  | 2 BHK | 715.0235 |  | 0 | 1072.5352 | N
4 |  | 2 BHK | 715.1419 |  | 0 | 1072.7128 | N
5 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N
6 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N
7th Floor
1 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N | 7th Floor
2 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N
3 |  | Refuge Area |  |  |  |  | N
4 |  | 2 BHK | 715.1419 |  | 0 | 1072.7128 | N
5 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N
6 |  | 2 BHK | 763.9749 |  | 0 | 1145.9624 | N
23rd Floor (Fire Check)
11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
1 |  | 5 BHK | 1175.9778 |  | 0 | 1763.9666 | N | 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
4 |  | 2 BHK | 715.1419 |  | 0 | 1072.7128 | N
5 |  | 2 BHK | 715.1419 |  | 0 | 1072.7128 | N
12th, 17th, 22nd & 28th Floors (Part Refuge Area)
1 |  | 5 BHK | 1175.9778 |  | 0 | 1763.9666 | N | 12th, 17th, 22nd & 28th Floors
3 |  | 2 BHK | 715.1419 |  | 0 | 1072.7128 | N
4 |  | 2 BHK | 715.1419 |  | 0 | 1072.7128 | N
5 |  | 5 BHK | 1175.9778 |  | 0 | 1763.9666 | N
Building No. R2
Ground Floor is for Parking
1st Podium Floor is for Parking
2nd Podium (E-DECK) Floor (Fitness Centre)
3rd to 6th, 8th to 11th, 13th & 14th Floors
1 |  | 2 BHK | 601.8421 |  | 0 | 902.7632 | N | 3rd to 6th, 8th to 11th, 13th & 14th Floors
2 |  | 2 BHK | 601.8421 |  | 0 | 902.7632 | N
3 |  | 2 BHK | 604.1865 |  | 0 | 906.2798 | N
4 |  | 2 BHK | 604.1865 |  | 0 | 906.2798 | N
5 |  | 2 BHK | 765.6164 |  | 0 | 1148.4246 | N
6 |  | 2 BHK | 597.6173 |  | 0 | 896.4259 | N
7 |  | 2 BHK | 606.5299 |  | 0 | 909.7948 | N
7th & 12th Floors
1 |  | Refuge Area |  |  |  |  | N | 7th & 12th Floors
2 | [6 empty] | N
3 |  | 2 BHK | 604.1865 |  | 0 | 906.2798 | N
4 |  | 2 BHK | 765.6164 |  | 0 | 1148.4246 | N
5 |  | 2 BHK | 597.6173 |  | 0 | 896.4259 | N
6 |  | 2 BHK | 606.5299 |  | 0 | 909.7948 | N
7 |  | 2 BHK | 605.2005 |  | 0 | 907.8008 | N
15th, 16th, 18th to 21st, 24th & 25th Floor
1 |  | 2 BHK | 609.2639 |  | 0 | 913.8959 | N | 15th, 16th, 18th to 21st, 24th & 25th Floor
2 |  | 2 BHK | 609.2639 |  | 0 | 913.8959 | N
3 |  | 5 BHK | 1178.2608 |  | 0 | 1767.3912 | N
5 |  | 2 BHK | 683.133 |  | 0 | 1024.6994 | N
6 |  | 2 BHK | 609.6676 |  | 0 | 914.5014 | N
7 |  | 2 BHK | 604.6085 |  | 0 | 906.9127 | N
17th & 22nd Floors
1 |  | Refuge Area |  |  |  |  | N | 17th & 22nd Floors
2 | [6 empty] | N
3 |  | 5 BHK | 1178.2608 |  | 0 | 1767.3912 | N
5 |  | 2 BHK | 683.133 |  | 0 | 1024.6994 | N
6 |  | 2 BHK | 609.6676 |  | 0 | 914.5014 | N
7 |  | 2 BHK | 604.6085 |  | 0 | 906.9127 | N
23rd Floor (Fire Check)
26th & 27th Floors (Part Terrace Area on 26th Floor)
1 |  | 2 BHK | 609.2639 |  | 0 | 913.8959 | N | 26th & 27th Floors
2 |  | 2 BHK | 609.2639 |  | 0 | 913.8959 | N
3 |  | 5 BHK | 1178.2608 |  | 0 | 1767.3912 | N
6 |  | 2 BHK | 683.133 |  | 0 | 1024.6994 | N
28th Floor (Part Refuge Area)
3 |  | 2 BHK | 1174.3419 |  | 0 | 1761.5129 | N | 28th Floor
5 |  | 2 BHK | 693.6515 |  | 0 | 1040.4773 | N
29th Floor (Part Terrace Area)
3 |  | 2 BHK | 1174.3419 |  | 0 | 1761.5129 | N | 29th Floor
5 |  | 2 BHK | 693.6515 |  | 0 | 1040.4773 | N
Building No. R3
Ground Floor is for Parking
1st Podium Floor is for Parking
2nd Podium (E-DECK) Floor (Fitness Centre)
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
1 |  | 2 BHK | 560.531 |  | 0 | 840.7965 | N | 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
2 |  | 2 BHK | 560.531 |  | 0 | 840.7965 | N
3 |  | 2 BHK | 706.7406 |  | 0 | 1060.1108 | N
4 |  | 2 BHK | 706.7406 |  | 0 | 1060.1108 | N
5 |  | 2 BHK | 642.3686 |  | 0 | 963.5529 | N
6 |  | 2 BHK | 642.3686 |  | 0 | 963.5529 | N
23rd Floor (Fire Check)
7th, 12th, 17th, 22nd & 28th Floors
1 |  | 2 BHK | 560.531 |  | 0 | 840.7965 | N | 7th, 12th, 17th, 22nd & 28th Floors
2 |  | 2 BHK | 560.531 |  | 0 | 840.7965 | N
3 |  | 2 BHK | 706.7406 |  | 0 | 1060.1108 | N
4 |  | Refuge Area |  |  |  |  | N
5 |  | 2 BHK | 642.3686 |  | 0 | 963.5529 | N
6 |  | 2 BHK | 642.3686 |  | 0 | 963.5529 | N
Building No. S1
Ground Floor is for Parking
1st Podium Floor is for Parking
2nd Podium (E-DECK) Floor (Fitness Centre)
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
1 |  | 3 BHK | 845.4046 |  | 0 | 1268.1068 | N | 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
2 |  | 2 BHK | 700.0055 |  | 0 | 1050.0083 | N
3 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
4 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
5 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
6 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
7 |  | 2 BHK | 684.7476 |  | 0 | 1027.1213 | N
8 |  | 3 BHK | 868.4094 |  | 0 | 1302.6141 | N
7th, 12th, 17th & 22nd Floors
1 |  | 3 BHK | 845.4046 |  | 0 | 1268.1068 | N | 7th, 12th, 17th & 22nd Floors
2 |  | 2 BHK | 700.0055 |  | 0 | 1050.0083 | N
3 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
4 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
5 |  | Refuge Area |  |  |  |  | N
6 | [6 empty] | N
7 |  | 2 BHK | 684.7476 |  | 0 | 1027.1213 | N
8 |  | 3 BHK | 868.4094 |  | 0 | 1302.6141 | N
23rd Floor (Fire Check)
28th Floor
1 |  | 3 BHK | 845.4046 |  | 0 | 1268.1068 | N | 28th Floor
2 |  | 2 BHK | 700.0055 |  | 0 | 1050.0083 | N
3 |  | Terrace Area |  |  |  |  | N
4 | [6 empty] | N
5 | [6 empty] | N
6 | [6 empty] | N
7 |  | 2 BHK | 684.7476 |  | 0 | 1027.1213 | N
8 |  | 3 BHK | 868.4094 |  | 0 | 1302.6141 | N
Building No. S2
Ground Floor is for Parking
1st Podium Floor is for Parking
2nd Podium (E-DECK) Floor (Fitness Centre)
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
1 |  | 3 BHK | 845.4046 |  | 0 | 1268.1068 | N | 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 24th to 27th Floors
2 |  | 2 BHK | 700.0055 |  | 0 | 1050.0083 | N
3 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
4 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
5 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
6 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
7 |  | 2 BHK | 684.7476 |  | 0 | 1027.1213 | N
8 |  | 3 BHK | 868.4094 |  | 0 | 1302.6141 | N
23rd Floor (Fire Check)
7th, 12th, 17th & 22nd Floors
1 |  | 3 BHK | 845.4046 |  | 0 | 1268.1068 | N | 7th, 12th, 17th & 22nd Floors
2 |  | 2 BHK | 700.0055 |  | 0 | 1050.0083 | N
3 |  | Refuge Area |  |  |  |  | N
4 | [6 empty] | N
5 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
6 |  | 2 BHK | 628.962 |  | 0 | 943.4431 | N
7 |  | 2 BHK | 684.7476 |  | 0 | 1027.1213 | N
8 |  | 3 BHK | 868.4094 |  | 0 | 1302.6141 | N
Remarks:
1. Building No. R1 = Work not yet started. Building No. R2, R3 = Construction work is the same as last visit (dtd.04/06/2025). (Slow Speed) Building No. S1 = Construction work is the same as last visit (dtd.08/03/2025). (Slow Speed) Building No. S2 = Construction work is the same as last visit (dtd.10/12/2024). (Slow Speed) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + A.P Area. 5. We have given rate as per Market Inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated CC from RERA site on 17/03/2025. 8. Please provide revised approved plans. 8. On site, we meet Mr.Zaid - 7058035869. | [8 empty] | r2 work resumed
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report Prepared By : |  |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Opulus
Google Map :
S1
S1
S1
S1
S2
R3
R2
S1
R3
R2
S2
S1
R2
R3

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 28
Particulars | total floor | 28
plinth | 10 | 0 | 0%
slab | 29 | 0 | 0% |  | Parking |  | Rate
Bricks | 28 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 28 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 28 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 28 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 28 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 0 | 20 |  | Progress |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 0% | 20% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## S1%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 28
Particulars | total floor | 28
plinth | 10 | 1 | 10%
slab | 29 | 0 | 0% |  | Parking |  | Rate
Bricks | 28 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 28 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 28 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 28 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 28 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 1 | 21 |  | Progress |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 21 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 1% | 21% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-12-14 | Pratiksha

## Valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Housing |  |  |  |  | #DIV/0!
Proptiger |  |  |  |  | #DIV/0!
Magic Brick |  |  |  |  | #DIV/0!
Magic Brick |  |  |  |  | #DIV/0!
Magic Brick |  |  |  |  | #DIV/0!
99 Acres |  |  |  |  | #DIV/0!
99 Acres |  |  |  |  | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted |  |  |  |  | 32000

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.9 | 3.75 | 10.875 | CB | 1.8 | 0.75 | 1.35 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  | 2.9 | 0.75 | 2.175 |  |  |  | 0 |  |  | 0
| kitch | 2.45 | 2.15 | 5.2675 | CB | 2.15 | 0.6 | 1.29 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.43 | 3.05 | 7.4115 | CB | 3.05 | 0.6 | 1.83 |  |  | 0
|  | 3.15 | 0.75 | 2.3625 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.28 | 3.05 | 6.954 | CB | 3.05 | 6 | 18.3 |  |  | 0
|  | 2.88 | 0.75 | 2.16 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.15 | 1.35 | 2.9025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.15 | 1.3 | 2.795 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.12 | 0.6 | 0.672 |  |  |  | 0 |  |  | 0
| passage2 | 1 | 2.88 | 2.88 |  |  |  | 0 |  |  | 0
| passage3 | 0.7 | 2.5 | 1.75 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 518.8786 | 48.205 |  |  | 245.0963 | 22.77 |  | 0 | 0
|  |  | 763.9749 | 70.975

## Sheet1
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.05 | 3.49 | 10.6445 | CB | 2.4 | 0.6 | 1.44 |  |  | 0
|  | 2.45 | 2.4 | 5.88 | FB |  |  | 0 |  |  | 0
|  | 3.05 | 0.75 | 2.2875 |  |  |  | 0 |  |  | 0
| kitch | 2.45 | 2.15 | 5.2675 | CB | 2.15 | 0.6 | 1.29 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.9 | 3.43 | 9.947 | CB |  |  | 0 |  |  | 0
|  | 3.43 | 0.75 | 2.5725 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.41 | 2.4 | 5.784 | CB | 2.4 | 0.6 | 1.44 |  |  | 0
|  | 3.01 | 0.75 | 2.2575 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.35 | 2.15 | 2.9025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.15 | 1.3 | 2.795 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.9 | 2.16 | 6.264 |  |  |  | 0 |  |  | 0
| passage2 | 1 | 1.5 | 1.5 |  |  |  | 0 |  |  | 0
| passage3 | 1.71 | 2.43 | 4.1553 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 670.1376 | 62.2573 |  |  | 44.8859 | 4.17 |  | 0 | 0
|  |  | 715.0235 | 66.4273

## Sheet2
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.9 | 3.75 | 10.875 | CB | 1.8 | 0.6 | 1.08 |  |  | 0
|  | 2.9 | 0.75 | 2.175 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.45 | 2.15 | 5.2675 | CB | 2.15 | 0.6 | 1.29 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.45 | 3.05 | 7.4725 | CB | 3.05 | 0.6 | 1.83 |  |  | 0
|  | 2.45 | 0.75 | 1.8375 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.28 | 3.05 | 6.954 | CB | 3.05 | 0.6 | 1.83 |  |  | 0
|  | 2.88 | 0.75 | 2.16 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.28 | 3.05 | 6.954 | CB | 3.05 | 0.6 | 1.83 |  |  | 0
|  | 2.88 | 3.05 | 8.784 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.43 | 3.05 | 7.4115 | CB | 3.05 | 0.6 | 1.83 |  |  | 0
|  | 3.03 | 0.75 | 2.2725 | FB |  |  | 0 |  |  | 0
| toilet1 | 2.15 | 1.35 | 2.9025 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.15 | 1.35 | 2.9025 | DB |  |  | 0 |  |  | 0
| toilet3 | 2.15 | 1.3 | 2.795 | DB |  |  | 0 |  |  | 0
|  | 2.15 | 1.35 | 2.9025 |  |  |  | 0 |  |  | 0
| passage1 | 1.5 | 1.2 | 1.8 |  |  |  | 0 |  |  | 0
| passage2 | 2.9 | 3.75 | 10.875 |  |  |  | 0 |  |  | 0
| passage3 | 2.9 | 0.75 | 2.175 |  |  |  | 0 |  |  | 0
| passage4 | 2.9 | 0.6 | 1.74 |  |  |  | 0 |  |  | 0
|  | 2.65 | 0.7 | 1.855 |  |  |  | 0 |  |  | 0
|  | 1 | 2.15 | 2.15 |  |  |  | 0 |  |  | 0
|  | 1 | 2.15 | 2.15 |  | 1 | 3.15 | 3.15 |  |  | 0
| Total |  | 1037.768 | 96.411 |  |  | 138.2098 | 12.84 |  | 0 | 0
|  |  | 1175.9778 | 109.251