## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 13/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/s.Poddar Housing And Development Limited
Name of the builder company |  |  |  |  | M/s.Poddar Housing And Development Limited
Name of the Project |  |  |  |  | Poddar Riviera Phase - I
Contact Details ( Name & Contact No.) |  |  |  |  | Mr.Vinod Thakkar 8657561720
Site Person - Contact Details ( Name & Contact No). |  |  |  |  | NA | [5 empty] | Mr. Surendra 7718922212
Name / No of the Building |  |  |  |  | Building No.1 (Wing A1, A2, A3 & A4)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P51700023508
Project location details |  | Poddar Riviera Phase - I, Survey No.S.No.9 H.No.1B, 2, 3 & S. No.10, 11 H.No.1, 2, Bhiwandi - Murbad Road, Mharal, Shahad, Kalyan, Thane.
Survey No |  | S.No.9 H.No.1B, 2, 3 & S. No.10, 11 H.No.1, 2
Road |  | Bhiwandi - Murbad Road |  |  | Locality/Village |  | Mharal
City |  | Shahad |  |  | District |  | Thane
Taluka |  | Kalyan |  |  | Pin Code |  | 421103
Near by Landmark |  | Poddar Big leap |  |  | Distance from city centre: |  | About 2.9Km from Shahad Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.2502 |  | Longitude |  | 73.1783
Location Link |  | https://goo.gl/maps/mgdWyLntZQ5itkXh8
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 54903.9
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 1.3285
Total FSI availaible for the project |  |  |  |  | 2.3285
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 127845.98
Total number of Buildings |  |  |  |  | 04 Buildings
Approval Detail : Plan approval
Layout Approval No |  | EE/BP/PMAY/A/MHADA/40/2020 |  |  |  | Dated | 13/02/2020.
Approved Floor plan No. |  | EE/BP/PMAY/A/MHADA/40/2020 |  |  |  | Dated | 13/02/2020.
Commencement Certificate No. |  | E.E/BP/PMAY/A/MHADA/41/2020 |  |  |  | Dated | 13/02/2020.
Valid Up to: Building No.1 (Wing A1, A2, A3 & A4) = Plinth Level Only
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 13/02/2020. |  | Expected Completion |  | As per RERA-30/09/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 33744.28 |  | Approved no of units |  | Flats = 672
Approved no of Floors |  | Building No.1 (Wing A1, A2, A3 & A4) = B + G + 1st To 23rd Floor
Quality of construction: NA |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Nothing
Construction details: |  | Building No.1 (Wing A1) = B + G + 1st To 23rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 23 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 5.75 | Extra Construction % given already
Excavation |  | 23 | 100% |  | 11.67% |  | 46.25% |  | Excavation in process |  | 11.5
Plinth |  | 23 | 100% | [5 empty] | Excavation Completed |  | 23
RCC (Including podiums) |  | 1 | 4.167% | [5 empty] | Footing in Process |  | 4.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 9.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 13.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 18.4
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 23
Construction details: |  | Building No.1 (Wing A2) = B + G + 1st To 23rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 23 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 5.75
Excavation |  | 23 | 100% |  | 11.67% |  | 46.25% |  | Excavation in process |  | 11.5
Plinth |  | 23 | 100% | [5 empty] | Excavation Completed |  | 23
RCC (Including podiums) |  | 1 | 4.167% | [5 empty] | Footing in Process |  | 4.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 9.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 13.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 18.4
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 23
Construction details: |  | Building No.1 (Wing A3) = B + G + 1st To 23rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 23 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 5.75
Excavation |  | 23 | 100% |  | 15% |  | 48.75% |  | Excavation in process |  | 11.5
Plinth |  | 23 | 100% | [5 empty] | Excavation Completed |  | 23
RCC (Including podiums) |  | 3 | 12.5% | [5 empty] | Footing in Process |  | 4.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 9.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 13.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 18.4
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 23
Construction details: |  | Building No.1 (Wing A4) = B + G + 1st To 23rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 23 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 5.75
Excavation |  | 23 | 100% |  | 16.67% |  | 50% |  | Excavation in process |  | 11.5
Plinth |  | 23 | 100% | [5 empty] | Excavation Completed |  | 23
RCC (Including podiums) |  | 4 | 16.67% | [5 empty] | Footing in Process |  | 4.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed |  | 9.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 13.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 18.4
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 23
Wheather the construction is as per approved Building plan : NA
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 6300
Floor Rise Rate Per Sq. Ft. from 2nd Floor | [5 empty] | 13/-
Club House Charges | [5 empty] | 4,50,000/-
Recommended rate of Parking | [5 empty] | 300000/-
Distressed valuation of the Property | [5 empty] | 5040
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
A1 Wing |  | 169 | 69925.4197 |  |  | 104888.1296
A2 Wing |  | 169 | 69925.4197 |  |  | 104888.1296
A3 Wing |  | 169 | 69925.4197 |  |  | 104888.1296
A4 Wing |  | 213 | 86683.5684 |  |  | 130025.3526
Total |  | 720 | 296459.8276 |  |  | 444689.7413
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1
A1 Wing
Ground Floor is For Parking
1st Podium Floor for Parking & Residential
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 1st Podium Floor for Parking & Residential |  | 1.5
6 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
7 |  | Double Height
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N |  |  | 1.5
2nd Podium Floor for Parking & Residential
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 2nd Podium Floor for Parking & Residential |  | 1.5
6 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
7 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N
3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
1 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N | 3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 6293.5361
6 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
7 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N |  |  | 6323.4426
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N |  |  | 6618.0378
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | Refuge Area
7 |  | Refuge Area
8 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N
18th Floor (Part Refuge Area)
1 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N | 18th Floor (Part Refuge Area)
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 8373.8438
6 |  | Refuge Area
7 |  | Refuge Area
8 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N
A2 Wing
Ground Floor is For Parking
1st Podium Floor for Parking & Residential
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 1st Podium Floor for Parking & Residential |  | 1.5
6 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
7 |  | Double Height
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N |  |  | 1.5
2nd Podium Floor for Parking & Residential
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 2nd Podium Floor for Parking & Residential |  | 1.5
6 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
7 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N
3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
1 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N | 3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
7 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N |  |  | 8264.4612
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | Refuge Area
7 |  | Refuge Area
8 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N
18th Floor (Part Refuge Area)
1 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N | 18th Floor (Part Refuge Area)
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 8373.8438
6 |  | Refuge Area
7 |  | Refuge Area
8 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N
A3 Wing
Ground Floor is For Parking
1st Podium Floor for Parking & Residential
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 1st Podium Floor for Parking & Residential |  | 1.5
6 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
7 |  | Double Height
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N |  |  | 1.5
2nd Podium Floor for Parking & Residential
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 2nd Podium Floor for Parking & Residential |  | 1.5
6 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
7 |  | 1BHK | 375.1254 |  | 0 | 562.6881 | N |  |  | 1.5
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N
3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
1 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N | 3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
7 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
8 |  | 2BHK | 533.8944 |  | 0 | 800.8416 | N |  |  | 8264.4612
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N | 8th & 13th Floor
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | Refuge Area
7 |  | Refuge Area
8 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N
18th Floor (Part Refuge Area)
1 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N | 18th Floor
2 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
3 |  | 1BHK | 342.8334 |  | 0 | 514.2501 | N
4 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 8373.8438
6 |  | Refuge Area
7 |  | Refuge Area
8 |  | 2BHK | 534.2173 |  | 0 | 801.326 | N
A4 Wing
Ground Floor is For Parking
1st Podium Floor for Parking & Residential
6 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 1st Podium Floor for Parking & Residential |  | 1.5
7 |  | 1BHK | 339.066 |  | 0 | 508.599 | N |  |  | 1.5
8 |  | Double height
9 |  | 1BHK | 339.066 |  | 0 | 508.599 | N |  |  | 1.5
10 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 1.5
2nd Podium Floor for Parking & Residential
6 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 2nd Podium Floor for Parking & Residential |  | 1.5
7 |  | 1BHK | 339.066 |  | 0 | 508.599 | N |  |  | 1.5
8 |  | 2BHK | 518.2866 |  | 0 | 777.4299 | N |  |  | 1.5
9 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
10 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
1 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 3rd To 7th, 9th To 12th, 14th To 17th & 19th To 23rd Floor
2 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
3 |  | 2BHK | 518.2866 |  | 0 | 777.4299 | N
4 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
7 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
8 |  | 2BHK | 518.2866 |  | 0 | 777.4299 | N |  |  | 6714.8747
9 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
10 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 5466.7308
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
3 |  | 2BHK | 518.2866 |  | 0 | 777.4299 | N
4 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
7 |  | Refuge Area
8 |  | Refuge Area
9 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
10 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 6714.8747
18th Floor (Part Refuge Area)
1 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N | 18th Floor (Part Refuge Area)
2 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
3 |  | 2BHK | 518.2866 |  | 0 | 777.4299 | N
4 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
5 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
6 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N
7 |  | Refuge Area
8 |  | Refuge Area
9 |  | 1BHK | 339.066 |  | 0 | 508.599 | N
10 |  | 2BHK | 421.9488 |  | 0 | 632.9232 | N |  |  | 6714.8747
Remarks:
1. Construction work was stopped at the time of visit. Work is same as last visit (08/12/2023). 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Car parking is subjected to authentic documentation. 8. We have updated revised approved floor plan & C.C (on 25/06/2021). 9. Please provide revised approved CC, As the construction work goes beyond the CC permission. 10. As checked on RERA portal on date 13/09/2025, we have observed that above project " Poddar Riveria Phase - I" is kept under abeyance. Please check from your end. 10. Project recieved first CC on 13/02/2020 but construction work is not completed yet.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Bapardekar |  | Report Prepared By : |  |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Poddar Riviera Phase - I
Google Map :
A3
A1
A2
A4

## A1%
Basement | Podium | Ground | Upper Floor
1 | 0 | 1 | 23
Particulars | total floor | 23
plinth | 10 | 3 | 30%
slab | 25 | 0 | 0% |  | Parking |  | Rate
Bricks | 23 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 23 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 23 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 23 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 23 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 3 | 23 |  | Progress |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 23 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 3% | 23% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## A2,A3%
Basement | Podium | Ground | Upper Floor
1 | 0 | 1 | 23
Particulars | total floor | 23
plinth | 10 | 6 | 60%
slab | 25 | 0 | 0% |  | Parking |  | Rate
Bricks | 23 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 23 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 23 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 23 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 23 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 6 | 26 |  | Progress |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 26 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 6% | 26% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## A3%
Basement | Podium | Ground | Upper Floor
1 | 0 | 1 | 23
Particulars | total floor | 23
plinth | 10 | 3 | 30%
slab | 25 | 0 | 0% |  | Parking |  | Rate
Bricks | 23 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 23 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 23 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 23 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 23 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 3 | 23 |  | Progress |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 23 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 3% | 23% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## A4%
Basement | Podium | Ground | Upper Floor
1 | 0 | 1 | 23
Particulars | total floor | 23
plinth | 10 | 7 | 70%
slab | 25 | 0 | 0% |  | Parking |  | Rate
Bricks | 23 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 23 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 23 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 23 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 23 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 7 | 27 |  | Progress |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 7% | 27% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.21 | 8.8275 | CB | 1.175 | 3.05 | 3.5838 |  |  | 0
|  |  |  | 0 | FB | 2.75 | 1.79 | 4.9225 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.665 | 2.43 | 4.046 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.125 | 2.73 | 5.8012 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.75 | 3.05 | 8.3875 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.275 | 2.05 | 2.6138 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.315 | 2.05 | 2.6957 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.8 | 0.9 | 2.52 |  |  |  | 0 |  |  | 0
| passage2 | 1.5 | 2.75 | 4.125 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 419.9758 | 39.0167 |  |  | 91.5613 | 8.5062 |  | 0 | 0
|  |  | 511.537 | 47.523

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Poddar Riviera | 1BHK | 375 | 675 | 4814.8148 | 3250000
housing | Poddar Riviera | 1.5BHK | 475 | 855 | 4970.7602 | 4250000
housing | Poddar Riviera | 2BHK | 568 | 1022.4 | 5183.8811 | 5300000
Average |  |  |  |  | 4989.8187
Valuation Adopted |  |  |  |  | 5000