## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-13
Name of the builder group |  |  |  |  | M/s.Alexander And Pal Garden Phase II
Name of the builder company |  |  |  |  | M/s.Alexander And Pal Garden Phase II
Name of the Project |  |  |  |  | Pal Garden Phase II
Contect Details ( Name & Contect No.) |  |  |  |  | 9960940306
Site Meet Contect Details ( Name & Contect No.) |  |  |  |  | NA |  |  |  |  | Mr. R.K. Mishra : 7249509059.
Name / No of the Building |  |  |  |  | Wing (D, E, F, G & H)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000015378
Project location details |  | Pal Garden Phase II, Survey No.17, Hissa No.1/C/1, 2, 3, Internal Road, Karjat, Raigad.
Survey No |  | 17 |  |  | Hissa No |  | 1/C/1, 2, 3
Road |  | Internal Road |  |  | Locality/Village |  | Karjat
City |  | Karjat |  |  | District |  | Raigad
Taluka |  | Karjat |  |  | Pin Code |  | 410201
Near by Landmark |  | Mateshwari Hills Park |  |  | Distance from city centre: |  | About 1.1Km from Karjat Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Road |  | Open Plot |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 18.9062 |  | Longitude |  | 73.3161
Location Link |  | https://maps.app.goo.gl/1rDwh6TNo7h8KsLN7
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 4920
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.20447
Total FSI availaible for the project |  |  |  |  | 1.2045
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5926
Total number of Buildings |  |  |  |  | 04 Buildings
Approval Detail : Plan approval
Layout Approval No |  | S.R-40/16-17 |  |  |  | Dated | 04/02/2017.
Approved Floor plan No. Wing E, F, G, & H |  | S.R-40/16-17 |  |  |  | Dated | 04/02/2017.
Approved Floor plan No. Wing D |  | S.R-27/12-13 |  |  |  | Dated | 21/02/2013.
Commencement Certificate No. |  | JK/90/16-17/KT-1/SR.40/16-17 Valid Up to: Wing E, F, G, & H = G + 4th Floor |  |  |  | Dated | 04/02/2017.
O. Certificate No.: Approved upto : |  | 1751/16-17 D Wing = Gr. + 1st to 3rd Floor |  |  | Date of approval: | Dated | 10/10/2016. | NA
Commencement date of construction |  |  | 04/02/2017. |  | Expected Completion |  | 31/12/2025.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5926 |  | Approved no of units |  | Flats = 96 & shop = 39
Approved no of Floors |  | Wing D = G + 3rd Floor Wing E, F, G & H = G + 4th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Wing D = G + 1st to 3rd Floor | [6 empty] | Excavation work Completed. 0, RCC upto 1 Slab, Internal Plaster upto Slab/Floor Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 5 Floor, Finishing upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Construction details: |  | Wing E & F = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Construction details: |  | Wing G & H = G + 1st to 4th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 91.25% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Wing H = G + 1st to 4th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 91.25% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000/-
Legal charges & Other | [5 empty] | 12000/-
Development Charges & Meter Society | [5 empty] | 75000/-
Recommended rate of Parking | [5 empty] | 100000/-
Distressed valuation of the Property | [5 empty] | 2800
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
E Wing |  | 9 | 914.1865 |  |  | 1306
F Wing |  | 10 | 1010.309 |  |  | 1443
G Wing |  | 10 | 1010.309 |  |  | 1443
H Wing |  | 10 | 1010.309 |  |  | 1443
Total |  | 39 | 3945.1136 |  |  | 5635 |  |  |  |  | 62337.2267 | 44099.8034
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
D Wing |  | 12 | 6602.2253 |  |  | 9573.2267
E Wing |  | 24 | 8745.1042 |  |  | 12220
F Wing |  | 18 | 7466.2333 |  |  | 10522
G Wing |  | 24 | 9874.8936 |  |  | 13894
H Wing |  | 18 | 7466.2333 |  |  | 10493
Total |  | 96 | 40154.6897 |  |  | 56702.2267
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
D Wing
Ground Floor for Parking
1st Floor
1 |  | 2BHK | 608.3974 |  | 0 | 882.1763 | N | 1st Floor |  |  | 1.45
2 |  | 1BHK | 437.5297 |  | 0 | 634.4181 | N
3 |  | 2BHK | 572.2885 |  | 0 | 829.8183 | N
4 |  | 2BHK | 582.5262 |  | 0 | 844.6629 | N
2nd Floor
5 |  | 2BHK | 608.3974 |  | 0 | 882.1763 | N | 2nd Floor
6 |  | 1BHK | 437.5297 |  | 0 | 634.4181 | N
7 |  | 2BHK | 572.2885 |  | 0 | 829.8183 | N
8 |  | 2BHK | 582.5262 |  | 0 | 844.6629 | N
3rd Floor
9 |  | 2BHK | 608.3974 |  | 0 | 882.1763 | N | 3rd Floor
10 |  | 1BHK | 437.5297 |  | 0 | 634.4181 | N
11 |  | 2BHK | 572.2885 |  | 0 | 829.8183 | N
12 |  | 2BHK | 582.5262 |  | 0 | 844.6629 | N
E Wing
Ground Floor for Parking & Commercial
1 |  | Shop | 75.1327 |  | 0 | 107 | N | Ground Floor
2 |  | Shop | 96.876 |  | 0 | 139 | N
3 |  | Shop | 136.1646 |  | 0 | 194 | N
4 |  | Shop | 136.1646 |  | 0 | 194 | N
5 |  | Shop | 96.876 |  | 0 | 139 | N
6 |  | Shop | 73.7334 |  | 0 | 106 | N
7 |  | Shop | 113.8831 |  | 0 | 163 | N
8 |  | Shop | 89.2336 |  | 0 | 127 | N
9 |  | Shop | 96.1225 |  | 0 | 137 | N
1st & 3rd Floor
1 |  | 1RK | 248.6484 |  | 0 | 356 | N | 1st & 3rd Floor |  | 1.4317
2 |  | 1BHK | 412.8263 |  | 54.7619 | 610 | N |  |  | 1.4776
3 |  | 1RK | 258.1207 |  | 0 | 369 | N |  |  | 1.4296
4 |  | 1BHK | 473.7505 |  | 0 | 646 | N |  |  | 1.3636
5 |  | 1BHK | 400.3401 |  | 0 | 552 | N |  |  | 1.3788
6 |  | 1BHK | 392.59 |  | 0 | 542 | N |  |  | 1.3806
2nd & 4th Floor | [9 empty] | #DIV/0!
7 |  | 1RK | 248.6484 |  | 0 | 356 | N | 2nd & 4th Floor |  | 1.4317
8 |  | 1BHK | 412.8263 |  | 0 | 570 | N |  |  | 1.3807
9 |  | 1RK | 258.1207 |  | 0 | 369 | N |  |  | 1.4296
10 |  | 1BHK | 473.7505 |  | 0 | 646 | N |  |  | 1.3636
11 |  | 1BHK | 400.3401 |  | 0 | 552 | N |  |  | 1.3788
12 |  | 1BHK | 392.59 |  | 0 | 542 | N |  |  | 1.3806
F Wing | [9 empty] | #DIV/0!
Ground Floor for Parking & Commercial | [9 empty] | #DIV/0!
1 |  | Shop | 96.1225 |  | 0 | 137 | N | Ground Floor |  | 1.4253
2 |  | Shop | 96.1225 |  | 0 | 137 | N |  |  | 1.4253
3 |  | Shop | 89.2336 |  | 0 | 127 | N |  |  | 1.4232
4 |  | Shop | 113.8831 |  | 0 | 163 | N |  |  | 1.4313
5 |  | Shop | 73.7334 |  | 0 | 106 | N |  |  | 1.4376
6 |  | Shop | 96.876 |  | 0 | 139 | N |  |  | 1.4348
7 |  | Shop | 136.1646 |  | 0 | 194 | N |  |  | 1.4247
8 |  | Shop | 136.1646 |  | 0 | 194 | N |  |  | 1.4247
9 |  | Shop | 96.876 |  | 0 | 139 | N |  |  | 1.4348
10 |  | Shop | 75.1327 |  | 0 | 107 | N |  |  | 1.4241
1st & 3rd Floor
1 |  | 1RK | 248.6484 |  | 0 | 356 | N | 1st & 3rd Floor
2 |  | 1BHK | 398.2949 |  | 0 | 550 | N
3 |  | 1BHK | 398.0796 |  | 0 | 550 | N
4 |  | 2BHK | 589.329 |  | 0 | 800 | N
5 |  | 1BHK | 424.7744 |  | 44.4015 | 628 | N
6 |  | 1BHK | 429.6182 |  | 44.4015 | 633 | N
2nd & 4th Floor
7 |  | 1RK | 248.6484 |  | 0 | 356 | N | 2nd & 4th Floor
8 |  | 1BHK | 398.2949 |  | 0 | 550 | N
9 |  | 1BHK | 398.0796 |  | 0 | 550 | N
10 |  | 2BHK | 589.329 |  | 0 | 800 | N
11 |  | 1BHK | 424.7744 |  | 0 | 613 | N
12 |  | 1BHK | 429.6182 |  | 0 | 619 | N
G Wing
Ground Floor for Parking & Commercial
1 |  | Shop | 75.1327 |  | 0 | 107 | N | Ground Floor
2 |  | Shop | 96.876 |  | 0 | 139 | N |  |  | 667200
3 |  | Shop | 136.1646 |  | 0 | 194 | N
4 |  | Shop | 136.1646 |  | 0 | 194 | N
5 |  | Shop | 96.876 |  | 0 | 139 | N
6 |  | Shop | 73.7334 |  | 0 | 106 | N
7 |  | Shop | 113.8831 |  | 0 | 163 | N
8 |  | Shop | 89.2336 |  | 0 | 127 | N
9 |  | Shop | 96.1225 |  | 0 | 137 | N
10 |  | Shop | 96.1225 |  | 0 | 137 | N
1st & 3rd Floor
1 |  | 1RK | 248.6484 |  | 0 | 356 | N | 1st & 3rd Floor
2 |  | 1BHK | 412.8263 |  | 44.4015 | 610 | N
3 |  | 1BHK | 424.7744 |  | 0 | 628 | N
4 |  | 2BHK | 589.5443 |  | 0 | 800 | N
5 |  | 1BHK | 400.3401 |  | 0 | 552 | N
6 |  | 1BHK | 392.59 |  | 0 | 542 | N
2nd & 4th Floor
7 |  | 1RK | 248.6484 |  | 0 | 356 | N | 2nd & 4th Floor
8 |  | 1BHK | 412.8263 |  | 0 | 596 | N
9 |  | 1BHK | 424.7744 |  | 0 | 613 | N
10 |  | 2BHK | 589.5443 |  | 0 | 800 | N
11 |  | 1BHK | 400.3401 |  | 0 | 552 | N
12 |  | 1BHK | 392.59 |  | 0 | 542 | N
H Wing
Ground Floor for Parking & Commercial
1 |  | Shop | 96.1225 |  | 0 | 137 | N | Ground Floor
2 |  | Shop | 96.1225 |  | 0 | 137 | N
3 |  | Shop | 89.2336 |  | 0 | 127 | N
4 |  | Shop | 113.8831 |  | 0 | 163 | N
5 |  | Shop | 73.7334 |  | 0 | 106 | N
6 |  | Shop | 96.876 |  | 0 | 139 | N
7 |  | Shop | 136.1646 |  | 0 | 194 | N
8 |  | Shop | 136.1646 |  | 0 | 194 | N
9 |  | Shop | 96.876 |  | 0 | 139 | N | Ground Floor
10 |  | Shop | 75.1327 |  | 0 | 107 | N
1st & 3rd Floor
1 |  | 1RK | 248.6484 |  | 0 | 356 | N | 1st & 3rd Floor
2 |  | 1BHK | 398.2949 |  | 0 | 550 | N
3 |  | 1BHK | 398.0796 |  | 0 | 550 | N
4 |  | 2BHK | 589.329 |  | 0 | 800 | N
5 |  | 1BHK | 424.7744 |  | 44.4015 | 628 | N
6 |  | 1BHK | 429.6182 |  | 44.4015 | 633 | N
2nd & 4th Floor
7 |  | 1RK | 248.6484 |  | 0 | 356 | N | 2nd & 4th Floor
8 |  | 1BHK | 398.2949 |  | 0 | 550 | N
9 |  | 1BHK | 398.0796 |  | 0 | 550 | N
10 |  | 2BHK | 589.329 |  | 0 | 800 | N
11 |  | 1BHK | 424.7744 |  | 0 | 613 | N
12 |  | 1BHK | 429.6182 |  | 0 | 619 | N
Remarks:
1. D Wing = All work completed. OC Received. E & F Wing = All work completed. Please provide OC. G & H Wing = Some flat are occupied by tenants but finishing & lift work is Pending. 3. We considered Saleable area as per Builder area sheet. 4. We considered Carpet area as per Approved Plan. 5. We considered Gross carpet area = Net carpet + Enclose balcony + A.P Area. 6. We have considered rate by verifying it from market inquire. 7. We have considered Other charges from cost sheet. 8. Car parking is subjected to authentic documentation. 9. We have updated revised plans & CC of Wing D (on 23/12/2022). 10. As per RERA, completion period of project Pal Garden is expired on 30/12/2023 but still project is under construction. 11. Since the Rera website is down right now, on 29/06/2024, we are unable to find outExpiry Date of Pal Garden.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Lovanshi |  | Report Prepared By : |  |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pal garden Phase II
Google Map :
E & F Wing
G Wing
H Wing
G Wing
H Wing
H Wing
G Wing
H Wing
Wing G
Wing F
Wing H
Wing H
Wing D
Wing E
Wing G
Wing G
Wing H
Wing D
Wing E
Wing F
Wing G
Wing H

## E & F C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G C% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 4 | 80% |  | Parking |  | Rate
Bricks | 4 | 2 | 50% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 32 | 7.5 | 0 | 0 | 0 | 0
RCC | 32 | 24 |  | Recommended |  | 30 | 24 | 7.5 | 0 | 0 | 0 | 0
Bricks | 7.5 | 7.5
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 49.5% | 61.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## H C% (3)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 7 | 70%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 7 | 27 |  | Progress |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 7% | 27% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
24/03/2021 | Pratiksha | OLD APF | As per his information, 1RK =12.5 Lac, 1BHK = 21 Lac, 2BHK = 27 Lac, Shop = 11 Lac

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 4.65 | 12.7875 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.5 | 2.2 | 5.5 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.45 | 1.2 | 1.74 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 0.9 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.2 | 1.2 | 1.44 |  |  |  | 0 |  |  | 0
| passage2 | 0.4 | 1.2 | 0.48 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 247.868 | 23.0275 |  |  | 0 | 0 |  | 0 | 0
|  |  | 247.868 | 23.0275