## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-13
Name of the builder group |  |  |  | Nirvaana Construction Co
Name of the builder company |  |  |  | Nirvaana Construction Co
Name of the Project |  |  |  | Nirvaana Residency Phase I & II
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Deepak Shinde (8779898058)
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Deepak Shinde (8779898058)
Name / No of the Building |  |  |  | Phase I = Building No.2 Wing A & B, Building No.4 Phase II = Building No.1 Wing A & B, Building No.3
Name / No of the Existing Building |  |  |  | NA | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC & Cost Sheet. | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | Phase I = P52000013902 Phase II = P52000016647 |  |  |  | #N/A |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Nirvaana Residency Phase I & II, Gut No.106/0, Sub Plot No. 1 to 25, near Dmart, Karjat-Neral Road, Vanjale, Vanjale, Karjat (West), Karjat, Raigad - 410201. | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Gut No |  | 106/0, Sub Plot No. 1 to 25 | [9 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Vanjale | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Karjat-Neral Road |  | Locality/Village |  | Vanjale | [5 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Karjat (West) |  | District |  | Raigad | [5 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Karjat |  | Pin Code |  | 410201 | [8 empty] | Mahad | Daund
Nearby Landmark |  | Dmart |  | Distance from city centre: |  | 3.40KM from Karjat Railway Station | [8 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [10 empty] | Mangaon | Ambegaon
[15 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [10 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [10 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [10 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Gut No. 102 Sub Plot No. 1 |  |  | Open plot
West | NA | Gut No. 109 |  |  | Open plot
North | NA | Gut No. 1 |  |  | Internal Road
South | NA | Gut No. 107 & 108 |  |  | Eco Greens
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.932789,73.321963
Location Link |  | https://goo.gl/maps/T3TEdCjxXhFrHX3s8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 13560
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.37133
Total FSI availaible for the project |  |  |  | 1.4713 |  |  |  | 1.4713
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19951.228
Total number of Buildings |  |  |  | 06 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector of Raigad
Layout Approval No |  | MS/LNA-1S/06/2021 |  |  | Dated | 2022-02-14
Approved Floor plan No. |  | MS/LNA-1S/06/2021 |  |  | Dated | 2022-02-14
Commencement-CC No |  | MS/L.N.A.1(B)/Token No.15228/06/2021 |  |  | Dated | 2022-02-14
Valid Up to: |  | Building No. 1 = Gr + 1st to 11th Floor Building No. 2, 3 & 4 = Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 12950.573
Approved no of units |  |  | Flats - 240
Approved no of Floors |  |  | Building No.1 (A & B Wing) = G + 1st to 11th Floor Building No.2 (A & B Wing) = G + 1st to 7th Floor Building No.3 = G + 1st to 7th Floor Building No.4 = G + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 (A & B Wing) = G + 1st to 11th Floor
Building No.2 (A & B Wing) = G + 1st to 7th Floor
Building No.3 = G + 1st to 7th Floor
Building No.4 = G + 1st to 7th Floor
Expected Completion |  |  | As per RERA - Phase I = Completed, Phase II = 30/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Yoga/Meditation Area, Children's Play Area, Cycling & Jogging Track, Gymnasium, Club House, Landscaping & Tree Planting & Swimming Pool, etc. | [5 empty] | https://housing.com/in/buy/projects/page/102260-nirvaana-residency-by-nirvaana-construction-in-karjat
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (A Wing) = G + 1st to 11th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 2 Floor Completed | , RCC upto 5 Slab, Brickwork upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 28.03% |  | 58.41% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 5 | 41.67% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 2 | 18.18% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Building No.1 (B Wing) = G + 1st to 11th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed |  |  | Allready Given extra % For 1B Wing
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 10% |  | 45% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Building No.2 (A & B Wing) = G + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.3 = G + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.4 = G + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3700
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 150000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 2960
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 Wing A |  | 120 |  | 50057.6367 |  | 75086.4551
Building No. 1 Wing B |  | 120 |  | 50097.7657 |  | 75146.6486
Total |  | 240 |  | 100155.4025 |  | 150233.1037
Grand Total |  | 240 |  | 100155.4025 |  | 150233.1037
Building details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
45%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor |  | 40.23 | 35.61 | 2.34
3 |  |  |  | 0 | 0 | Ground Floor |  | 38.175 | 35.045 | 2.475
4 |  |  |  | 0 | 0 | Ground Floor |  | 38.325
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor |  | 33.925
[5 empty] | 50% |  |  | 34.075
Phase II | [7 empty] | 33.925
Building No. 1 | [7 empty] | 33.775
Wing A | [7 empty] | 40.19
Ground Floor For Parking | [7 empty] | 55.468 | 48.815 | 2.475
1st to 7th & 9th to 11th Floor For Residential | [7 empty] | 39.218 | Cost Sheet
101 ,.., 1101 |  | 1BHK | 433.0357 | 0 | 649.5536 | 1st to 7th & 9th to 11th Floor For Residential |  | 39.218 | 3692.7916
102 ,.., 1102 |  | 1BHK | 410.9157 | 0 | 616.3736
103 ,.., 1103 |  | 1BHK | 412.5303 | 0 | 618.7955
104 ,.., 1104 |  | 1BHK | 365.1687 | 0 | 547.7531
105 ,.., 1105 |  | 1BHK | 366.7833 | 0 | 550.1749
106 ,.., 1106 |  | 1BHK | 365.1687 | 0 | 547.7531
107 ,.., 1107 |  | 1BHK | 363.5541 | 0 | 545.3311
108 ,.., 1108 |  | 1BHK | 432.6052 | 0 | 648.9077
109 ,.., 1109 |  | 2BHK | 597.0576 | 0 | 895.5863 |  |  |  | 3702.3756
110 ,.., 1110 |  | 1BHK | 422.1426 | 0 | 633.2138
111 ,.., 1111 |  | 1BHK | 422.1426 | 0 | 633.2138 |  |  |  | 3708.1929
8th Floor (Part Refuge Area) | [8 empty] | 3701.12
801 |  | 1BHK | 433.0357 | 0 | 649.5536 | 8th Floor (Part Refuge Area)
802 |  | 1BHK | 385.3719 | 0 | 578.0579
803 |  | 1BHK | 412.5303 | 0 | 618.7955
804 |  | 1BHK | 365.1687 | 0 | 547.7531
805 |  | 1BHK | 366.7833 | 0 | 550.1749 |  |  | 39.218 | 33.81 | 2.475
806 |  | 1BHK | 368.3441 | 0 | 552.5161 |  |  | 39.218
807 |  | 1BHK | 363.5541 | 0 | 545.3311 |  |  | 55.468 | 48.9765 | 2.475
808 |  | 1BHK | 432.6052 | 0 | 648.9077 |  |  | 40.34
809 |  | 2BHK | 597.0576 | 0 | 895.5863 |  |  | 33.775 | 28.9175 | 2.475
810 |  | 1BHK | 422.1426 | 0 | 633.2138 |  |  | 33.925
811 |  | Refuge Area | [5 empty] | 34.075
Wing B | [7 empty] | 33.925
Ground Floor For Parking | [7 empty] | 38.325
1st to 7th & 9th to 11th Floor For Residential | [7 empty] | 38.175
101 ,.., 1101 |  | 1BHK | 422.1426 | 0 | 633.2138 | 1st to 7th & 9th to 11th Floor For Residential |  | 40.23
102 ,.., 1102 |  | 1BHK | 422.1426 | 0 | 633.2138
103 ,.., 1103 |  | 2BHK | 597.0576 | 0 | 895.5863
104 ,.., 1104 |  | 1BHK | 434.2198 | 0 | 651.3296
105 ,.., 1105 |  | 1BHK | 363.5541 | 0 | 545.3311
106 ,.., 1106 |  | 1BHK | 365.1687 | 0 | 547.7531
107 ,.., 1107 |  | 1BHK | 366.7833 | 0 | 550.1749
108 ,.., 1108 |  | 1BHK | 365.1687 | 0 | 547.7531
109 ,.., 1109 |  | 1BHK | 412.5303 | 0 | 618.7955
110 ,.., 1110 |  | 1BHK | 410.9157 | 0 | 616.3736
111 ,.., 1111 |  | 1BHK | 433.0357 | 0 | 649.5536
8th Floor (Part Refuge Area)
801 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
802 |  | 1BHK | 422.1426 | 0 | 633.2138
803 |  | 2BHK | 597.0576 | 0 | 895.5863
804 |  | 1BHK | 434.2198 | 0 | 651.3296
805 |  | 1BHK | 363.5541 | 0 | 545.3311
806 |  | 1BHK | 365.1687 | 0 | 547.7531
807 |  | 1BHK | 366.7833 | 0 | 550.1749
808 |  | 1BHK | 365.1687 | 0 | 547.7531
809 |  | 1BHK | 412.5303 | 0 | 618.7955
810 |  | 1BHK | 410.9157 | 0 | 616.3736
811 |  | 1BHK | 433.0357 | 0 | 649.5536
Remarks:
* | Building No. 1 (Wing A) = Construction work is in process at the time of Visit.(Slow Speed) Building No. 1 (Wing B) = Construction work is same as last visit dtd.12/08/2024 Building No. 2 (Wing A & B) = All work completed. Please provide OC. Building No. 3 & 4 = All work completed. Please provide OC.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised plans & CC for Phase II (building no.1 wing A & B) (on 18/09/2023).
* | As per RERA, completion period of project Nirvaana Residency Phase I is expired on 29/12/2024 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Nirvaana Residency Phase I & II
Allready Given extra % For 1B Wing
Layout :
Google Map :
Formulas:
Vanjale = [Vanjale, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building
Building No. 2
Wing A
Building No. 2
Wing B
Building No. 3
Building No. 4
Building No. 1
Wing A & B
Building No. 2
Wing A & B
Building No. 4
Building No. 3
Bldg No. 4
Bldg No. 1, 2 & 3
Building No. 1
Wing A
Building No. 1
Wing B
Building No. 2
Wing A
Building No. 2
Wing B
Building No. 3
Building No. 4
4
3
2B
2A
1B
1A
1A
1B
2A
2A
3
4
2A
2B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC