## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-07
Name of the builder group |  |  |  | Trinetram Realty
Name of the builder company |  |  |  | Trinetram Realty
Name of the Project |  |  |  | Vinayak Greens
Provided Contact Details ( Name & Contact No.) |  |  |  | Anil Kapadia 9699709000
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Ms. Nisha Mhatre 7249122920 |  |  |  | Mr.Mihir 9137003629
Name / No of the Building |  |  |  | A, B, C & D Wing
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000046863
Project location details |  | Vinayak Greens, Survey No.19/1D, near Escon Elevators Factory, Savroli - Kharpada Road, , Kasap, Rasayani, Panvel, Raigad - 410220.
Survey No |  | 19/1D
Locality |  | NA
Road |  | Savroli - Kharpada Road |  | Locality/Village |  | Kasap
City |  | Rasayani |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410220
Nearby Landmark |  | Escon Elevators Factory |  | Distance from city centre: |  | 5.6KM from Rasayani Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 18.872 |  | Longitude |  | 73.1614
Location Link |  | https://goo.gl/maps/1xEnt982AGE6Suio6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3600
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.2
Total FSI availaible for the project |  |  |  | 1.3
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4680
Total number of Buildings |  |  |  | 04 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector of raigad
Layout Approval No |  | MS/LNA-1SR/192/20018 |  |  | Dated | 2021-12-23
Approved Floor plan No. |  | MS/LNA-1SR/192/20018 |  |  | Dated | 2021-12-23
Commencement-CC No Valid Up to: |  | KMS/LNA.1(B)/TN.14106/SR.192/2018 |  |  | Dated | 2021-12-23
A to D Wing = G + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4680
Approved no of units |  |  | Flats - 129, Shops - 5
Approved no of Floors |  |  | A to D Wing = G + 1st to 7th Floor
Proposed no of Floors |  |  | A to D Wing = G + 1st to 7th Floor
Expected Completion |  |  | As per RERA -31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A & B Wing = G + 1st to 7th Floor C Wing = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 30% |  | 60% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 4 | 50% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | C Wing = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 30% |  | 60% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 4 | 50% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | D Wing = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab Completed | , RCC upto 5 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 35% |  | 63.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 5 | 62.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3800 |  |  | 3500 to 3800 | smith | 2024-01-08
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000
Water, MSEB, Development Charges |  |  |  |  | 154583
Club Membership Charges |  |  |  |  | 51183
Society Formation Charges |  |  |  |  | 51183
Recommended rate of Parking |  |  |  |  | 150000 |  |  | 1L to 1.5L | 2024-01-08
Distressed valuation of the Property |  |  |  |  | 3040
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 5 |  | 1186.0744 |  | 2394.08
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 30 |  | 13024.3431 |  | 23480
B Wing |  | 31 |  | 10573.8755 |  | 18380 |  |  | 45769.7013
C Wing |  | 30 |  | 10200.397 |  | 17635
D Wing |  | 38 |  | 10785.0113 |  | 19130
Total |  | 129 |  | 44583.6269 |  | 78625
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
A Wing
Ground Floor For Part Commercial & Parking | [8 empty] | 22.195
1 |  | Shop | 239.7143 | 0 | 483.82 | Ground Floor For Part Commercial & Parking |  |  | 2.0183
2 |  | Shop | 235.5486 | 0 | 475.48
3 |  | Shop | 235.5486 | 0 | 475.48
4 |  | Shop | 235.5486 | 0 | 475.48
5 |  | Shop | 239.7143 | 0 | 483.82
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
A Wing
Ground Floor For Part Commercial, Part Residential & Parking | [9 empty] | 21.2625
1 |  | 1RK | 230.1558 | 0 | 370 | Ground Floor For Part Commercial, Part Residential & Parking |  |  | 1.6076
2 |  | 1RK | 213.6331 | 0 | 350
1st Floor For Residential
1 |  | 2BHK | 469.2028 | 144.7893 | 975 | 1st Floor For Residential |  |  | 38.68
2 |  | 2BHK | 469.2243 | 144.7893 | 975
3 |  | 2BHK | 515.0251 | 47.3616 | 890
4 |  | 1BHK | 357.9783 | 43.8095 | 630
2nd, 4th & 6th Floor
1 |  | 2BHK | 454.5099 | 51.1828 | 830 | 2nd, 4th & 6th Floor
2 |  | 2BHK | 454.5314 | 51.1828 | 830
3 |  | 2BHK | 494.6811 | 88.2648 | 925
4 |  | 1BHK | 356.8481 | 27.5827 | 600
3rd, 5th & 7th Floor
1 |  | 2BHK | 488.7932 | 59.054 | 865 | 3rd, 5th & 7th Floor
2 |  | 2BHK | 488.0613 | 59.054 | 865
3 |  | 2BHK | 494.3044 | 43.8095 | 885
4 |  | 1BHK | 357.9783 | 43.8095 | 630
B Wing
Ground Floor For Residential & Parking
1 |  | 1RK | 213.6331 | 0 | 360 | Ground Floor For Residential & Parking |  |  | 4900 | 1260000
2 |  | 1RK | 213.6331 | 0 | 360 |  |  |  |  | 1260000
3 |  | 1RK | 213.6331 | 0 | 360 |  |  |  |  | 1260000
1st Floor For Residential | [8 empty] | 3730.7087
1 |  | 1BHK | 357.9783 | 45.5855 | 635 | 1st Floor For Residential |  |  | `
2 |  | 1BHK | 357.9783 | 45.5855 | 635
3 |  | 1BHK | 357.9783 | 45.5855 | 635
4 |  | 1BHK | 357.9783 | 45.5855 | 635
2nd, 4th & 6th Floor
1 |  | 1BHK | 343.2855 | 24.2728 | 600 | 2nd, 4th & 6th Floor
2 |  | 1BHK | 343.2855 | 24.2728 | 600
3 |  | 1BHK | 356.8481 | 27.5827 | 600
4 |  | 1BHK | 356.8481 | 27.5827 | 600
3rd, 5th & 7th Floor
1 |  | 1BHK | 358.3551 | 45.5855 | 630 | 3rd, 5th & 7th Floor
2 |  | 1BHK | 358.3551 | 45.5855 | 630
3 |  | 1BHK | 358.3551 | 45.5855 | 630
4 |  | 1BHK | 358.3551 | 45.5855 | 630
C Wing | [8 empty] | `
Ground Floor For Residential & Parking
1 |  | 1RK | 213.6331 | 0 | 355 | Ground Floor For Residential & Parking
2 |  | 1RK | 197.7024 | 0 | 330
1st Floor For Residential
1 |  | 1BHK | 357.9783 | 45.5855 | 630 | 1st Floor For Residential
2 |  | 1BHK | 340.9174 | 44.4015 | 600
3 |  | 1BHK | 340.9174 | 44.4015 | 600
4 |  | 1BHK | 357.9783 | 45.5855 | 630
2nd, 4th & 6th Floor
1 |  | 1BHK | 356.8481 | 27.5827 | 600 | 2nd, 4th & 6th Floor
2 |  | 1BHK | 340.9174 | 25.5645 | 585
3 |  | 1BHK | 340.9174 | 25.5645 | 585
4 |  | 1BHK | 356.8481 | 27.5827 | 600
3rd, 5th & 7th Floor
1 |  | 1BHK | 358.3551 | 45.5855 | 630 | 3rd, 5th & 7th Floor
2 |  | 1BHK | 342.4244 | 44.4015 | 600
3 |  | 1BHK | 342.4244 | 44.4015 | 600
4 |  | 1BHK | 358.3551 | 45.5855 | 630
D Wing
Ground Floor For Residential & Parking
1 |  | 1RK | 220.3606 | 0 | 355 | Ground Floor For Residential & Parking
2 |  | 1RK | 220.3606 | 0 | 355
3 |  | 1RK | 197.7024 | 0 | 330
1st Floor For Residential
1 |  | 1RK | 265.5694 | 43.3116 | 490 | 1st Floor For Residential
2 |  | 1RK | 239.1976 | 43.3116 | 450
3 |  | 1RK | 224.1818 | 30.6774 | 415
4 |  | 1BHK | 340.9174 | 42.6254 | 600
5 |  | 1BHK | 340.7344 | 42.6254 | 610
2nd, 4th & 6th Floor
1 |  | 1RK | 284.4064 | 22.3891 | 475 | 2nd, 4th & 6th Floor
2 |  | 1RK | 258.0346 | 63.6421 | 490
3 |  | 1RK | 246.7862 | 83.421 | 510
4 |  | 1BHK | 340.9174 | 25.5645 | 575
5 |  | 1BHK | 354.2971 | 0 | 560
3rd, 5th & 7th Floor
1 |  | 1RK | 277.6251 | 43.2336 | 490 | 3rd, 5th & 7th Floor
2 |  | 1RK | 239.1976 | 43.2336 | 450
3 |  | 1RK | 226.4423 | 33.7451 | 415
4 |  | 1BHK | 341.6709 | 42.6254 | 600
5 |  | 1BHK | 342.6181 | 42.6254 | 610
Remarks:
* | Wing A to C = Construction work is same as last visit dtd. 05/06/2025 but work is in process at the time of visit (Slow Speed). Wing D = Construction work is in process at the time of visit. | [6 empty] | Construction work has incresed as compare to last visited date 12/12/2024 but at the time of visit no labour or no active work found on site.
* | We considered Saleable area of Flat as per Builder area Sheet. | [6 empty] | Wing A to D = Construction work has increased as compare to last visit dated 08/03/2025. (Very Slow Speed).
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 08/01/2024
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh Patil |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vinayak Greens
Layout :
-
Google Map :
Formulas:
Kasap = [Kasap, row above]
North
North
Wing A
Wing B
Wing C
Wing D
C
D
D
Wing A
Wing A
Wing B
Wing C
Wing D
Wing D
Wing C
Wing B
Wing A
Wing A
Wing B
Wing C
Wing D

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted