## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-10
Name of the builder group |  |  |  | Bharat Realty Venture Private Limited
Name of the builder company |  |  |  | Bharat Realty Venture Private Limited
Name of the Project as per Builder |  |  |  | Bharat Altavistas
Name of the Project as per Rera |  |  |  | Proposed Residential cum Commercial Redevelopment of Apna Ghar Unit No. 9 CHSL
Provided Contact Details (Name & Contact No.) |  |  |  | 022-26378000
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Shraddha : 9653664162
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | Apna Ghar Unit No-09 (Sheetal Chhaya) CO-OP. HSG. Society LTD. |  |  |  | As per legel title " Municipal No. 35 & 36 Known as Sheetal Chhaya" | [5 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC & EC. | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800052790 |  |  |  | #N/A | [5 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Bharat Altavistas, Plot No.11, CTS No.1/28, Surver No.41(Pt) & Redevlopement of " Apna Ghar Unit No-09 (Sheetal Chhaya) CO-OP. HSG. Society LTD.", near Royal Accord, P Tandon Marg, Lokhandwala Complex, Oshiwara, Andheri West, Andheri, Mumbai - 400053. | [11 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 11, CTS No.1/28, Surver No.41(Pt) & Redevlopement of " Apna Ghar Unit No-09 (Sheetal Chhaya) CO-OP. HSG. Society LTD." | [11 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Lokhandwala Complex | [11 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | P Tandon Marg |  | Locality/Village |  | Oshiwara | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Andheri West |  | District |  | Mumbai | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Andheri |  | Pin Code |  | 400053 | [10 empty] | Mahad | Daund
Nearby Landmark |  | Royal Accord |  | Distance from city centre: |  | 3.10Km from Jogeshwari Railway Station | [10 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [12 empty] | Mangaon | Ambegaon
[17 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [12 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [12 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [12 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Clanfield Housing Society
West | NA | 27.45 M. Wide Road |  |  | Lokhandwala Complex Road
North | NA | Other Plot |  |  | Nilgiri Bldg/Brookfield Apartment
South | NA | 36.60 M. Wide Road |  |  | P Tondon Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.140686,72.82665
Location Link |  | https://maps.app.goo.gl/PTixq9bNZxKictm4A
Area Statement Details : | [10 empty] | 480
Total land area of the project in Sq. Mt. |  |  |  | 5829.51
Permissible FSI |  |  |  | 4 |  |  |  | 4.2587
Permissible TDR/Paid FSI |  |  |  | 1.7442
Total FSI availaible for the project |  |  |  | 5.7442
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 33485.7
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | K/W/PVT/0180/20230130/AP/S |  |  | Dated | 2024-04-22 |  | SRA/ENG/K/W/PVT/0180/20230130/AP/S |  |  | 2023-03-31
Approved Floor plan No. |  | K/W/PVT/0180/20230130/AP/S |  |  | Dated | 2024-04-22
Commencement-CC No |  | K-W/PVT/0180/20230130/AP/S |  |  | Dated | 2024-04-22
Valid Up to: |  | This C.C is further extended upto Basement + Ground +1st Commercial + 2nd to 6th Podium Level's + 7th Amenity floors + Service floor + 8th to 16th upper floors as per last approved amended plans Dated 22/04/2024
Environmental Clearance (EC) No. |  | SIA/MH/INFRA2/426183/2023 |  |  | Dated | 2023-08-10
Part O. Certificate No.: |  | K/W/PVT/0180/20230130/AP/S Valid Upto : Sale Building = Gr. + 1st Floor |  |  | Dated | 2025-04-04
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 33485.7
Approved no of units |  |  | Flats - 257, Rehab Shops - 9, Sale shops - 17
Approved no of Floors |  |  | G + 1st to 29th Floor
Proposed no of Floors |  |  | G + 1st to 29th Floor
Expected Completion |  |  | As per RERA - 30/09/2030
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Kids Play Area, Fitness centre, Cumminity Hall, Snookers, Badminton Court, SPA, Yoga Room, Squash Court & Garden, etc. |  |  |  |  | from site and plan | https://bharataltavistalokhandwala.net/
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Part I = G + 1st to 29th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 13 Slab, Brickwork upto 5 Floor Completed | , RCC upto 13 Slab, Brickwork upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 29 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 13 Slab, Brickwork upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 28.63% |  | 58.86% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 13 | 43.33% |  |  |  |  | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 5 | 17.24% |  |  |  |  | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 29
Construction details: |  | Part II = G + 1st to 29th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 7 Floor Completed | , RCC upto 15 Slab, Brickwork upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 29 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 31.81% |  | 61.21% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 15 | 50% |  |  |  |  | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 7 | 24.14% |  |  |  |  | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 29
Average Progress % |  | 30.22% |  | Average Disbursement % |  | 60.03% |  | Plinth completed | 29
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 28000 |  |  | 26000 to 28000 & OC 12L by Nilesh & aakash on 15/02/2025
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 67000 |  |  | 35000 to 67000 | Sanjay | Tamanna Bhatia Case |  | 2024-06-18 | Cost Sheet
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges |  |  |  |  | 950000
Legal Charges
Gas Connection Charges
MSEB/MJP/Electric Meter |  |  |  |  | 75000
Society Formation |  |  |  |  | 50000
Society Corpus |  |  |  |  | 125000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 22400
Commercial Area Details (Rehab) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 9 |  | 4935.6546 |  | 7897.0474
Commercial Area Details (Sale) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 17 |  | 30857.204 |  | 49371.5264
Residential Area Details (Sale & Rehab) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 257 |  | 297072.0731 |  | 460461.7133 |  | 20 | 257 | 22 | 264 | 256 | 270
Grand Total |  | 283 |  | 332864.9317 |  | 517730.2871
Building details Floor Wise | [8 empty] | 30923.9067
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Sale / Rehab | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor For Commercial, Parking, Fire Control Room & Lobby | [8 empty] | 493.7444
1 | Rehab | Shop | 579.9374 | 0 | 927.8999 | Ground Floor For Commercial, Parking, Fire Control Room & Lobby |  | 53.8775
2 | Rehab | Shop | 601.0349 | 0 | 961.6558 |  |  | 55.8375 | 53.4188
3 | Rehab | Shop | 575.0398 | 0 | 920.0637 |  |  | 53.4225
4 | Rehab | Shop | 533.5456 | 0 | 853.673 |  |  | 49.5676
5 | Rehab | Shop | 391.1734 | 0 | 625.8775 |  |  | 36.3409
6 | Rehab | Shop | 586.342 | 0 | 938.1472
7 | Rehab | Shop | 552.0586 | 0 | 883.2938
8 | Rehab | Shop | 552.0586 | 0 | 883.2938
9 | Rehab | Shop | 564.4642 | 0 | 903.1427 |  |  | 52.4551 | 52.4498
10A | Sale | Shop (Duplex With 1st Floor) | 254.2844 | 0 | 406.8551 |  |  | 121.583 | 682.195 | 230.333 | 505.5485 |  | 7873.866
10 | Sale | Shop (Duplex With 1st Floor) | 2240.4556 | 0 | 3584.7289 |  |  | 121.583 | 682.195 | 230.333 | 505.5485 |  | 7873.866
11 | Sale | Shop (Duplex With 1st Floor) | 1430.9662 | 0 | 2289.5459 |  |  | 117.635 | 104.4 | 117.541 | 2530.4549
12 | Sale | Shop (Duplex With 1st Floor) | 1243.0999 | 0 | 1988.9599 |  |  | 108.52 |  |  |  |  | 51.5208
14 | Sale | Shop (Duplex With 1st Floor) | 1264.8819 | 0 | 2023.8111 |  |  | 108.5655
15 | Sale | Shop (Duplex With 1st Floor) | 1243.7393 | 0 | 1989.9829 |  |  | 108.5655
16 | Sale | Shop (Duplex With 1st Floor) | 1243.7393 | 0 | 1989.9829 |  |  | 107.388
18 | Sale | Shop (Duplex With 1st Floor) | 1237.3046 | 0 | 1979.6873 |  |  | 109.1935
19 | Sale | Shop (Duplex With 1st Floor) | 1257.528 | 0 | 2012.0448 |  |  | 124.815
20 | Sale | Shop (Duplex With 1st Floor) | 1257.528 | 0 | 2012.0448 |  |  | 172.292
21 | Sale | Shop (Duplex With 1st Floor) | 1243.7393 | 0 | 1989.9829 |  |  | 153.9293 | 152.9108
22 | Sale | Shop (Duplex With 1st Floor) | 1264.8819 | 0 | 2023.8111 |  |  | 185.1168 | 5611.1914
23 | Sale | Shop (Duplex With 1st Floor) | 1237.3046 | 0 | 1979.6873 |  |  | 109.1935
24 | Sale | Shop (Duplex With 1st Floor) | 1427.5992 | 0 | 2284.1587 |  |  | 124.815
25 | Sale | Shop (Duplex With 1st Floor) | 3824.8109 | 0 | 6119.6974 |  |  | 172.292
26 | Sale | Shop (Duplex With 1st Floor) | 4259.444 | 0 | 6815.1103 |  |  | 153.9293 | 152.9108
27 | Sale | Shop (Duplex With 1st Floor) | 4925.897 | 0 | 7881.4352 |  |  | 185.1168 | 5611.1914
1st Floor For Duplex Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
2nd to 6th Podium Floor For Parking
7th Floor For Cumminity Hall, Fitness Centre, Snookers, Badminton Court, SPA, Swimming Pool, Letter Box Room, Yoga Room, Squash Court & Garden
RCC Girder Level Between 7th & 8th Floor
Service Floor Between 7th & 8th Floor
8th Floor For Residential
1 |  | 3BHK | 882.0345 | 0 | 1367.1534 | 8th Floor For Residential |  | 79.7739 | 76.5984 | 38400.9578
2 |  | 3BHK | 858.3214 | 0 | 1330.3981
3 |  | 3BHK | 1009.7708 | 0 | 1565.1448
4 |  | 3BHK | 1009.7708 | 0 | 1565.1448
5 |  | 3BHK | 1007.7257 | 0 | 1561.9748
6 |  | 3BHK | 1007.7257 | 0 | 1561.9748
7 |  | 3BHK | 1007.7257 | 0 | 1561.9748
8 |  | 3BHK | 1007.7257 | 0 | 1561.9748
9 |  | 3BHK | 1009.7708 | 0 | 1565.1448
10 |  | 3BHK | 1009.7708 | 0 | 1565.1448
11 |  | 3BHK | 882.0022 | 0 | 1367.1033
12 |  | 3BHK | 882.0022 | 0 | 1367.1033
9th Floor
1 |  | 3BHK | 882.0345 | 0 | 1367.1534 | 9th Floor
2 |  | 3BHK | 882.0345 | 0 | 1367.1534
3 |  | 3BHK | 1009.7708 | 0 | 1565.1448
4 |  | 3BHK | 1009.7708 | 0 | 1565.1448
5 |  | 3BHK | 1007.7257 | 0 | 1561.9748
6 |  | 3BHK | 1007.7257 | 0 | 1561.9748
7 |  | 3BHK | 1007.7257 | 0 | 1561.9748
8 |  | 3BHK | 1007.7257 | 0 | 1561.9748
9 |  | 3BHK | 1009.7708 | 0 | 1565.1448
10 |  | 3BHK | 1009.7708 | 0 | 1565.1448
11 |  | 3BHK | 882.0022 | 0 | 1367.1033
12 |  | 3BHK | 882.0022 | 0 | 1367.1033
10th to 13th Floor
1 |  | 3BHK | 972.3121 | 0 | 1507.0838 | 10th to 13th Floor
2 |  | 3BHK | 972.3121 | 0 | 1507.0838
3 |  | 3BHK | 1009.7708 | 0 | 1565.1448
4 |  | 3BHK | 1009.7708 | 0 | 1565.1448
5 |  | 3BHK | 1007.7257 | 0 | 1561.9748
6 |  | 3BHK | 1007.7257 | 0 | 1561.9748
7 |  | 3BHK | 1007.7257 | 0 | 1561.9748
8 |  | 3BHK | 1007.7257 | 0 | 1561.9748
9 |  | 3BHK | 1009.7708 | 0 | 1565.1448
10 |  | 3BHK | 1009.7708 | 0 | 1565.1448
11 |  | 3BHK | 972.3121 | 0 | 1507.0838
12 |  | 3BHK | 972.3121 | 0 | 1507.0838
14th Floor (Part Refuge Area)
1 |  | 3BHK | 972.3121 | 0 | 1507.0838 | 14th Floor (Part Refuge Area)
2 |  | 3BHK | 972.3121 | 0 | 1507.0838
3 |  | 3BHK | 1009.7708 | 0 | 1565.1448
4 |  | 3BHK | 1009.7708 | 0 | 1565.1448
5 |  | Refuge Area
6
7
8 |  | 3BHK | 1007.7257 | 0 | 1561.9748
9 |  | 3BHK | 1009.7708 | 0 | 1565.1448
10 |  | 3BHK | 1009.7708 | 0 | 1565.1448
11 |  | 3BHK | 972.3121 | 0 | 1507.0838
12 |  | 3BHK | 972.3121 | 0 | 1507.0838
15th to 17th Floor
1 |  | 3BHK | 1007.7257 | 0 | 1561.9748 | 15th to 17th Floor
2 |  | 3BHK | 1007.7257 | 0 | 1561.9748
3 |  | 3BHK | 1009.7708 | 0 | 1565.1448
4 |  | 3BHK | 1009.7708 | 0 | 1565.1448
5 |  | 3BHK | 1007.7257 | 0 | 1561.9748
6 |  | 3BHK | 1007.7257 | 0 | 1561.9748
7 |  | 3BHK | 1007.7257 | 0 | 1561.9748
8 |  | 3BHK | 1007.7257 | 0 | 1561.9748
9 |  | 3BHK | 1009.7708 | 0 | 1565.1448
10 |  | 3BHK | 1009.7708 | 0 | 1565.1448
11 |  | 3BHK | 1007.7257 | 0 | 1561.9748
12 |  | 3BHK | 1007.7257 | 0 | 1561.9748
18th, 19th, 20th, 22nd to 29th Floor
1 |  | 3BHK | 1282.8535 | 0 | 1988.423 | 18th, 19th, 20th, 22nd to 29th Floor |  | 27609.8201 | 26402.8334
2 |  | 3BHK | 1282.8535 | 0 | 1988.423 |  |  | 27609.8201 |  | 53200000
3 |  | 3BHK | 1308.3642 | 0 | 2027.9645 |  |  | 27416.6534 | 26233.2007
4 |  | 3BHK | 1308.3642 | 0 | 2027.9645 |  |  | 27416.6534
5 |  | 3BHK | 1282.8535 | 0 | 1988.423
6 |  | 3BHK | 1282.8535 | 0 | 1988.423
7 |  | 3BHK | 1282.8535 | 0 | 1988.423
8 |  | 3BHK | 1282.8535 | 0 | 1988.423
9 |  | 3BHK | 1308.3642 | 0 | 2027.9645
10 |  | 3BHK | 1308.3642 | 0 | 2027.9645
11 |  | 3BHK | 1282.8535 | 0 | 1988.423
12 |  | 3BHK | 1282.8535 | 0 | 1988.423
21th Floor (Part Refuge Area)
1 |  | 3BHK | 1282.8535 | 0 | 1988.423 | 21th Floor (Part Refuge Area)
2 |  | 3BHK | 1282.8535 | 0 | 1988.423
3 |  | 3BHK | 1308.3642 | 0 | 2027.9645
4 |  | 3BHK | 1308.3642 | 0 | 2027.9645
5 |  | Refuge Area
6
7
8
9 |  | 3BHK | 1308.3642 | 0 | 2027.9645
10 |  | 3BHK | 1308.3642 | 0 | 2027.9645
11 |  | 3BHK | 1282.8535 | 0 | 1988.423
12 |  | 3BHK | 1282.8535 | 0 | 1988.423
Remarks:
1 | Construction work is in process at the time of Visit. Internal photos was not allowed.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Chajja Area
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | As per Approved Floor plan, Building consist of 257 units For Residential ( Rehab = 109 units & Sale = 148 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
11 | We are not able to calculate 1st Floor area of Shop No. 10A because complete dimensions of shop is not provided in approved plans.
12 | As per Site Visit, Project is divided into 2 Wings i.e. East Wing & West Wing.
13 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below.
14 | We have updated C.C (on 22/06/2024).
15 | Recommended Rates/Other Charges of the Property have been revised on 15/02/2025.
16 | We have updated Part OC on 21/06/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Bharat Altavistas
Remark No. 10
Layout :
Remark No. 13
Google Map :
Formulas:
Oshiwara = [Oshiwara, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on D58: Sachin: If multiple building in project or complex just mention builtup of required building
Note on I137: VSJC: GROUND Floor
Note on I138: VSJC: GROUND Floor
Part I
Part II
Part II
Part I

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC