## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 07/06/2025
CPC Name: |  |  |  |  | Axis Kalina.
Date Of Property Visit |  |  |  |  | 2025-06-04
Name of the builder group |  |  |  |  | M/s. Chetna Global
Name of the builder company |  |  |  |  | M/s. Chetna Global
Name of the Project |  |  |  |  | Bhalla Chsl Jupiter - Venus
Contect Details ( Name & Contect No.) |  |  |  |  | 9870803582
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr Kishor 9892008878
Name / no of the Building |  |  |  |  | Jupiter = A Wing Venus = B Wing
Docouments Provided |  |  |  |  | Approved Plans, CC & Cost Sheet.
RERA Number |  |  |  |  | P51800000906
Project location details |  | Bhalla CHSL Jupiter - Venus, Plot No 1109/2A, 1109/2B, 1109/3, Lala Devidayal Road, Near Meghal Industrial Estate, Mulund west, Kurla, MSD Mumbai 400080
Plot No |  | 1109/2A, 1109/2B, 1109/3 |  |  | Locality |  | Mulund
Road |  | Lala Devidayal Road |  |  | District |  | Mumbai
City |  | Mulund West |  |  | Pin Code |  | 400080
Near by Landmark |  | Near Meghal Industrial Estate |  |  | Distance from city centre: |  | 1.9Km from Mulund Railway Station.
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Meghal Industrial Estate |  | KOKO Kmbaiids Play School |  | Lala Devidayal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.175542,72.944024
Location Link |  | https://goo.gl/maps/2FkHorE5ro5c88MC9
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 1616.7
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.53433
Total FSI availaible for the project |  |  |  |  | 1.5343
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 2480.55
Total number of Buildings |  |  |  |  | 01 Building (2 Wings)
Approval Detail : Plan approval
Layout Approval No |  | CHE/ES/1550/T/337(NEW) |  |  |  | Dated | 2019-10-03
Building plan approval No |  | CHE/ES/1550/T/337(NEW) |  |  |  | Dated | 2019-10-03
Date of Commencement of Construction Valid Up to: |  | CHE/ES/1550/T/337(NEW)/FCC/7/Amend |  |  |  | Dated | 2023-09-06
|  | Full C.C. is granted as per approved amended plan dated 18.08.2022 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  |  | Expiry date: | 2023-11-01
Part O. Certificate No.: CHE/ES/1550/T/337(NEW) The Part 1 development work of Resi+Comm building comprising of 2 Nos. Shops on Ground Floor of Wing A. | [5 empty] | Date of approval: | 03/10/2018.
Commencement date of construction |  |  | 2019-10-03 |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2480.55 |  | Approved no of units |  |  | Shop - 2 Flats = 36
Approved no of Floors |  | A Wing = G + 3 Podium + 4th to 16th floor. B Wing = G + 3 Podium + 4th to 8th floor.
Proposed no of Floors |  | A Wing = G + 3 Podium + 4th to 18th floor. B Wing = G + 3 Podium + 4th to 16th floor.
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion.
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: Jupiter (A Wing) = G + 3 Podium + 4th to 18th floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 18 Floor completed, Internal Plaster upto 18 Floor completed, External Plaster upto 18 Floor completed, Flooring upto 18 Floor completed, Painting upto 18 Floor completed, Finishing upto 7 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 18 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 18 Floor completed, Internal Plaster upto 18 Floor completed, External Plaster upto 18 Floor completed, Flooring upto 18 Floor completed, Painting upto 18 Floor completed, Finishing upto 7 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 18 | 100% |  | 91.94% |  | 95%
Plinth |  | 18 | 100%
RCC |  | 19 | 100% | [5 empty] | Excavation in process | 9
Brickwork | Brickwork & Internal Plaster | 18 | 100% | [5 empty] | Excavation Completed | 18
Internal Plaster | Brickwork & Internal Plaster | 18 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 100% | [5 empty] | Footing in Process | 4.5
Flooring & Fitting | Flooring & Fitting | 18 | 100% | [5 empty] | Footing Completed | 9
Painting & Wooden |  | 18 | 100% | [5 empty] | Plinth in process | 13.5
Building Common Amenities | Building Common Amenities | 7 | 38.89% | [5 empty] | Plinth completed | 18
Possession |  | 0 | 0%
Construction details: Venus (B Wing) = G + 3 Podium + 4th to 16th floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 17 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 14 Floor completed, External Plaster upto 13 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 16 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 17 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 14 Floor completed, External Plaster upto 13 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 16 | 100% |  | 72.19% |  | 88.44%
Plinth |  | 16 | 100%
RCC |  | 17 | 100% | [5 empty] | Excavation in process | 8
Brickwork | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Excavation Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 14 | 87.5%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 81.25% | [5 empty] | Footing in Process | 4
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed | 8
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process | 12
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 16
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) Including All other Charges | [5 empty] | 18000
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 22000/-
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 600000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 14400
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | RERA Carpet |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
A Wing
Ground Floor For Parking & Shops
1 |  | Shop | 598.1081 |  | 0 | 897.1622 | N | Ground
2 |  | Shop | 542.5056 |  | 0 | 813.7584 | N
1st to 3rd floor for Podium.
4th Floor.
1 |  | 3.5 BHK | 880.7105 |  | 0 | 1321.0657 | N | 4th Floor.
2 |  | 1 BHK | 481.0432 |  | 0 | 721.5647 | N
5th & 6th Floor.
1 |  | 3 BHK | 1037.219 |  | 0 | 1555.8286 | N | 5th & 6th Floor.
2 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
7th Floor.
1 |  | 4 BHK | 1281.2389 |  | 0 | 1921.8584 | N | 7th Floor.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
8th & 10th Floors.
1 |  | 4 BHK | 1281.2389 |  | 0 | 1921.8584 | N | 8th & 10th Floors.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
9th Floor (Part Refuge Area)
1 |  | 4 BHK | 1281.2389 |  | 0 | 1921.8584 | N | 9th Floor.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
11th Floor (Part Refuge Area)
1 |  | 4 BHK | 1281.2389 |  | 0 | 1921.8584 | N | 11th Floor.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
12th Floors.
1 |  | 4 BHK | 1281.2389 |  | 0 | 1921.8584 | N | 12th Floors.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
13th Floor (Part Refuge Area)
1 |  | 4 BHK | 1411.591 |  | 0 | 2117.3864 | N | 13th Floor.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
14th Floor.
1 |  | 4 BHK | 1411.591 |  | 0 | 2117.3864 | N | 14th Floor.
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
15th Floor (Part Refuge Area)
1 |  | 4 BHK | 1337.2117 |  | 0 | 2005.8176 | N | 15th Floor
2 |  | 2 BHK | 736.15 |  | 0 | 1104.2249 | N
16th Floor.
1 |  | 4 BHK | 1337.2117 |  | 0 | 2005.8176 | N | 16th Floor.
2 |  | 2 BHK | 762.8447 |  | 0 | 1144.267 | N
B Wing
Ground Floor For Parking
1st to 2nd floor for Podium.
3rd floor for Podium & Fitness Centre.
4th To 6th & 8th Floor.
1 |  | 3 BHK | 1037.219 |  | 0 | 1555.8286 | N | 4th To 6th & 8th Floor.
2 |  | 2 BHK | 690.8335 |  | 0 | 1036.2503 | N
7th Floor.
1 |  | 3 BHK | 1037.219 |  | 0 | 1555.8286 | N | 7th Floor.
2 |  | 2 BHK | 690.8335 |  | 0 | 1036.2503 | N
Remarks: 1. Jupiter (A Wing) = Finishing work is in process at the time of Visit. Venus (B Wing) = Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approve Plan. 4. We have considered rate by verifying it from market inquire. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 6. We considered construction percentage as per proposed no of Floors (A Wing = G + 3 Podium + 18th floor & B Wing = G + 3 Podium + 16th floor.) 7. We update revised Approved plans & CC (on 18/10/2020). 8. We have updated latest C.C (on 22/03/2024). 9. Please provide revised approved plans, As the construction work goes beyond the approved plans. 10. As per RERA, completion period of project is expired on 31/12/2024, but still project is under construction. 9. On site, we meet Mr.Kishor - 9892008878.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Bhalla Chsl Jupiter - Venus
Google Map :
Formulas:
Mulund = [Mulund, row above]
Venus
Jupiter

## A%
Particulars | totaL floor | 18
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 84.2105 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 19 | 16 | 77.7778 | Progress |  |  | 10 | 33.6842 | 11.6667 | 6.1111 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 61.1111 | Recommended |  |  | 30 | 25.2632 | 11.6667 | 6.1111 | 0 | 0 | 0
| 18 | 14 | 0
plaster | Total Floor | completed Floor | 0
| 18 | 11 | 0
Flooring | Total Floor | completed Floor
| 18 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 18 | 0 |  | RCC | 33.6842 | 25.2632
Finishing | Total Floor | completed Floor |  | Bricks | 11.6667 | 11.6667
| 18 | 0 |  | Plaster | 6.1111 | 6.1111
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 61.462 | 73.0409

## B % (2)
Particulars | totaL floor | 16
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 52.9412 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 17 | 9 | 43.75 | Progress |  |  | 10 | 21.1765 | 6.5625 | 4.375 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 43.75 | Recommended |  |  | 30 | 15.8824 | 6.5625 | 4.375 | 0 | 0 | 0
| 16 | 7 | 0
plaster | Total Floor | completed Floor | 0
| 16 | 7 | 0
Flooring | Total Floor | completed Floor
| 16 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 16 | 0 |  | RCC | 21.1765 | 15.8824
Finishing | Total Floor | completed Floor |  | Bricks | 6.5625 | 6.5625
| 16 | 0 |  | Plaster | 4.375 | 4.375
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 42.114 | 56.8199

## A1
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 5.3 | 3.05 | 16.165 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.3 | 2.75 | 6.325 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.5 | 3.5 | 12.25 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.35 | 2.45 | 3.3075 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.45 | 1.2 | 2.94 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.2 | 2.55 | 3.06 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 474.1273 | 44.0475 |  |  | 0 | 0 |  | 0 | 0
474.1273

## A2
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 8.46 | 3.25 | 27.495 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.3 | 2.45 | 5.635 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.2 | 2.3 | 7.36 | CB |  |  | 0 |  |  | 0
|  | 1.55 | 2.3 | 3.565 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.5 | 3.55 | 12.425 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.5 | 3.25 | 11.375 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.45 | 1.3 | 3.185 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.5 | 2.45 | 3.675 | DB |  |  | 0 |  |  | 0
| toilet3 | 1.2 | 2.45 | 2.94 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 6.75 | 1 | 6.75 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 908.5354 | 84.405 |  |  | 0 | 0 |  | 0 | 0
908.5354

## A51
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 5.3 | 3.6 | 19.08 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.3 | 2.75 | 6.325 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.5 | 3.35 | 11.725 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.5 | 4.3 | 15.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.35 | 2.45 | 3.3075 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.55 | 1.2 | 3.06 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 630.2053 | 58.5475 |  |  | 0 | 0 |  | 0 | 0

## Valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Common Floor | Bhalla CHSL Jupiter Venus | 1BHK | 690 | 1104 | 16213.7681 | 17900000
Common Floor | Bhalla CHSL Jupiter Venus | 4BHK | 1412 | 2259.2 | 16023.3711 | 36200000
Common Floor | Bhalla CHSL Jupiter Venus | 3BHK | 1037 | 1659.2 | 16875.6027 | 28000000
Common Floor | Bhalla CHSL Jupiter Venus | 4BHK | 1281 | 2049.6 | 16930.1327 | 34700000
Common Floor | Bhalla CHSL Jupiter Venus | 2BHk | 736 | 1177.6 | 16813.8587 | 19800000
Proptiger | Bhalla CHSL Jupiter Venus | 2BHk | 736 | 1177.6 | 16813.8587 | 19800000
Quiker | Bhalla CHSL Jupiter Venus | 2BHk | 736 | 1177.6 | 16813.8587 | 19800000
Quiker | Bhalla CHSL Jupiter Venus | 1BHK | 690 | 1104 | 16213.7681 | 17900000
Average |  |  |  |  | 16587.2774
Valuation Adopted |  |  |  |  | 18000

## Note
01/10/2020. | 1. Rate is Changed.
Before it was = 18000/-sq.ft & Now it is given as 15900/-sq.ft