## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | M/s. Bhaveshwar Infratech
Name of the builder company |  |  |  | M/s. Bhaveshwar Infratech
Name of the Project |  |  |  | Bhaveshwar Aqua 2
Contact Details ( Name & Contact No.) |  |  |  | 9867061436
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Vinod 9137971199
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000045696
Project location details |  | Bhaveshwar Aqua 2, Plot No..C - 7/2, Sector - 12, near Kalamboli Pond (Visharjan Talav), Shiv Mandir Road, Kalamboli, Kalamboli, Navi Mumbai, Panvel, Raigad - 410206.
Plot No. |  | C - 7/2, Sector - 12
Locality |  | Kalamboli
Road |  | Shiv Mandir Road |  | Village |  | Kalamboli
City |  | Navi Mumbai |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Kalamboli Pond (Visharjan Talav) |  | Distance from city centre: |  | 3.6KM from Mansarovar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Sewage Treatment Plant
West | NA | NA |  |  | Shiv Mandir Rd
North | NA | NA |  |  | Kalamboli Pond (Visharjan Talav)
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.0347433,73.0951646
Location Link |  | https://goo.gl/maps/Cp1pegjsj7VJh8iv9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3893.48
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.7241
Total FSI availaible for the project |  |  |  | 3.2241
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12553.056
Total number of Buildings |  |  |  | 2 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Muncipal Corporation
Layout Approval No |  | PMP/NRV/16351/JK2847/2022 |  |  | Dated | 2022-12-05
Approved Floor plan No. |  | PMP/NRV/16351/JK2847/2022 |  |  | Dated | 2022-12-05
Commencement-CC No Valid Up to: |  | PMC/TP/Kalamboli/12/C-7/2/21-22/16351/2847/2022 |  |  | Dated | 2022-12-05
Wing - A = G + 1st to 11th Floor Wing - B = G + 1st to 10th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 12553.056
Approved no of units |  |  | Flats - 204, Shops -12, Offices -2
Approved no of Floors |  |  | Wing A = G + 1st to 11th Floor Wing B = G + 1st to 10th Floor
Proposed no of Floors |  |  | Wing A = G + 1st to 15th Floor
Wing B = G + 1st to 15th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = G + 1st to 15th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor Completed | , RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 48.83% |  | 72.63% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 11 | 68.75% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 8 | 53.33% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 8 | 53.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 33.33% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Wing B = G + 1st to 15th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 9 Floor, External Plaster upto 9 Floor, Flooring upto 2 Floor Completed | , RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 9 Floor, External Plaster upto 9 Floor, Flooring upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 9 Floor, External Plaster upto 9 Floor, Flooring upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 53.83% |  | 75.29% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 11 | 68.75% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 9 | 60% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 60% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 60% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 13.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6650 |  |  | 4783600 | 22/09/2022 - flat rate change - 6500 to 6650 - by palas sir
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 12000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 8000
Floor Rise Rate
Water, Electricity, Development Charges |  |  |  |  | 350000
Club Charges |  |  |  |  | 200000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 100000
Advance Maintenance Charges |  |  |  |  | 50000
Recommended rate of Parking |  |  |  |  | 450000
Distressed valuation of the Property |  |  |  |  | 5320
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shop | 12 |  | 4339.033 |  | 6942.4528
| Office | 2 |  | 5892.3212 |  | 9427.714
Total |  | 14 |  | 10231.3542 |  | 16370.1668
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 66 |  | 39125.0356 |  | 69480
Wing B |  | 138 |  | 58738.5237 |  | 101540
Total |  | 204 |  | 97863.5593 |  | 171020
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
A Wing
Ground Floor For Commercial
1 |  | Shop | 356.6974 | 0 | 570.7159 | Ground Floor For Commercial |  | 33.1375
2 |  | Shop | 356.6974 | 0 | 570.7159
3 |  | Shop | 356.6974 | 0 | 570.7159
4 |  | Shop | 342.0046 | 0 | 547.2073 |  |  | 10.764
5 |  | Shop | 311.7039 | 0 | 498.7263
6 |  | Shop | 367.8597 | 0 | 588.5755
7 |  | Shop | 444.4348 | 0 | 711.0957
8 |  | Shop | 376.148 | 0 | 601.8368
9 |  | Shop | 356.6974 | 0 | 570.7159
10 |  | Shop | 356.6974 | 0 | 570.7159
11 |  | Shop | 356.6974 | 0 | 570.7159
12 |  | Shop | 356.6974 | 0 | 570.7159
1st Floor For Commercial
1 |  | Office | 2609.1936 | 0 | 4174.7098 | 1st Floor For Commercial
2 |  | Office | 3283.1276 | 0 | 5253.0042 | 1st Floor For Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
A Wing
2nd Floor for Residential
1 |  | 1BHK | 340.0778 | 359.2765 | 985 | 2nd Floor for Residential |  | 40.7659 | 4060.9137
2 |  | 2BHK | 541.7618 | 321.7467 | 1330 | 2nd Floor for Residential
3 |  | 2BHK | 575.1582 | 140.1042 | 1225 | 2nd Floor for Residential
4 |  | 2BHK | 575.1528 | 140.1042 | 1225 | 2nd Floor for Residential
5 |  | 2BHK | 541.7521 | 327.3009 | 1330 | 2nd Floor for Residential
6 |  | 2BHK | 532.5381 | 215.7418 | 1125 | 2nd Floor for Residential |  | 28.6135
7 |  | 2BHK | 530.719 | 42.8192 | 1025 | 2nd Floor for Residential
3rd to 6th Floor
1 |  | 1BHK | 379.5548 | 0 | 705 | 3rd to 6th Floor |  | 40.7659 | 5673.7589
2 |  | 2BHK | 645.769 | 0 | 1110 | 3rd to 6th Floor
3 |  | 2BHK | 674.8867 | 0 | 1155 | 3rd to 6th Floor
4 |  | 2BHK | 674.8813 | 0 | 1155 | 3rd to 6th Floor |  |  |  | 0
5 |  | 2BHK | 645.7593 | 0 | 1110 | 3rd to 6th Floor
6 |  | 2BHK | 556.0844 | 0 | 955 | 3rd to 6th Floor |  | 28.6135
7 |  | 2BHK | 554.2653 | 0 | 955 | 3rd to 6th Floor |  |  | 6806.2827
7th & 9th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th & 9th Floor (Part Refuge Area) |  | 40.7659 | #DIV/0!
2 |  | 2BHK | 645.769 | 0 | 1110 | 7th & 9th Floor (Part Refuge Area)
3 |  | 2BHK | 674.8867 | 0 | 1155 | 7th & 9th Floor (Part Refuge Area)
4 |  | 2BHK | 674.8813 | 0 | 1155 | 7th & 9th Floor (Part Refuge Area) |  |  |  | 0
5 |  | 2BHK | 645.7593 | 0 | 1110 | 7th & 9th Floor (Part Refuge Area)
6 |  | 2BHK | 556.0844 | 0 | 955 | 7th & 9th Floor (Part Refuge Area) |  | 28.6135
7 |  | 2BHK | 554.2653 | 0 | 955 | 7th & 9th Floor (Part Refuge Area) |  |  | 6806.2827
8th & 10th Floor
1 |  | 1BHK | 379.5548 | 0 | 705 | 8th & 10th Floor |  | 40.7659 | 5673.7589
2 |  | 2BHK | 645.769 | 0 | 1110 | 8th & 10th Floor
3 |  | 2BHK | 674.8867 | 0 | 1155 | 8th & 10th Floor
4 |  | 2BHK | 674.8813 | 0 | 1155 | 8th & 10th Floor |  |  |  | 0
5 |  | 2BHK | 645.7593 | 0 | 1110 | 8th & 10th Floor
6 |  | 2BHK | 556.0844 | 0 | 955 | 8th & 10th Floor |  | 28.6135
7 |  | 2BHK | 554.2653 | 0 | 955 | 8th & 10th Floor |  |  | 6806.2827
11th Floor (Part Refuge Area & Terrace Area)
1 |  | Refuge Area |  |  |  | 11th Floor (Part Refuge Area & Terrace Area) |  | 40.7659 | #DIV/0!
2 |  | 2BHK | 645.769 | 0 | 1110 | 11th Floor (Part Refuge Area & Terrace Area)
3 |  | 2BHK | 674.8867 | 0 | 1155 | 11th Floor (Part Refuge Area & Terrace Area)
4 |  | 2BHK | 674.8813 | 0 | 1155 | 11th Floor (Part Refuge Area & Terrace Area) |  |  |  | 0
5 |  | 2BHK | 645.7593 | 0 | 1110 | 11th Floor (Part Refuge Area & Terrace Area)
6 |  | 2BHK | 556.0844 | 0 | 955 | 11th Floor (Part Refuge Area & Terrace Area) |  | 28.6135
7 |  | Terrace Area |  |  |  | 11th Floor (Part Refuge Area & Terrace Area) |  |  | #DIV/0!
B Wing
Ground Floor For Parking
1st Floor for Residential
1 |  | 2BHK | 556.0844 | 0 | 955 | 1st Floor for Residential |  | 40.7659
2 |  | 2BHK | 556.0844 | 0 | 955 | 1st Floor for Residential
3 |  | 1BHK | 405.2646 | 0 | 690 | 1st Floor for Residential
4 |  | 1BHK | 397.5899 | 0 | 680 | 1st Floor for Residential
5 |  | 1BHK | 397.5899 | 0 | 680 | 1st Floor for Residential
6 |  | 1BHK | 418.4505 | 0 | 710 | 1st Floor for Residential |  | 28.6135
7 |  | 1BHK | 401.7017 | 0 | 690 | 1st Floor for Residential
8 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
9 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
10 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
11 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
12 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
13 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
14 |  | 1BHK | 403.101 | 0 | 705 | 1st Floor for Residential
2nd Floor
1 |  | 2BHK | 556.0844 | 0 | 955 | 2nd Floor |  | 40.7659
2 |  | 2BHK | 556.0844 | 0 | 955 | 2nd Floor
3 |  | 1BHK | 405.2646 | 0 | 690 | 2nd Floor
4 |  | 1BHK | 397.5899 | 0 | 680 | 2nd Floor
5 |  | 1BHK | 397.5899 | 0 | 680 | 2nd Floor
6 |  | 1BHK | 418.4505 | 0 | 710 | 2nd Floor |  | 28.6135
7 |  | 1BHK | 401.7017 | 0 | 690 | 2nd Floor
8 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
9 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
10 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
11 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
12 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
13 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
14 |  | 1BHK | 403.101 | 0 | 705 | 2nd Floor
3rd to 6th Floor
1 |  | 2BHK | 556.0844 | 0 | 955 | 3rd to 6th Floor |  | 40.7659
2 |  | 2BHK | 556.0844 | 0 | 955 | 3rd to 6th Floor
3 |  | 1BHK | 405.2646 | 0 | 690 | 3rd to 6th Floor
4 |  | 1BHK | 397.5899 | 0 | 680 | 3rd to 6th Floor
5 |  | 1BHK | 397.5899 | 0 | 680 | 3rd to 6th Floor
6 |  | 1BHK | 418.4505 | 0 | 710 | 3rd to 6th Floor |  | 28.6135
7 |  | 1BHK | 401.7017 | 0 | 690 | 3rd to 6th Floor
8 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
9 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
10 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
11 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
12 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
13 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
14 |  | 1BHK | 403.101 | 0 | 705 | 3rd to 6th Floor
7th & 9th Floor (Part Refuge Area)
1 |  | 2BHK | 556.0844 | 0 | 955 | 7th & 9th Floor (Part Refuge Area) |  | 40.7659
2 |  | 2BHK | 556.0844 | 0 | 955 | 7th & 9th Floor (Part Refuge Area)
3 |  | 1BHK | 405.2646 | 0 | 690 | 7th & 9th Floor (Part Refuge Area)
4 |  | 1BHK | 397.5899 | 0 | 680 | 7th & 9th Floor (Part Refuge Area)
5 |  | 1BHK | 397.5899 | 0 | 680 | 7th & 9th Floor (Part Refuge Area)
6 |  | 1BHK | 418.4505 | 0 | 710 | 7th & 9th Floor (Part Refuge Area) |  | 28.6135
7 |  | 1BHK | 401.7017 | 0 | 690 | 7th & 9th Floor (Part Refuge Area)
8 |  | 1BHK | 403.101 | 0 | 705 | 7th & 9th Floor (Part Refuge Area)
9 |  | 1BHK | 403.101 | 0 | 705 | 7th & 9th Floor (Part Refuge Area)
10 |  | 1BHK | 403.101 | 0 | 705 | 7th & 9th Floor (Part Refuge Area)
11 |  | Refuge Area |  |  |  | 7th & 9th Floor (Part Refuge Area)
12 |  | 1BHK | 403.101 | 0 | 705 | 7th & 9th Floor (Part Refuge Area)
13 |  | 1BHK | 403.101 | 0 | 705 | 7th & 9th Floor (Part Refuge Area)
14 |  | 1BHK | 403.101 | 0 | 705 | 7th & 9th Floor (Part Refuge Area)
8th & 10th Floor
1 |  | 2BHK | 556.0844 | 0 | 955 | 8th & 10th Floor |  | 40.7659
2 |  | 2BHK | 556.0844 | 0 | 955 | 8th & 10th Floor
3 |  | 1BHK | 405.2646 | 0 | 690 | 8th & 10th Floor
4 |  | 1BHK | 397.5899 | 0 | 680 | 8th & 10th Floor
5 |  | 1BHK | 397.5899 | 0 | 680 | 8th & 10th Floor
6 |  | 1BHK | 418.4505 | 0 | 710 | 8th & 10th Floor |  | 28.6135
7 |  | 1BHK | 401.7017 | 0 | 690 | 8th & 10th Floor
8 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
9 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
10 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
11 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
12 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
13 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
14 |  | 1BHK | 403.101 | 0 | 705 | 8th & 10th Floor
Remarks:
* | Wing A = Construction work is the same as last visit. (dtd.06/06/2025) (Waiting for revised CC) Wing B = Construction work is the same as last visit (dtd.08/03/2025), but work is in process at the time of the visit. (Slow Speed)
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On East side there is sewage tratment plant There is a road on the west side of the project, and a creek is next to the other side of the road. On north side there is kalamboli pond On south side there is Nala
* | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project.
* | On Site, we meet Miss. Bhavna (9892638736)
* | We have updated revised approved plans & CC (on 15/12/2022).
* | Please provide revised approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Bhaveshwar Aqua 2
Google Map :
A
B
A
B
Nala
Sewage treatment plant
All Religion Cementry
Creek
Bhaveshwar Aqua 2
Wing A
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted