## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Palak Developers
Name of the builder company |  |  |  | Palak Developers
Name of the Project |  |  |  | Florence Landmark Phase 1
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Vaibhav 9922550640
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Kiran 7208010790
Name / No of the Building |  |  |  | Building 1 (Wing A, B & C)
Name / No of the Existing Building |  |  |  | NA | [9 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC cum NA Order, Builder Saleable Area & Cost Sheet. | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000051375 |  |  |  | #N/A | [5 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Florence Landmark Phase 1, Survey No.71 H. No.1/B/1, near Sunrise Residency, Neral Badlapur Road, Damat, Damat, Shelu West, Karjat, Raigad - 410101. | [11 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 71 H. No.1/B/1 | [11 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Damat | [11 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Neral Badlapur Road |  | Locality/Village |  | Damat | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Shelu West |  | District |  | Raigad | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Karjat |  | Pin Code |  | 410101 | [10 empty] | Mahad | Daund
Nearby Landmark |  | Sunrise Residency |  | Distance from city centre: |  | 1.80KM from Shelu Railway Station | [10 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [12 empty] | Mangaon | Ambegaon
[17 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [12 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [12 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [12 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | S. No. 71 & 72 |  |  | Open Plot
West | NA | State Highway No. 76 |  |  | Neral Badlapur Road
North | NA | S. No. 70 |  |  | River/Open Plot
South | NA | Other Plot |  |  | Sunrise Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.050695,73.315103
Location Link |  | https://maps.app.goo.gl/7Z3WjS3pH4yYKe8u6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 8352.13
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.71218
Total FSI availaible for the project |  |  |  | 1.8122
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 15135.57 |  |  |  | Building + open space | 14993.5 | only Building
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector Of Raigad, Alibag
Layout Approval No |  | MS/LNA-1/S.R./TokanNo.15818/ P.K.144/2021 |  |  | Dated | 2022-10-18
Approved Floor plan No. |  | MS/LNA-1/S.R./TokanNo.15818/ P.K.144/2021 |  |  | Dated | 2022-10-18
NA Order No |  | MS/L.N.A.1/A-1(B)/Token No.15818/ P.K.144/2021 |  |  | Dated | 2022-10-18
Valid Up to: |  | Building 1 Wing A, B & C = 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9357.55
Approved no of units |  |  | Flats - 161, Shops - 24, Offices - 24
Approved no of Floors |  |  | Building 1 (Wing A, B & C) = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building 1 (Wing A, B & C) = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Kids' Play Areas, Jogging / Cycle Track, Power Backup Treated, Club House, Indoor Games, Parking, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building 1 (Wing A) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | , Internal Plaster upto 3 Floor, External Plaster upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 62.14% |  | 82.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 42.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building 1 (Wing B) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 3 Floor Completed | , RCC upto 7 Slab, Brickwork upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 48.21% |  | 73.39% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 7 | 87.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 3 | 42.86% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building 1 (Wing C) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 3 Floor, Internal Plaster upto 1 Floor Completed | , RCC upto 7 Slab, Brickwork upto 3 Floor, Internal Plaster upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 3 Floor, Internal Plaster upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 49.29% |  | 74.11% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 7 | 87.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 3 | 42.86% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 1 | 14.29% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 5500
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 4500
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 150000
Club Charges |  |  |  |  | 25000 |  |  | 210000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges (24 Months) |  |  |  |  | 35000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2400
Commercial Area Details (Shops) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building 1 | Wing A | 4 |  | 810.7445 |  | 2320
| Wing B | 12 |  | 2477.7652 |  | 7055
| Wing C | 8 |  | 1901.1377 |  | 5405
Total |  | 24 |  | 5189.6473 |  | 14780
Commercial Area Details (Offices) :
Building 1 | Wing A | 4 |  | 1662.3922 |  | 3630
| Wing B | 12 |  | 5029.5866 |  | 10920
| Wing C | 8 |  | 3215.4221 |  | 7000
Total |  | 24 |  | 9907.4009 |  | 21550
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building 1 | Wing A | 54 |  | 20426.5199 |  | 32275
| Wing B | 53 |  | 17404.7422 |  | 28415
| Wing C | 54 |  | 20613.5982 |  | 32345
Total |  | 161 |  | 58444.8602 |  | 93035
Grand Total |  | 209 |  | 73541.9084 |  | 129365
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Building No. 1
Wing A
Ground Floor For Commercial, Entrance Lobby & Parking
1 |  | Shop | 193.2138 | 64.3687 | 555 | Ground Floor For Commercial, Entrance Lobby & Parking |  | 17.955 | 555 |  | 12960
2 |  | Shop | 213.5578 | 71.2577 | 610 |  |  | 19.845 | 610 |  | 12747.541
3 |  | Shop | 217.5404 | 72.5494 | 620 |  |  | 20.2125 | 620
4 |  | Shop | 186.4325 | 62.1083 | 535 |  |  | 17.325 | 535
1st Floor For Part Commercial
101 |  | Office | 416.9974 | 0 | 910 | 1st Floor For Part Commercial |  |  | 910
102 |  | Office | 414.1987 | 0 | 905 |  |  |  | 905
2nd Floor For Part Commercial
201 |  | Office | 416.9974 | 0 | 910 | 2nd Floor For Part Commercial
202 |  | Office | 414.1987 | 0 | 905
Wing B
Ground Floor For Commercial, Entrance Lobby & Parking
5 |  | Shop | 168.4566 | 56.1881 | 480 | Ground Floor For Commercial, Entrance Lobby & Parking |  |  |  | 2.5159
6 |  | Shop | 217.5404 | 72.5494 | 620 |  |  |  |  | 2.5165
7 |  | Shop | 275.2355 | 91.7093 | 775 |  |  | 25.575 | 91.7631 | 2.4826
8 |  | Shop | 213.2348 | 71.0424 | 600 |  |  |  |  | 2.4806
9 |  | Shop | 186.4325 | 62.1083 | 535 |  |  |  |  | 2.5365
10 |  | Shop | 217.5404 | 72.5494 | 620 |  |  |  |  | 2.5165
11 |  | Shop | 168.4566 | 56.1881 | 480 |  |  |  |  | 2.5159
12 |  | Shop | 186.4325 | 62.2159 | 535 |  |  |  |  | 2.536
13 |  | Shop | 272.0063 | 91.7093 | 775 |  |  |  |  | 2.512
14 |  | Shop | 217.5404 | 72.5494 | 620 |  |  |  |  | 2.5165
15 |  | Shop | 168.4566 | 56.1881 | 480 |  |  |  |  | 2.5159
16 |  | Shop | 186.4325 | 62.2159 | 535 |  |  |  |  | 2.536
1st Floor For Part Commercial
103 |  | Office | 461.2374 | 0 | 990 | 1st Floor For Part Commercial
104 |  | Office | 397.9451 | 0 | 865
105 |  | Office | 414.1987 | 0 | 905
106 |  | Office | 365.2225 | 0 | 800
107 |  | Office | 510.9671 | 0 | 1100
108 |  | Office | 365.2225 | 0 | 800
2nd Floor For Part Commercial
203 |  | Office | 461.2374 | 0 | 990 | 2nd Floor For Part Commercial
204 |  | Office | 397.9451 | 0 | 865
205 |  | Office | 414.1987 | 0 | 905
206 |  | Office | 365.2225 | 0 | 800
207 |  | Office | 510.9671 | 0 | 1100
208 |  | Office | 365.2225 | 0 | 800
Wing C
Ground Floor For Commercial, Entrance Lobby & Parking
17 |  | Shop | 217.5404 | 72.5494 | 620 | Ground Floor For Commercial, Entrance Lobby & Parking
18 |  | Shop | 213.5578 | 71.15 | 610
19 |  | Shop | 193.2138 | 64.3687 | 555 |  |  | 17.955
20 |  | Shop | 285.7842 | 95.2614 | 805
21 |  | Shop | 285.7842 | 95.2614 | 805
22 |  | Shop | 285.7842 | 95.2614 | 805
23 |  | Shop | 285.7842 | 95.2614 | 805
24 |  | Shop | 133.6889 | 44.563 | 400 |  |  | 12.42
1st Floor For Part Commercial
109 |  | Office | 443.0462 | 0 | 960 | 1st Floor For Part Commercial
110 |  | Office | 440.7858 | 0 | 965
111 |  | Office | 486.5328 | 0 | 1055
112 |  | Office | 237.3462 | 0 | 520
2nd Floor For Part Commercial
209 |  | Office | 443.0462 | 0 | 960 | 2nd Floor For Part Commercial
210 |  | Office | 440.7858 | 0 | 965
211 |  | Office | 486.5328 | 0 | 1055
212 |  | Office | 237.3462 | 0 | 520
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building 1
Wing A
1st Floor For Part Residential
101 |  | 1BHK | 358.7641 | 0 | 555 | 1st Floor For Part Residential |  | 33.33 | 26.13 | 7.63 | 33.76 | 555 | 1.547
102 |  | 1BHK | 358.7641 | 0 | 555 | [6 empty] | 555 | 1.547
103 |  | 1BHK | 356.2884 | 0 | 545 | [6 empty] | 545 | 1.5297
104 |  | 1BHK | 355.5349 | 0 | 545 |  |  | 28.55 | 4.88 |  |  | 545 | 1.5329
105 |  | 2BHK | 447.89 | 0 | 710 |  |  | 38.22 | 2.75 |  |  | 710 | 1.5852
106 |  | 1BHK | 358.7641 | 0 | 555 | [6 empty] | 555 | 1.547
107 |  | 1BHK | 358.7641 | 0 | 555 |  |  | 25.95 | 7.63 |  |  | 555 | 1.547
2nd Floor For Part Residential
201 |  | 1BHK | 358.7641 | 0 | 555 | 2nd Floor For Part Residential |  |  |  | 1.547 | 1776000 | 1976000
202 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547 | 1776000 | 1976000
203 |  | 1BHK | 356.2884 | 0 | 560 |  |  |  |  | 1.5718 | 1792000 | 2002000
204 |  | 1BHK | 355.5349 | 0 | 560 |  |  |  |  | 1.5751 | 1792000 | 1992000
205 |  | 2BHK | 447.89 | 0 | 710 |  |  |  |  | 1.5852 | 2272000 | 2472000
206 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547 | 1776000 | 1976000
207 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547 | 1776000 | 1976000
3rd Floor
301 |  | 2BHK | 418.289 | 276.3119 | 940 | 3rd Floor |  | 39.48 |  | 2.2472
302 |  | 1BHK | 358.7641 | 0 | 555 |  |  | 25.95 | 7.63 | 1.547
303 |  | 1BHK | 358.7641 | 0 | 555 |  |  | 25.95 | 7.63 | 1.547
304 |  | 1BHK | 361.1322 | 0 | 560 |  |  | 26.17 | 7.63 | 1.5507 | 3456
305 |  | 1BHK | 385.0283 | 0 | 595 |  |  | 28.55 | 7.63 | 1.5453
306 |  | 2BHK | 447.89 | 0 | 710 |  |  | 38.22 | 2.75 | 1.5852 | 3456
307 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 7.63 | 1.547
308 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 7.63 | 1.547
4th to 7th Floor | [9 empty] | #DIV/0!
401 to 701 |  | 2BHK | 418.289 | 0 | 710 | 4th to 7th Floor |  | 38.22 |  | 1.6974
402 to 702 |  | 1BHK | 358.7641 | 0 | 555 |  |  | 25.95 |  | 1.547
403 to 703 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547
404 to 704 |  | 1BHK | 361.1322 | 0 | 560 |  |  |  |  | 1.5507
405 to 705 |  | 1BHK | 385.0283 | 0 | 595 |  |  |  |  | 1.5453
406 to 706 |  | 2BHK | 447.89 | 0 | 710 |  |  |  |  | 1.5852
407 to 707 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547
408 to 708 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547
Wing B | [9 empty] | #DIV/0!
1st Floor For Part Residential | [9 empty] | #DIV/0!
101 |  | 1BHK | 361.1322 | 0 | 555 | 1st Floor For Part Residential |  | 20.21 | 2.75 | 1.5368
102 |  | 1RK | 251.9852 | 0 | 390 |  |  |  |  | 1.5477
103 |  | 1RK | 251.9852 | 0 | 390 |  |  |  |  | 1.5477
104 |  | 1BHK | 361.1322 | 0 | 555 |  |  |  |  | 1.5368
2nd Floor For Part Residential | [9 empty] | #DIV/0!
201 |  | 1BHK | 361.1322 | 0 | 560 | 2nd Floor For Part Residential |  |  |  | 1.5507
202 |  | 1RK | 251.9852 | 0 | 390 |  |  |  |  | 1.5477
203 |  | 1RK | 251.9852 | 0 | 390 |  |  |  |  | 1.5477
204 |  | 1BHK | 361.1322 | 0 | 560 |  |  |  |  | 1.5507
3rd Floor | [9 empty] | #DIV/0!
301 |  | 1BHK | 361.1322 | 0 | 555 | 3rd Floor |  |  |  | 1.5368
302 |  | 1RK | 251.9852 | 0 | 390 |  |  |  |  | 1.5477
303 |  | 1BHK | 329.1631 | 311.9945 | 810 |  |  |  |  | 2.4608 | 2.2238
304 |  | 1BHK | 329.1631 | 311.9945 | 810 |  |  |  |  | 2.4608
305 |  | 1BHK | 329.1631 | 311.9945 | 810 |  |  | 25.95 | 4.88 | 2.4608
306 |  | 1BHK | 329.1631 | 311.9945 | 810 |  |  |  |  | 2.4608
307 |  | 1BHK | 329.1631 | 311.9945 | 810 |  |  |  |  | 2.4608
308 |  | 1RK | 251.9852 | 0 | 390 |  |  |  |  | 1.5477
309 |  | 1BHK | 361.1322 | 0 | 560 |  |  |  |  | 1.5507
4th to 7th Floor | [9 empty] | #DIV/0!
401 to 701 |  | 1BHK | 361.1322 | 0 | 555 | 4th to 7th Floor |  |  | 1.5368 | 1.5368
402 to 702 |  | 1RK | 251.9852 | 0 | 390 |  |  |  | 1.5477 | 1.5477
403 to 703 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
404 to 704 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
405 to 705 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
406 to 706 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
407 to 707 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
408 to 708 |  | 1RK | 251.9852 | 0 | 390 |  |  |  | 1.5477 | 1.5477
409 to 709 |  | 1BHK | 361.1322 | 0 | 560 |  |  |  | 1.5507 | 1.5507
Wing C | [9 empty] | #DIV/0!
1st Floor For Part Residential | [9 empty] | #DIV/0!
101 |  | 1BHK | 358.7641 | 0 | 555 | 1st Floor For Part Residential |  |  |  | 1.547
102 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547
103 |  | 2BHK | 447.89 | 0 | 710 |  |  | 7.98 |  | 1.5852
104 |  | 1BHK | 385.0283 | 0 | 595 |  |  | 28.55 | 7.63 | 1.5453
105 |  | 1BHK | 361.1322 | 0 | 555 |  |  |  |  | 1.5368
106 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547
107 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  |  | 1.547
2nd Floor For Part Residential | [9 empty] | #DIV/0!
201 |  | 1BHK | 358.7641 | 0 | 555 | 2nd Floor For Part Residential |  |  | 1.547 | 1.547
202 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
203 |  | 2BHK | 447.89 | 0 | 710 |  |  |  | 1.5852 | 1.5852
204 |  | 1BHK | 385.0283 | 0 | 595 |  |  |  | 1.5453 | 1.5453
205 |  | 1BHK | 361.1322 | 0 | 560 |  |  |  | 1.5507 | 1.5507
206 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
207 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
3rd Floor | [9 empty] | #DIV/0!
301 |  | 1BHK | 358.7641 | 0 | 555 | 3rd Floor |  |  | 1.547 | 1.547
302 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
303 |  | 2BHK | 447.89 | 0 | 710 |  |  |  | 1.5852 | 1.5852
304 |  | 1BHK | 385.0283 | 0 | 595 |  |  |  | 1.5453 | 1.5453
305 |  | 1BHK | 361.1322 | 0 | 555 |  |  |  | 1.5368 | 1.5368
306 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
307 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
308 |  | 1BHK | 418.289 | 276.3119 | 940 |  |  |  | 2.2472 | 2.2472
4th to 7th Floor | [9 empty] | #DIV/0!
401 to 701 |  | 1BHK | 358.7641 | 0 | 555 | 4th to 7th Floor |  |  | 1.547 | 1.547
402 to 702 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
403 to 703 |  | 2BHK | 447.89 | 0 | 710 |  |  |  | 1.5852 | 1.5852
404 to 704 |  | 1BHK | 385.0283 | 0 | 595 |  |  |  | 1.5453 | 1.5453
405 to 705 |  | 1BHK | 361.1322 | 0 | 555 |  |  |  | 1.5368 | 1.5368
406 to 706 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
407 to 707 |  | 1BHK | 358.7641 | 0 | 555 |  |  |  | 1.547 | 1.547
408 to 708 |  | 1BHK | 447.89 | 0 | 710 |  |  |  | 1.5852 | 1.5852
Remarks:
* | Construction work is in process at the time of Visit. (Slow Speed)
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Lovanshi |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Florence Landmark Phase 1
Layout :
Google Map :
Formulas:
Damat = [Damat, row above]
WING C
WING A
WING C
WING B
Building 1 (Wing A, B & C)
WING B
A Wing
A Wing
C Wing
B Wing
A Wing
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC