## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-10
Name of the builder group |  |  |  | Vl Savli Developers LLP
Name of the builder company |  |  |  | Vl Savli Developers LLP
Name of the Project |  |  |  | Eastern Groves Phase 1A, 1B & 2
Contact Details ( Name & Contact No.) |  |  |  | 8104714579
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Nitin site engineer 7666574735
Name / No of the Building |  |  |  | Eastern Groves Phase 1A = (Wing E & F) Eastern Groves Phase 1B = (Wing C & D) Eastern Groves Phase 2 = (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No & RERA Name |  |  |  | P51800028005 = Eastern Groves Phase 1A P51800028289 = Eastern Groves Phase 1B P51800051916 = Eastern Groves Phase 2
Project location details |  | Proposed Redevelopment of Existing Building No 156, 161, 162 & 163 On Plot Bearing C.T.S No. 356 (Pt) At Kannamwar Nagar, Vikroli (East), Mumbai - 400083
C.T.S No |  | 356 (Pt)
Road |  | Internal Road |  | Locality/Village |  | Kannamwar Nagar
City |  | Vikroli (East) |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400083
Nearby Landmark |  | Sambhaji Maidan Vikhroli |  | Distance from city centre: |  | 1.7 KM from Vikroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Yeshwant Rao Open University Library
West | NA | NA |  |  | Sambhaji Maidan Circle
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Buildings
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.1160554,72.9364555
Location Link |  | https://goo.gl/maps/ZkjR6jkqffECAFj38
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3814.45
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 2.906
Total FSI availaible for the project |  |  |  | 5.906
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 22528.15
Total number of Buildings |  |  |  | 06 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority.
Layout Approval No |  | Mhada9/539/2022 |  |  | Dated | 2022-04-07
Approved Floor plan No. |  | Mhada9/539/2022 |  |  | Dated | 2022-04-07
Commencement-CC No Valid Up to: |  | MH/EE/(B.P.)/GM/MHADA-9/539/2022 |  |  | Dated | 2022-06-17
This FCC is further extended for building comprising of wing C for (pt) for shops + (pt) for stilt+ (pt) for entrance lobby (ht. 3.40m) + (pt) for meter room + 1st to 23rd upper floors for residential users having ht. 69.94m + LMR and OHT. Wing D for (pt) for shops + (pt) for stilt + (pt) for entrance lobby (ht. 3.40m) + (pt) for meter room + 1st to 23rd upper floors for residential users having ht. 69.94m + LMR and OHT. Wing E for (pt) for shops + (pt) for stilt + (pt) for1 entrance lobby (ht. 3.40m) + (pt) for meter room + 1st to 23rd upper floors for residential users having ht. 69.94m + LMR and OHT. Wing F for (pt) for shops + (pt) for stilt, (pt) for entrance lobby (ht. 3.40m) + (pt) for meter room + 1st to 23rd upper floors for residential users having ht. 69.94m + LMR and OHT. Full Plinth CC for Wing A and B as per phase programme for Phase-II at pg. 805 as per approved plans dtd. 07.04.2022 u/no. MH/EE/(BP)/GM/MHADA-9/539/2022 .
Commencement-CC No Valid Up to: |  | MH/EE/(B.P.)/GM/MHADA-9/539/2023 |  |  | Dated | 05/09/2023
This Further CC is granted for Wing A, comprising of (pt) for Stilt parking + (pt) for shops + (pt) for Entrance Lobby (ht. 3.27 M) + (pt) for meter room + (pt) for substation + 1st to top of 18th upper floor for Residential user having ht. 55.54 Μι. & Wing B, comprising of (pt) for shops + (pt) for stilt + (pt) Entrance Lobby (ht. 3.27 M)+ for Pump Room+ (pt) for meter room 1st to top of 18th upper floor for Residential user having ht. 55.54 Mt. as per last approved plan dt.11.07.2023
Commencement-CC No Valid Up to: |  | MH/EE/(B.P.)/GM/MHADA-9/539/2024 |  |  | Dated | 28/06/2024
This full CC is granted for Wing A comprising of (pt) for shops + (pt) for Stilt + (pt) for Entrance lobby (ht.3.40m) + (pt) for meter room + 1st to 23rd upper floors for residential users having ht. 69.94m+LMR+ OHT and for Wing B comprising of (pt) for shops + (pt) for Stilt+ (pt) for Entrance lobby (ht.3.40m)+ (pt) for meter room 1st to 23rd upper floors for residential users having ht. 69.94m + LMR + OHT. as per last approved plan dt. 11.07.2023.
Part O. Certificate No.: |  | MH/EE/(BP()/GM/MHADA-9/539/2025/OCC/1/New Approved upto : Phase 1A (Wing E & F) = Gr/St + 1st to 23rd Floor Phase 1B (Wing C & D)= Gr/St + 1st to 23rd Floor |  |  | Dated | 2025-01-27
O. Certificate No.: |  | NA Approved upto : |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 22528.15
Approved no of units |  |  | Sale Flats - 552, Shops - 32, Offices - 4, Mhada Flats - 23
Approved no of Floors |  |  | Phase 1A (Wing E & F) = Gr/St + 1st to 23rd Floor Phase 1B (Wing C & D)= Gr/St + 1st to 23rd Floor Phase 2 (Wing A & B)= Gr/St + 1st to 23rd Floor
Proposed no of Floors |  |  | Phase 1A (Wing E & F) = Gr/St + 1st to 23rd Floor | [5 empty] | 378
Phase 1B (Wing C & D)= Gr/St + 1st to 23rd Floor
Phase 2 (Wing A & B)= Gr/St + 1st to 23rd Floor
Expected Completion |  |  | As per RERA - 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Phase 1A (Wing E & F) = Gr/St + 1st to 23rd Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 17.25
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase 1B (Wing C & D)= Gr/St + 1st to 23rd Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 17.25
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase 2 (Wing A & B)= Gr/St + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 21 Floor, Painting upto 20 Floor, Finishing upto 9 Floor Completed | , Flooring upto 21 Floor, Painting upto 20 Floor, Finishing upto 9 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 21 Floor, Painting upto 20 Floor, Finishing upto 9 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 90.43% |  | 94.57% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 21 | 91.3% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 20 | 86.96% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 9 | 39.13% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase 2 (Wing B)= Gr/St + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 16 Floor, External Plaster upto 14 Floor, Flooring upto 3 Floor Completed | , Internal Plaster upto 16 Floor, External Plaster upto 14 Floor, Flooring upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 16 Floor, External Plaster upto 14 Floor, Flooring upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 70.11% |  | 87.17% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 16 | 69.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 60.87% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 13.04% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 13400 |  |  | 13000 to 13400 | Smith | 2024-02-02 | igr
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 32500 |  |  | shop rate 23000 to 2800 & other charges add | cost sheet & IGR | 2022-09-21 | sejal & sachin sir
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 21000 |  |  |  | Shop Rate 32500 Sanjay Cost sheet |  | 2024-11-18
Legal Charges |  |  |  |  | 8500
Corpus Fund with existing members to be paid to society |  |  |  |  | 39000
Advance Maintenance Charges For 1Year |  |  |  |  | 46500
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 10720
Commercial Area Details for Shops
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 1A & 1B & Phase 2 (Wing A to F) |  | 32 |  | 7173.8449 |  | 11478.1518
Commercial Area Details for Offices
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 1A & 1B & Phase 2 (Wing A to F) |  | 4 |  | 6006.3012 |  | 9009.4519
Residential Area Details : Sale
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 2 (Wing A) |  | 107 |  | 47852.0078 |  | 71778.0118 |  | 111
Phase 2 (Wing B) |  | 101 |  | 55127.0725 |  | 82690.6088 |  | 110
Phase 1B (Wing C) |  | 86 |  | 47420.0485 |  | 71323.6956
Phase 1B (Wing D) |  | 86 |  | 34777.9458 |  | 52332.557
Phase 1A (Wing E) |  | 86 |  | 34777.9458 |  | 52332.557
Phase 1A (Wing F) |  | 86 |  | 48322.5023 |  | 72580.5648
Total |  | 552 |  | 268277.5228 |  | 403037.9951
Residential Area Details : Mhada
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 2 (Wing A) |  | 4 |  | 1863.0331 |  | 2794.5497 |  | 111
Phase 2 (Wing B) |  | 9 |  | 4710.2188 |  | 7065.3281 |  | 110
Phase 1B (Wing C) |  | 3 |  | 1602.9749 |  | 2404.4623
Phase 1B (Wing D) |  | 2 |  | 1068.6499 |  | 1602.9749
Phase 1A (Wing E) |  | 2 |  | 753.0494 |  | 1129.5742
Phase 1A (Wing F) |  | 3 |  | 1602.9749 |  | 2404.4623
Total |  | 23 |  | 11600.901 |  | 17401.3515
Grand Total |  | 611 |  | 293058.5699 |  | 440926.9502
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Phase 1B, Phase 1A & Phase 2
Wing A to F
Ground Floor for Commercial
1 |  | Shop | 200.3019 | 0 | 320.483 | Ground Floor for Commercial
2 |  | Shop | 171.9065 | 0 | 275.0503
3 |  | Shop | 126.4232 | 0 | 202.2771
4 |  | Shop | 451.5498 | 0 | 722.4797
5 |  | Shop | 172.224 | 0 | 275.5584
6 |  | Shop | 184.1828 | 0 | 294.6925
7 |  | Shop | 182.9988 | 0 | 292.798
8 |  | Shop | 224.7523 | 0 | 359.6037
9 |  | Shop | 157.585 | 0 | 252.1359
10 |  | Shop | 180.8352 | 0 | 289.3363
11 |  | Shop | 434.6934 | 0 | 695.5094
12 |  | Shop | 169.9636 | 0 | 271.9417
13 |  | Shop | 230.0805 | 0 | 368.1288
14 |  | Shop | 171.6858 | 0 | 274.6973
15 |  | Shop | 345.9383 | 0 | 553.5012
16 |  | Shop | 299.7505 | 0 | 479.6008
17 |  | Shop | 169.4899 | 0 | 271.1839
18 |  | Shop | 169.4899 | 0 | 271.1839
19 |  | Shop | 230.7802 | 0 | 369.2483
20 |  | Shop | 345.7935 | 0 | 553.2696
21 |  | Shop | 231.3829 | 0 | 370.2127
22 |  | Shop | 169.0163 | 0 | 270.4261
23 |  | Shop | 148.5432 | 0 | 237.6691
24 |  | Shop | 146.6057 | 0 | 234.5691
25 |  | Shop | 172.9344 | 0 | 276.6951
26 |  | Shop | 190.8242 | 0 | 305.3187
27 |  | Shop | 275.8544 | 0 | 441.3671
28 |  | Shop | 300.2133 | 0 | 480.3413
29 |  | Shop | 161.46 | 0 | 258.336
30 |  | Shop | 358.9794 | 0 | 574.367
31 |  | Shop | 228.5897 | 0 | 365.7435
32 |  | Shop | 169.0163 | 0 | 270.4261
Phase 1B, Phase 1A & Phase 2
Wing A to F
1st Floor for Commercial
1 |  | Office | 2376.6535 | 0 | 3564.9803 | 1st Floor for Commercial
3 |  | Office | 1255.5399 | 0 | 1883.3098
4 |  | Office | 1150.0311 | 0 | 1725.0467
5 |  | Office | 1224.0767 | 0 | 1836.115
Flat No. (Approved Plan) | Sale/ MHADA | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Phase 2
Wing A
1st Floor for Residential
1 | MHADA | 2BHK | 504.6163 | 0 | 756.9245 | 1st Floor for Residential
2 | MHADA | 1BHK | 358.7641 | 0 | 538.1462
5 | MHADA | 1BHK | 399.5597 | 0 | 599.3395
2nd Floor
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 2nd Floor
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462
3 | MHADA | 2BHK | 600.093 | 0 | 900.1395
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
3rd to 7th, 9th to 14th Floor
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 3rd to 7th, 9th to 14th Floor
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462
3 | Sale | 2BHK | 600.093 | 0 | 900.1395
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
8th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 8th Floor (Part Refuge Floor)
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462
3 | Refuge Floor
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
15th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 15th Floor (Part Refuge Floor)
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462
3 | Refuge Floor
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
16th to 18th Floor
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 16th to 18th Floor
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462
3 | Sale | 2BHK | 600.093 | 0 | 900.1395
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
19th, 20th & 21st Floor
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 19th, 20th & 21st Floor |  |  | 1B |  | 1A | Shop | Office
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462 |  |  |  | Makan |  | Housing | 7885714.2857 | #DIV/0!
3 | Sale | 2BHK | 600.093 | 0 | 900.1395 |  |  |  | 18330.4921 |  | 13474.946 | 4928571.4286 | #DIV/0!
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395 |  |  | On Saleable Area | 12220.3281 |  | 17217.9866
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
22nd Floor (Part Refuge Area) | [10 empty] | 27634.97
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 22nd Floor (Part Refuge Area) |  |  |  |  | 34526.2856
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462 | [5 empty] | 23213.547
3 | Sale | 1BHK | 475.3382 | 0 | 713.0074 |  |  |  |  | On Saleable Area | 15475.698
- | Refuge Area
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
23rd Floor
1 | Sale | 2BHK | 504.6163 | 0 | 756.9245 | 23rd Floor
2 | Sale | 1BHK | 358.7641 | 0 | 538.1462
3 | Sale | 2BHK | 600.093 | 0 | 900.1395
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 1BHK | 399.5597 | 0 | 599.3395
Wing B
1st Floor for Residential
1 | MHADA | 2BHK | 535.1861 | 0 | 802.7791 | 1st Floor for Residential
3 | MHADA | 1RK | 236.4851 | 0 | 354.7276
4 | MHADA | 1BHK | 399.5597 | 0 | 599.3395
5 | MHADA | 3BHK | 829.7968 | 0 | 1244.6951
2nd Floor
1 | MHADA | 2BHK | 535.1861 | 0 | 802.7791 | 2nd Floor
2 | MHADA | 2BHK | 535.1861 | 0 | 802.7791
3 | MHADA | 1BHK | 409.4626 | 0 | 614.1938
4 | MHADA | 1BHK | 399.5597 | 0 | 599.3395
5 | MHADA | 3BHK | 829.7968 | 0 | 1244.6951
3rd to 7th, 9th to 14th Floor
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 3rd to 7th, 9th to 14th Floor
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791
3 | Sale | 1BHK | 409.4626 | 0 | 614.1938
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
8th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 8th Floor (Part Refuge Floor)
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791
3 | Refuge Floor
4
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
15th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 15th Floor (Part Refuge Floor)
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791
3 | Refuge Floor
4
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
16th to 18th Floor
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 16th to 18th Floor
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791
3 | Sale | 1BHK | 409.4626 | 0 | 614.1938
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
19th, 20th & 21st Floor
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 19th, 20th & 21st Floor |  |  | 1B |  | 1A | Shop | Office
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791 |  |  |  | Makan |  | Housing | 7885714.2857 | #DIV/0!
3 | Sale | 1BHK | 409.4626 | 0 | 614.1938 |  |  |  | 26864.483 |  | 13474.946 | 4928571.4286 | #DIV/0!
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395 |  |  | On Saleable Area | 17909.6554 |  | 17217.9866
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
22nd Floor (Part Refuge Area) | [10 empty] | 27634.97
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 22nd Floor (Part Refuge Area) |  |  |  |  | 34526.2856
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | [5 empty] | 23213.547
- | Refuge Area
3 | Sale | 1RK | 261.5652 | 0 | 392.3478 |  |  |  |  | On Saleable Area | 15475.698
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
23rd Floor
1 | Sale | 2BHK | 535.1861 | 0 | 802.7791 | 23rd Floor
2 | Sale | 2BHK | 535.1861 | 0 | 802.7791
3 | Sale | 1BHK | 409.4626 | 0 | 614.1938
4 | Sale | 1BHK | 399.5597 | 0 | 599.3395
5 | Sale | 3BHK | 829.7968 | 0 | 1244.6951
Phase 1B
Wing C
1st Floor for Residential
1 | MHADA | 2BHK | 534.325 | 0 | 801.4874 | 1st Floor for Residential
3 | MHADA | 2BHK | 534.325 | 0 | 801.4874
4 | MHADA | 2BHK | 534.325 | 0 | 801.4874
2nd Floor
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 2nd Floor
2 | Sale | 2BHK | 534.325 | 96.8114 | 898.2989
3 | Sale | 2BHK | 534.325 | 96.8114 | 898.2989
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
3rd to 7th, 9th to 14th Floor
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 3rd to 7th, 9th to 14th Floor
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | 2BHK | 534.325 | 0 | 801.4874
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
8th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 8th Floor (Part Refuge Floor)
2 | Sale | Part Refuge Area
3 | Sale | 2BHK | 534.325 | 0 | 801.4874
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
15th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 15th Floor (Part Refuge Floor)
2 | Sale | Part Refuge Area
3 | Sale | 2BHK | 534.325 | 0 | 801.4874
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
16th to 18th Floor
1 | Sale | 2BHK | 546.273 | 0 | 819.4095 | 16th to 18th Floor
2 | Sale | 2BHK | 546.273 | 0 | 819.4095
3 | Sale | 2BHK | 546.273 | 0 | 819.4095
4 | Sale | 2BHK | 546.273 | 0 | 819.4095
19th, 20th & 21st Floor
1 | Sale | 2BHK | 546.273 | 0 | 819.4095 | 19th, 20th & 21st Floor |  |  | 1B |  | 1A | Shop | Office
2 | Sale | 3BHK | 658.2186 | 0 | 987.3279 |  |  |  | Makan |  | Housing | 41937.0734 | 35841.1557
3 | Sale | 3BHK | 658.2186 | 0 | 987.3279 |  |  |  | 16711.7733 |  | 18874.0497 | 26210.6709 | 22400.7223
4 | Sale | 2BHK | 546.273 | 0 | 819.4095 |  |  | On Saleable Area | 11141.1822 |  | 19090.9282
22nd Floor (Part Refuge Area) | [10 empty] | 19089.5069
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 22nd Floor (Part Refuge Area) |  |  |  |  | 19542.548
2 | Sale | 1RK | 413.23 | 0 | 619.8449 | [5 empty] | 19149.2582
3 | Sale | 3BHK | 665.2152 | 0 | 997.8228 |  |  |  |  | On Saleable Area | 12766.1721
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
23rd Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 23rd Floor
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 3BHK | 665.2152 | 0 | 997.8228
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
Wing D
1st Floor for Residential
1 | Mhada | 2BHK | 534.325 | 0 | 801.4874 | 1st Floor for Residential
4 | Mhada | 2BHK | 534.325 | 0 | 801.4874
2nd Floor
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 2nd Floor
2 | Sale | 2BHK | 534.325 | 96.8114 | 898.2989
3 | Sale | 2BHK | 534.325 | 96.8114 | 898.2989
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
3rd to 7th, 9th to 14th Floor
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 3rd to 7th, 9th to 14th Floor
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | 2BHK | 534.325 | 0 | 801.4874
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
8th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 8th Floor (Part Refuge Floor)
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | Part Refuge Area
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
15th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 15th Floor (Part Refuge Floor)
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | Part Refuge Area
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
16th to 18th Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 16th to 18th Floor
2 | Sale | 2BHK | 546.273 | 0 | 819.4095
3 | Sale | 2BHK | 546.273 | 0 | 819.4095
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
19th, 20th & 21st Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 19th, 20th & 21st Floor
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 3BHK | 665.2152 | 0 | 997.8228
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
22nd Floor (Part Refuge Area)
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 22nd Floor (Part Refuge Area)
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 1RK | 417.3203 | 0 | 625.9804
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
23rd Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 23rd Floor
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 3BHK | 665.2152 | 0 | 997.8228
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
Phase 1A
Wing E
1st Floor for Residential
1 | Mhada | 1BHK | 376.5247 | 0 | 564.7871 | 1st Floor for Residential
4 | Mhada | 1BHK | 376.5247 | 0 | 564.7871
2nd Floor
1 | Sale | 1BHK | 369.0976 | 0 | 553.6463 | 2nd Floor
2 | Sale | 1BHK | 369.0976 | 162.7517 | 635.0222
3 | Sale | 1.5 BHK | 481.9043 | 168.525 | 807.1189
4 | Sale | 1BHK | 369.0976 | 0 | 553.6463
3rd to 7th, 9th to 14th Floor
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 3rd to 7th, 9th to 14th Floor
2 | Sale | 1BHK | 381.4762 | 0 | 572.2142
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
8th Floor (Part Refuge Floor)
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 8th Floor (Part Refuge Floor)
2 | Sale | Part Refuge Area
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
15th Floor (Part Refuge Floor)
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 15th Floor (Part Refuge Floor)
2 | Sale | Part Refuge Area
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
16th to 18th Floor
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 16th to 18th Floor
2 | Sale | 1BHK | 381.4762 | 0 | 572.2142
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
19th, 20th & 21st Floor
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 19th, 20th & 21st Floor
2 | Sale | 1BHK | 381.4762 | 0 | 572.2142
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
22nd Floor (Part Refuge Area)
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 22nd Floor (Part Refuge Area)
2 | Sale | MP Room | 287.7217 | 0 | 431.5826
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
23rd Floor
1 | Sale | 1BHK | 376.5247 | 0 | 564.7871 | 23rd Floor
2 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
3 | Sale | 1.5 BHK | 481.9043 | 0 | 722.8564
4 | Sale | 1BHK | 376.5247 | 0 | 564.7871
Wing F
1st Floor for Residential
1 | Mhada | 2BHK | 534.325 | 0 | 801.4874 | 1st Floor for Residential
2 | Mhada | 2BHK | 534.325 | 0 | 801.4874
4 | Mhada | 2BHK | 534.325 | 0 | 801.4874
2nd Floor
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 2nd Floor
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | 2BHK | 534.325 | 96.8114 | 898.2989
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
3rd to 7th, 9th to 14th Floor
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 3rd to 7th, 9th to 14th Floor
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | 2BHK | 534.325 | 0 | 801.4874
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
8th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 8th Floor (Part Refuge Floor)
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | Part Refuge Area
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
15th Floor (Part Refuge Floor)
1 | Sale | 2BHK | 534.325 | 0 | 801.4874 | 15th Floor (Part Refuge Floor)
2 | Sale | 2BHK | 534.325 | 0 | 801.4874
3 | Sale | Part Refuge Area
4 | Sale | 2BHK | 534.325 | 0 | 801.4874
16th to 18th Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 16th to 18th Floor
2 | Sale | 2BHK | 593.8499 | 0 | 890.7748
3 | Sale | 2BHK | 593.8499 | 0 | 890.7748
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
19th, 20th & 21st Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 19th, 20th & 21st Floor
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 3BHK | 665.2152 | 0 | 997.8228
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
22nd Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 22nd Floor
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 1RK | 417.3203 | 0 | 625.9804
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
23rd Floor
1 | Sale | 2BHK | 593.8499 | 0 | 890.7748 | 23rd Floor
2 | Sale | 3BHK | 665.2152 | 0 | 997.8228
3 | Sale | 3BHK | 665.2152 | 0 | 997.8228
4 | Sale | 2BHK | 593.8499 | 0 | 890.7748
Remarks:
* | Phase 1A & 1B = All work completed. OC Received. Phase 2 = Finishing work is in process at the time of visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Please provide revised approved CC.
* | On Site, we meet Mr. Pooja Mule (9356497447).
* | We have updated revised approved floor plan & C.C for A & B Wing (on 21/09/2023).
* | Recommended Rates/Other Charges of the Property (shop) have been revised on 18/11/2024.
* | We have updated revised approved CC for Wing A & B on 14/02/2025.
* | Please provide revised approved plans dtd. 11/07/2023.
* | We have updated Part OC on 22/05/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nainesh Tambe |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Eastern Groves Phase 1A, 1B & 2
Layout Plan:
Google Map :
Formulas:
Kannamwar Nagar = [Kannamwar Nagar, row above]
Wing A
Wing B
Wing F
Wing D
Wing E
Wing D
Wing C
Wing B
Wing C
Wing E
Wing F

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted