## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-10
Name of the builder name |  |  |  |  | Mr. Kersi Jamshed Randeria
Name of the builder company |  |  |  |  | M/s. Heritage Housing Corporation
Name of the Project |  |  |  |  | Heritage Ahura Residency
Contact Details ( Name & Contact No.) |  |  |  |  | 2225146622
Name / No of the Building |  |  |  |  | Building No.R2 - Wing C, D & E
Docouments Provided |  |  |  |  | Approved Plans, CC
RERA No. |  |  |  |  | P51800009207
Project location details |  | Heritage Ahura Residency, CTS.1774,1775,1776B,1777, LBS Road, Kirol, Ghatkopar (West), Kurla, Mumbai, 400086.
CTS |  | 1774,1775,1776B,1777
Road |  | LBS Road |  |  | Locality/Village |  | Kirol
City |  | Ghatkopar (West) |  |  | District |  | Mumbai
Taluka |  | Kurla |  |  | Pin Code |  | 400086
Near by Landmark |  | Sarvodaya School |  |  | Distance from city centre: |  | About 1.2Km from Ghatkopar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Slum |  | Slum |  | Slum
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.089663,72.905536
Location Link |  | https://goo.gl/maps/SuSCfgeHPPxaVhVP7
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 7348.2
Permissible FSI |  |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 3
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 22044.6
Total number of Buildings |  |  |  |  | 01 Building (03 Wings)
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/2249/N/PL/AP |  |  |  | Dated | 2018-05-05
Approved Floor plan No. |  | SRA/ENG/2249/N/PL/AP |  |  |  | Dated | 05/05/2018.
Commencement Certificate No. |  | SRA/ENG/2249/N/PL/AP Valid Up to: Wing C = 1st to 5th Floor Wing D & E = 1st to 4th Floor |  |  |  | Dated | 05/05/2018. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 05/05/2018. |  | Expected Completion |  | 2023-12-29
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5106.17 |  | Approved no of units |  | Flats = 68
Approved no of Floors |  | Wing C = 1st to 5th Floor Wing D & E = 1st to 4th Floor |  |  |  | No of floors at site : See Construction details
Proposed no of Floors |  | Wing C, D & E = G + 1st to 12th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Wing C = G + 1st to 12th Floor Wing D = G + 1st to 12th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 12 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 12 | 100% |  | 19.23% |  | 51.92%
Plinth |  | 12 | 100%
RCC |  | 3 | 23.08% | [5 empty] | Excavation in process |  | 6
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed |  | 12
Internal Plaster | Brickwork & Internal Plaster | 0 | 0%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 3
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 6
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 9
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 12
Possession |  | 0 | 0%
Construction details: Wing D = G + 1st to 12th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 12 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 12 | 100% |  | 19.23% |  | 51.92%
Plinth |  | 12 | 100%
RCC |  | 3 | 23.08% | [5 empty] | Excavation in process |  | 6
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed |  | 12
Internal Plaster | Brickwork & Internal Plaster | 0 | 0%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 3
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 6
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 9
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 12
Possession |  | 0 | 0%
Construction details: |  | Wing E = G + 1st to 12th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 1 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 12 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 1 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 12 | 100% |  | 19.86% |  | 52.34%
Plinth |  | 12 | 100%
RCC |  | 3 | 23.08% | [5 empty] | Excavation in process |  | 6
Brickwork | Brickwork & Internal Plaster | 1 | 8.333% | [5 empty] | Excavation Completed |  | 12
Internal Plaster | Brickwork & Internal Plaster | 0 | 0%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 3
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 6
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 9
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 12
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 20000
Deposit for Water, Electricity | [5 empty] | 1,00,000/-
Maintenance for | [5 empty] | 15,000/-
Society formation charges | [5 empty] | 70,000/-
Recommended rate of Parking | [5 empty] | 800000/-
Development charges | [5 empty] | 2,50,000/-
Distressed valuation of the Property | [5 empty] | 16000
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
C |  | 40 | 18742.2768 |  |  | 27176.3014
D |  | 16 | 15396.3089 |  |  | 22324.6479
E |  | 12 | 8700.3259 |  |  | 12615.4726
Total |  | 68 | 42838.9116 |  |  | 62116.4219
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No. R2
Wing C (Aastha)
Ground Floor for Parking
1st to 5th Floors
1 |  | 1 BHK | 426.362 |  | 0 | 618.225 | N | 1st to 5th Floors |  | 10784.9091 | 46366.8718 | 11200.7816
2 |  | 1 BHK | 384.1672 |  | 0 | 557.0424 | N |  |  |  | 41778.1787
3 |  | 1 BHK | 612.1487 |  | 0 | 887.6156 | N |  |  | 11378.7997 | 66571.1689
4 |  | 1 BHK | 317.6456 |  | 0 | 460.5862 | N |  |  |  | 34543.9633
5 |  | 1 BHK | 331.8541 |  | 0 | 481.1885 | N |  |  |  | 36089.1355
6 |  | 1 BHK | 702.2434 |  | 0 | 1018.2529 | N |  |  |  | 76368.9654
7 |  | 1 BHK | 597.8326 |  | 0 | 866.8572 | N |  |  |  | 65014.2909
8 |  | 1 RK | 376.2018 |  | 0 | 545.4926 | N |  |  |  | 40911.9457
Wing D (Anmol) | [10 empty] | 0
Ground Floor for Parking | [10 empty] | 0
1st to 4th Floors | [10 empty] | 0
1 |  | 3 BHK | 973.8514 |  | 0 | 1412.0845 | N | 1st to 4th Floors |  |  | 105906.3367 | 15532.9294 | 70604.2245 | 282416.8979
2 |  | 3 BHK | 946.4785 |  | 0 | 1372.3939 | N |  |  |  | 102929.539 | 15096.3324 | 68619.6927 | 274478.7708
3 |  | 3 BHK | 1052.5039 |  | 0 | 1526.1307 | N |  |  |  | 114459.8013 | 16787.4375 | 76306.5342 | 305226.1368
4 |  | 3 BHK | 876.2434 |  | 0 | 1270.553 | N |  |  |  | 95291.4719 | 13976.0825 | 63527.648 | 254110.5918
Wing E (Ashraya) | [10 empty] | 0
Ground Floor for Parking | [10 empty] | 0
1st to 4th Floors | [10 empty] | 0
1 |  | 1 BHK | 489.3314 |  | 0 | 709.5306 | N | 1st to 4th Floors |  |  | 53214.7941
2 |  | 2 BHK | 705.2573 |  | 0 | 1022.6231 | N |  |  |  | 76696.7292
3 |  | 3 BHK | 980.4928 |  | 0 | 1421.7145 | N |  |  |  | 106628.5876
Remarks:
1. Construction work has stopped. Construction work is same from visit dtd.10/10/2020. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 7. We have considered Other charges from cost sheet. 8. Car parking is subjected to authentic documentation. 9. As per RERA, completion period of project Heritage Ahura Residency is expired on 29/12/2023 but still project is not completed. 10. The project has received first CC on 05/05/2018, But construction work is not yet completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sagar Naresh Katale |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Heritage Ahura Residency
Google Map :

## C% - C Wing
|  |  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | total floor | 5 |  | 6 | 0 | 0 | 1 | 5
plinth | 10 | 10 | 100%
slab | 6 | 3 | 50% |  | Parking |  | Rate
Bricks | 5 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 5 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 5 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 5 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 5 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 20 | 0 | 0 | 0 | 0 | 0
RCC | 20 | 15 |  | Recommended |  | 30 | 15 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 30% | 45% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C% - D Wing
|  |  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | total floor | 4 |  | 5 | 0 | 0 | 1 | 4
plinth | 10 | 10 | 100%
slab | 5 | 3 | 60% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 24 | 0 | 0 | 0 | 0 | 0
RCC | 24 | 18 |  | Recommended |  | 30 | 18 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 34% | 48% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C% - E Wing
|  |  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | total floor | 4 |  | 5 | 0 | 0 | 1 | 4
plinth | 10 | 10 | 100%
slab | 5 | 3 | 60% |  | Parking |  | Rate
Bricks | 4 | 1 | 25% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 24 | 3.75 | 0 | 0 | 0 | 0
RCC | 24 | 18 |  | Recommended |  | 30 | 18 | 3.75 | 0 | 0 | 0 | 0
Bricks | 3.75 | 3.75
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 37.75% | 51.75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-10-12 | Pratiksha

## Valuation
2020-10-12 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| commonfloor | Sanghvi Shri Parrsssva Eleganza | 1BHK | 445 | 712 | 9364.4663 | 6667500
| commonfloor | Sanghvi Shri Parrsssva Eleganza | 2BHK | 507 | 811.2 | 9375 | 7605000
| commonfloor | Sanghvi Shri Parrsssva Eleganza | 2BHK | 675 | 1080 | 9351.8519 | 10100000
| commonfloor | Sanghvi Shri Parrsssva Eleganza | 3BHK | 871 | 1393.6 | 9328.3582 | 13000000
| Average |  |  |  |  | 9354.9191
| Valuation Adopted |  |  |  |  | 9400

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.23 | 6.1 | 19.703 | CB |  |  | 0 |  |  | 0
|  | 3 | 2.93 | 8.79 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 3 | 3.07 | 9.21 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.05 | 3.17 | 9.6685 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.76 | 1.53 | 2.6928 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.22 | 2.35 | 2.867 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.98 | 1.92 | 1.8816 |  |  |  | 0 |  |  | 0
| passage2 | 2.1 | 2.07 | 4.347 |  |  |  | 0 |  |  | 0
| passage3 | 0.98 | 3.3 | 3.234 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 671.6079 | 62.3939 |  |  | 0 | 0 |  | 0 | 0
|  |  | 671.6079 | 62.3939