## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | M/s.Dream Developers
Name of the builder company |  |  |  | M/s.Dream Developers
Name of the Project |  |  |  | Dream Olympia
Contact Details ( Name & Contact No.) |  |  |  | Mr. Vicky Shyamlal Artwani 9320971133
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51800032632
Project location details |  | Dream Olympia, CTS No.459, 459/1 to 4, near Madhuban Garden, Lal Bahadur Shastri Road, Bhandup, Bhandup West, Kurla, Mumbai - 400078.
CTS No |  | 459, 459/1 to 4
Road |  | Lal Bahadur Shastri Road |  | Village |  | Bhandup
City |  | Bhandup West |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400078
Nearby Landmark |  | Madhuban Garden |  | Distance from city centre: |  | 1.7 KM from Bhandup Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Maruti Mandir Road
West | NA | NA |  |  | Bhandup Police Station
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Madhuban Garden
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.151544,72.936889
Location Link |  | https://goo.gl/maps/vZckLPWTciRsgb787
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1469.9
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.5
Total FSI availaible for the project |  |  |  | 1.5
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2204.85
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | CE/1001/BPES/AS |  |  | Dated | 2022-01-30
Approved Floor plan No. |  | CE/1001/BPES/AS |  |  | Dated | 2022-01-30
Commencement-CC No Valid Up to: |  | CE/ 1001 /BPES/AS/FCC/1/New |  |  | Dated | 2024-04-05
|  | Further C.C. is granted for shop no.1 to 9 on ground floor and 1st to 10th upper floors for residential wing as per amended approved plan dated 30.01.2022 for phase - I as per approved phase programme subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Valid Upto Date | 2025-03-29
Commencement-CC No Valid Up to: |  | CE/ 1001 /BPES/AS/FCC/1/Amend |  |  | Dated | 2025-04-15
|  | Further CC is granted for 11th and 12th floors, theater and shop no. 10 as per approved plans dtd 30.01.2022, subject to timely renewal of B.G., SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction along with precautionary measures for air pollution. |  |  | Valid Upto Date | 2026-03-29
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2204.85
Approved no of units |  |  | Flats - 51, Shops - 10
Approved no of Floors |  |  | 2B + G + 1st to 12th Floor
Proposed no of Floors |  |  | 2B + G + 1st to 21st Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Part I = 2B + G + 1st to 21st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 7 Floor Completed | , RCC upto 12 Slab, Brickwork upto 7 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 21 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 34.32% |  | 63.03% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 12 | 54.55% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 7 | 33.33% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 15.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Part II = 2B + G + 1st to 21st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 21 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed | Part II will start after Part I is completed 18/12/2024
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 11.82% |  | 46.36% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 1 | 4.545% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 15.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Avg. (Part I & II) Progress % |  | 23.07% |  | Avg. (Part I & II) Disbursement % |  | 54.7% |  | Plinth in process | 0
[8 empty] | Plinth completed | 0
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 15000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 23000
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 12000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 10 |  | 3395.3962 |  | 5432.6339
Theatre |  | 1 |  | 2888.3041 |  | 4621.2866
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 51 |  | 21963.6191 |  | 32945.4286
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
1st & 2nd Basement Floor For parking
Ground Floor For Commercial & Entrance Lobby
1 |  | Shop | 335.6215 | 0 | 536.9944 | Ground Floor For Commercial & Entrance Lobby
2 |  | Shop | 264.6868 | 0 | 423.4988 | Ground Floor For Commercial & Entrance Lobby
3 |  | Shop | 244.0199 | 0 | 390.4318 | Ground Floor For Commercial & Entrance Lobby
4 |  | Shop | 386.4276 | 0 | 618.2842 | Ground Floor For Commercial & Entrance Lobby
5 |  | Shop | 341.6494 | 0 | 546.639 | Ground Floor For Commercial & Entrance Lobby
6 |  | Shop | 384.3824 | 0 | 615.0119 | Ground Floor For Commercial & Entrance Lobby
7 |  | Shop | 375.556 | 0 | 600.8895 | Ground Floor For Commercial & Entrance Lobby
8 |  | Shop | 369.851 | 0 | 591.7617 | Ground Floor For Commercial & Entrance Lobby
9 |  | Shop | 390.5179 | 0 | 624.8287 | Ground Floor For Commercial & Entrance Lobby
10 |  | Shop | 302.6837 | 0 | 484.2939 | Ground Floor For Commercial & Entrance Lobby
1st Floor For Residential, Fitness Center & Part Theatre Area
1 |  | Theatre | 2888.3041 | 0 | 4621.2866 | 1st Floor For Residential, Fitness Center & Part Theatre Area
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
1st Floor For Residential, Fitness Center & Part Theatre Area
1 |  | Theatre Area |  |  |  | 1st Floor For Residential, Fitness Center & Part Theatre Area
2 | [5 empty] | 1st Floor For Residential, Fitness Center & Part Theatre Area
3 |  | 1BHK | 404.0806 | 0 | 606.1208 | 1st Floor For Residential, Fitness Center & Part Theatre Area
4 |  | 2BHK | 499.2343 | 0 | 748.8515 | 1st Floor For Residential, Fitness Center & Part Theatre Area
5 |  | 1BHK | 376.6324 | 0 | 564.9485 | 1st Floor For Residential, Fitness Center & Part Theatre Area
2nd Floor For Residential, Fitness Center & Part Theatre Area
1 |  | Theatre Area |  |  |  | 2nd Floor For Residential, Fitness Center & Part Theatre Area
2 | [5 empty] | 2nd Floor For Residential, Fitness Center & Part Theatre Area
3 |  | 1BHK | 404.0806 | 0 | 606.1208 | 2nd Floor For Residential, Fitness Center & Part Theatre Area
4 |  | 2BHK | 499.2343 | 0 | 748.8515 | 2nd Floor For Residential, Fitness Center & Part Theatre Area
5 |  | 1BHK | 376.6324 | 0 | 564.9485 | 2nd Floor For Residential, Fitness Center & Part Theatre Area
3rd & 4th Floor For Residential, Fitness Center & Part Theatre Area
1 |  | Theatre Area |  |  |  | 3rd & 4th Floor For Residential, Fitness Center & Part Theatre Area
2 | [5 empty] | 3rd & 4th Floor For Residential, Fitness Center & Part Theatre Area
3 |  | 1BHK | 404.0806 | 0 | 606.1208 | 3rd & 4th Floor For Residential, Fitness Center & Part Theatre Area
4 |  | 2BHK | 499.2343 | 0 | 748.8515 | 3rd & 4th Floor For Residential, Fitness Center & Part Theatre Area
5 |  | 1BHK | 376.6324 | 0 | 564.9485 | 3rd & 4th Floor For Residential, Fitness Center & Part Theatre Area
5th to 7th & 9th to 12th Floor
1 |  | 1BHK | 382.6602 | 0 | 573.9903 | 5th to 7th & 9th to 12th Floor
2 |  | 2BHK | 504.5087 | 0 | 756.763 | 5th to 7th & 9th to 12th Floor |  | 16517.7204
3 |  | 1BHK | 404.0806 | 0 | 606.1208 | 5th to 7th & 9th to 12th Floor
4 |  | 2BHK | 499.2343 | 0 | 748.8515 | 5th to 7th & 9th to 12th Floor
5 |  | 1BHK | 376.6324 | 0 | 564.9485 | 5th to 7th & 9th to 12th Floor |  | 15045.6181
8th Floor (Part Refuge Area)
1 |  | 1BHK | 394.07 | 0 | 591.1051 | 8th Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
3 |  | 1BHK | 404.0806 | 0 | 606.1208 | 8th Floor (Part Refuge Area)
4 |  | 2BHK | 499.2343 | 0 | 748.8515 | 8th Floor (Part Refuge Area)
5 |  | 1BHK | 376.6324 | 0 | 564.9485 | 8th Floor (Part Refuge Area)
Remarks:
* | Part I = Construction work is in process at the time of Visit (Slow Speed). Part II = Construction work is same as last visit dtd. 05/06/2025 but work is in process at the time of visit (Slow Speed) | [6 empty] | Construction Work resumes (Very Slow Speed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr.Anshul (Sales) - 9860684151.
* | We have updated latest CC from MCGM site On 14/06/2024 & 13/09/2025.
* | As per Visit dtd. 12/12/2024, we have observed that construction work is done in two parts: Part I = 9 slab completed, and Part II = plinth completed (the space kept for material storage).
* | Validity of CC is expired on 29/03/2025. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nainesh Tambe |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Dream Olympia
Google Map :
Formulas:
Bhandup = [Bhandup, row above]
part I
part II
Part 1
Part 2
Part 1

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres |  |  | 404 | 646.4 | 14077.9703 | 9100000
Magic Brick |  |  | 499 | 798.4 | 16157.3146 | 12900000
99 Acres |  |  | 404 | 646 | 13467.4923 | 8700000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted