## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 16/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group |  |  |  |  | M/s. Triveni Developers
Name of the builder company |  |  |  |  | M/s. Triveni Developers
Name of the Project |  |  |  |  | Kaveri Apartment CHSL
Name of the Project As Per RERA |  |  |  |  | Kaveri Apartments chsl Triveni Eden
Name & No of Buildings |  |  |  |  | Wing A & B
Docouments Provided |  |  |  |  | Refer Data
RERA No. |  |  |  |  | P51800007976
Project location details |  | Kaveri Apartment CHSL, CTS. No. 1141, I.C. Colony, Cross Road No. 3, Village Eksar, Borivali (W), Mumbai 400103.
CTS No |  | 1141 |  |  | Locality |  | Eksar
Road |  | Cross Road No. 3 |  |  | District |  | Mumbai
City |  | Borivali |  |  | Pin Code |  | 400103
Near by Landmark |  | I.C. Colony |  |  | Distance from city centre: |  | 3.1Km from Borivali Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Sachi Society |  | BMC Ground |  | Crescent Society |  | Sunflower
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.2467034,72.8448368
Location Link |  | https://goo.gl/maps/mjfSfcAeFfR4S4xH6
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 936
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | NA
Total FSI availaible for the project |  |  |  |  | NA
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 1347.64
Total number of Buildings |  |  |  |  | 02 Wing
Approval Detail : Plan approval
Layout Approval No |  | CHE/WSII/0721/R/C/337 (New) |  |  |  | Dated | 2017-03-27
Building plan approval No |  | CHE/WSII/0721/R/C/337 (New) |  |  |  | Dated | 2017-03-27 | Expiry date:NA
C.certificate No |  | CHE/WSII/0721/R/C/337(NEW) Valid Up to: Further C. C. up to 5th floor i.e. Stilt with pit for 3 tier pit/ stack parking + 1st to 5th floor for residential use as per Amended plan dated 06.03.2017. |  |  |  | Dated Valid Upto date | 27/03/2017 16/02/2018
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 2017-03-27 |  | Expected Completion |  | 2023-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 1347.64 |  | Approved no of units |  |  | NA
Approved no of Floors |  | Wing A & B = St + 1st to 5th Floor
Proposed no of Floors |  | Wing A & B = St + 1st to 7th Floor
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Wing A & B = St + 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor, Internal Plaster upto 5 Floor, External Plaster upto 4 Floor, Flooring upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor, Internal Plaster upto 5 Floor, External Plaster upto 4 Floor, Flooring upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 57.86% |  | 78.21% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 6 | 75% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 5 | 71.43% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 71.43% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 57.14% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 1 | 14.29% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Carpet area) | [5 empty] | 24000
Floor rise rate Per Sq. Ft. | [5 empty] | from floor
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 400000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 19200
Remarks: 1. Construction work was stopped from last visit 10/02/2021. 2. Car parking is subjected to authentic documentation. 3. We have considered rate by verifying it from market inquire. 4. Validity of CC is expired on 16/02/2018. Please provide revised CC. 5. As per RERA, completion period of project is expired on 31/12/2023. but still project is under construction.
Authorized Signatory Name & Seal of the agency
Photographs of Property : |  |  | Kaveri Apartments chsl Triveni Eden
`
Google Map :
Formulas:
Eksar = [Eksar, row above]

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Kaveri Apartment CHSL | 2BHK | 525 | 761.25 | 26095.2381 | 13700000
housing. | Kaveri Apartment CHSL | 2BHK | 602 | 872.9 | 26079.7342 | 15700000
housing. | Kaveri Apartment CHSL | 2BHK | 615 | 891.75 | 26016.2602 | 16000000
housing. | Kaveri Apartment CHSL | 3BHK | 816 | 1305.6 | 25980.3922 | 21200000
housing. | Kaveri Apartment CHSL | 3BHK | 910 | 1456 | 26043.956 | 23700000
Average |  |  |  |  | 26043.1161
Valuation Adopted |  |  |  |  | 26000

## C %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 75 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 6 | 71.4286 | Progress |  |  | 10 | 30 | 10.7143 | 7.1429 | 1.4286 | 0 | 0
Bricks | Total Floor | completed Floor | 71.4286 | Recommended |  |  | 30 | 22.5 | 10.7143 | 7.1429 | 0.71429 | 0 | 0
| 7 | 5 | 14.2857
plaster | Total Floor | completed Floor | 0
| 7 | 5 | 0
Flooring | Total Floor | completed Floor
| 7 | 1 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 30 | 22.5
Finishing | Total Floor | completed Floor |  | Bricks | 10.7143 | 10.7143
| 7 | 0 |  | Plaster | 7.1429 | 7.1429
|  |  |  | Flooring | 1.4286 | 0.71429
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 59.2857 | 71.0714

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0