## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Badlapur | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-08 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Bramha Constructions | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Bramha Constructions | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Kailash Complex Phase 1 & 2 | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Miss. Laveena 7887743379/ Mr. Kumar 7303554555
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Suraj Jadhav 9766624041
Name / No of the Building |  |  |  | Kailash Complex Phase 1 = Wing A Kailash Complex Phase 2 = Wing C, D & E
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, Sale Plans, Cost Sheet | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | Kailash Complex Phase 1 = P52000054450 Kailash Complex Phase 2 = P52000055271 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Kailash Complex Phase 1 & 2, Survey No.78/6, 9/B,11 & 169/8, near Shireen Park, Internal Rd, Mamdapur, Mamdapur, Neral, Karjat, Raigad - 410101. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 78/6, 9/B,11 & 169/8 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Mamdapur | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Rd |  | Locality/Village |  | Mamdapur | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Neral |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Karjat |  | Pin Code |  | 410101 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Shireen Park |  | Distance from city centre: |  | 1.4KM from Neral Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Adjn. S. No. 78/8 |  |  | Sunflower Bldg
West | NA | Adjn. S. No. 78/9A |  |  | Shireen Park
North | NA | Adjn. S. No. 79 |  |  | Vardhaman Nest Homes
South | NA | 7.5M Existing Rd |  |  | Internal Rd/Green Field
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.035171, 73.309920
Location Link |  | https://maps.app.goo.gl/Rk4Fq82ZyLVS86zu5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3787
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1406
Total FSI availaible for the project |  |  |  | 2.2406
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8485.26
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Raigad Zilha Parishad, Alibag | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | RJP/BD/NSVP/18/2022 |  |  | Dated | 2022-01-27 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | RJP/BD/NSVP/18/2022 |  |  | Dated | 2022-01-27 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Municipal Corporation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | RJP/BDKM/NSVP/18/2022 |  |  | Dated | 2022-01-27 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Proposed Built-up Area = 8485.26 Sq.M | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Total Proposed Built-up Area = 8485.26 Sq.M |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgaon Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad, Alibag
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 8485.26
Approved no of units |  |  | Flats - 175, Shops - 05
Approved no of Floors |  |  | A, C, D & E Wing = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | A, C, D & E Wing = Gr + 1st to 7th Floor
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - Phase 1 = Wing A = 31/03/2026 Phase 2 = Wing C, D & E = 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Center, Gym, Swimmingpool, Garden, Indoor Games, CCTV
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = Gr + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | C Wing = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 6 Floor, Flooring upto 1 Floor Completed | , External Plaster upto 6 Floor, Flooring upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 6 Floor, Flooring upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 75% |  | 90% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 1 | 14.29% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | D Wing (Part 1 - Flat No. 1 to 4) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 1 Floor, External Plaster upto 2 Floor Completed | , Internal Plaster upto 1 Floor, External Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 1 Floor, External Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 61.43% |  | 82.14% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5 |  | 0.18429
Internal Plaster | Brickwork & Internal Plaster | 1 | 14.29% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 28.57% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | D Wing (Part 2 - Flat No. 5 to 10)= Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 1 Floor Completed | , RCC upto 5 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 36.07% |  | 64.46% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 5 | 62.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 1 | 14.29% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Wing D (Part 1 & 2) Progress % |  | 46.21% |  | Wing D (Part 1 & 2) Disbursement % |  | 71.54%
Construction details: |  | E Wing = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed |  | wing E not yet started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3800 |  |  | 3700 to 3800 & sale area correction of Wing A flat no. 101 from index II on 08/07/2024. by smith | [8 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges |  |  |  |  | 50000 | [11 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, MSEB & Development Charges |  |  |  |  | 100000 | [11 empty] | 1500000 | 600000 | 500000
Society Formation Charges + Infrastruture + Maintenance Charges |  |  |  |  | 25000 | [11 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 150000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 3040 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 5 |  | 532.818 |  | 799.227
Total |  | 5 |  | 532.818 |  | 799.227
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 14 |  | 6256.1444 |  | 9071.4094
Wing C |  | 49 |  | 16098.1002 |  | 23342.2453
Wing D |  | 70 |  | 22547.889 |  | 32694.4391
Wing E |  | 42 |  | 14398.2493 |  | 20877.4615
Total |  | 175 |  | 59300.383 |  | 85985.5553
Grand Total |  | 180 |  | 59833.201 |  | 86784.7823
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Phase 1
Wing A
Ground Floor For Commercial & Meter Room
1 |  | Shop | 109.147 | 0 | 109.147 | 0 | 163.7204
2 |  | Shop | 147.8974 | 0 | 147.8974 | 0 | 221.846
3 |  | Shop | 107.4247 | 0 | 107.4247 | 0 | 161.1371
4 |  | Shop | 62.5388 | 0 | 62.5388 | 0 | 93.8083
5 |  | Shop | 105.8101 | 0 | 105.8101 | 0 | 158.7152
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Phase 1
Wing A
1st to 7th Floor For Residential
101 ,.., 701 |  | 2BHK | 374.5872 | 124.5395 | 499.1267 | 0 | 723.7337 |  | 6.4
102 ,.., 702 |  | 1BHK | 305.9129 | 88.6954 | 394.6082 | 0 | 572.1819 | 26.4675 | 8.2 | 8.2
Phase 2
Wing C
Ground Floor For Entrance Lobby, Driver Room, Meter Room & Parking
1st to 7th Floor For Residential | [8 empty] | 10.764
101 ,.., 701 |  | 1RK | 236.0545 | 22.0662 | 258.1207 | 0 | 374.275
102 ,.., 702 |  | 1BHK | 317.7533 | 24.219 | 341.9723 | 0 | 495.8598
103 ,.., 703 |  | 2BHK | 464.7895 | 53.9276 | 518.7172 | 0 | 752.1399 | 5.42 | 42.9321
104 ,.., 704 |  | 1RK | 189.6617 | 56.4034 | 246.065 | 0 | 356.7943
105 ,.., 705 |  | 1BHK | 286.9682 | 54.7888 | 341.757 | 0 | 495.5476
106 ,.., 706 |  | 1RK | 238.315 | 25.8336 | 264.1486 | 0 | 383.0154
107 ,.., 707 |  | 1BHK | 273.7285 | 55.2193 | 328.9478 | 0 | 476.9744 | 24.64 | 5.41
Wing D
Ground Floor For Entrance Lobby, Fitness Center, Driver Room, Society Office & Parking
1st to 7th Floor For Residential | [9 empty] | 3700
101 ,.., 701 |  | 1BHK | 305.6976 | 21.8509 | 327.5485 | 0 | 474.9454 |  |  | 1757297.8098 | 2007297.8098
102 ,.., 702 |  | 1BHK | 294.1801 | 47.4692 | 341.6494 | 0 | 495.3916 |  |  | 1832948.8164 | 2082948.8164
103 ,.., 703 |  | 1BHK | 269.7458 | 29.7086 | 299.4545 | 0 | 434.209 |  |  | 1606573.2852 | 1856573.2852
104 ,.., 704 |  | 1BHK | 278.4647 | 71.2577 | 349.7224 | 0 | 507.0974 |  |  | 1876260.4614 | 2126260.4614
105 ,.., 705 |  | 1BHK | 268.0236 | 78.2543 | 346.2779 | 0 | 502.1029 | 24.521 | 7.988 | 1857780.8262 | 2107780.8262
106 ,.., 706 |  | 1BHK | 268.0236 | 78.2543 | 346.2779 | 0 | 502.1029 |  |  | 1857780.8262 | 2107780.8262
107 ,.., 707 |  | 1RK | 196.3354 | 55.2193 | 251.5547 | 0 | 364.7543 |  |  | 1349590.8582 | 1599590.8582
108 ,.., 708 |  | 1BHK | 297.194 | 29.601 | 326.795 | 0 | 473.8528 |  |  | 1753255.3896 | 2003255.3896
109 ,.., 709 |  | 1BHK | 292.5655 | 20.2363 | 312.8018 | 0 | 453.5627 |  |  | 1678181.8716 | 1928181.8716
110 ,.., 710 |  | 1BHK | 297.194 | 21.8509 | 319.045 | 0 | 462.6152 |  |  | 1711676.2104 | 1961676.2104
Wing E
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
101 ,.., 701 |  | 1BHK | 297.3017 | 20.2363 | 317.538 | 0 | 460.4301
102 ,.., 702 |  | 1BHK | 263.5027 | 79.8689 | 343.3716 | 0 | 497.8888
103 ,.., 703 |  | 1BHK | 263.5027 | 79.8689 | 343.3716 | 0 | 497.8888
104 ,.., 704 |  | 1BHK | 265.8708 | 73.9487 | 339.8195 | 0 | 492.7382 | For Wing D layout on 02/01/2025
105 ,.., 705 |  | 1BHK | 292.2426 | 73.9487 | 366.1913 | 0 | 530.9774
106 ,.., 706 |  | 1BHK | 298.3781 | 48.2227 | 346.6008 | 0 | 502.5712
Remarks:
1 | Wing A = All work completed. Please provide OC. Wing C & D (Part 1 & 2) = Construction work is in process at the time of Visit. Wing E = Work is same as last visit (26/10/2024). | [6 empty] | As per site visit dtd. 02/01/2025, We have observed that Wing D building is constructed in Two part i.e(Part 1 included Flat No. 1 to 4(40%) & Part 2 included Flat No. 5 to 10(60%))
2 | As per site visit dtd. 02/01/2025, We have observed that Wing D building is constructed in Two part i.e(Part 1 included Flat No. 1 to 4 & Part 2 included Flat No. 5 to 10) | [6 empty] | As per site visit dtd. 02/01/2025, We have observed that Wing D building is constructed in Two part i.e(Part 1 included Flat No. 1 to 4(40%) & Part 2 included Flat No. 5 to 10(60%))
3 | We have considered Saleable area of Flats as per our Calculation.
4 | We have considered Saleable area of Commercial as per our Calculation.
5 | We considered Carpet area as per Approved Plan.
6 | We considered Gross carpet area = Net carpet + Balcony + C.B Area.
7 | We have considered proposed No. of Floor for Stage Calculation.
8 | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
10 | We have refer CC from RERA site on 16/05/2024. | [6 empty] | As per site visit dtd. 02/01/2025, We have observed that Wing D building is constructed in Two part i.e(Part 1 included Flat No. 1 to 4& Part 2 included Flat No. 5 to 10)
11 | As per approved floor plan Wing A flat no. 101 does not consist the terrace area. As per Index II Wing A flat no. 101 have terrace area 142 sqft. therefore total sale area should be consider as 888 sqft. | [6 empty] | 141.9772
12 | The sale plan and index II are provided by bank officials on WhatsApp, which is attached below. | [6 empty] | 141.9772
13 | Recommended Rates/Other Charges of the Property have been revised on 08/07/2024. | [6 empty] | 141.9772
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kailash Complex Phase 1 & 2
Remark No. 12 :
Layout :
Google Map :
Formulas:
Mamdapur = [Mamdapur, row above]
Wing A
N
N
Wing C
Wing D
Wing E
N
Part 2
Wing A
Wing D
Part 1
Wing C
Wing D
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F153: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H188: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate