## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group |  |  |  |  | M/s. Olympeo Infrastructure LLP & Pixie Business Ventures LLP.
Name of the builder company |  |  |  |  | M/s. Olympeo Infrastructure LLP & Pixie Business Ventures LLP.
Name of the Project |  |  |  |  | Olympeo Riverside
No. of Buildings |  | Phase I = Phase II = Phase III = |  |  | Type A = Bldg No.1 (Wing A & B) = A1 Type A = Bldg No.2 (Wing A & B) = A2 Type A = Bldg No.3 (Wing A & B ) = A3 Type A = Bldg No.4 (A & B Wing) = A4 Type B = Bldg No.5 (Wing A & B) = B1 Type B = Bldg No.13 (Wing A & B) = B2 Type B = Bldg No.14 (Wing A & B) = B3 Type C = Wing C-1, C-2, Type C = Wing C-3, C-5, C-6, C-7 & C-8
Contect Details ( Name & Contect No.) |  |  |  |  | 9922150952
RERA No. |  |  |  |  | Phase I - P52000002351 Phase II - P52000002440 Phase III - P52000012184
Docouments Provided |  |  |  |  | Approved Plans, CC of Building No.1- B Wing
Project location details |  | Olympeo Riverside, S.No. 44/2, 48/1B, 48/5,48/6, 48/7 At - Awsare, Taluka - Karjat, District - Raigad, Pin Code - 410101
S No |  | 44/2, 48/1B, 48/5,48/6, 48/7 |  |  | Locality |  | Awsare
Road |  | Shelu Road |  |  | District |  | Raigad
City |  | Karjat |  |  | Pin Code |  | 410101
Near by Landmark |  | Enjoy Farm & Resort |  |  | Distance from city centre: |  | About 3Km Distance From Shelu Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Open Plot |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.0725759,73.330658
Location Link |  | https://goo.gl/maps/5KT3gUCKx3Lxy5387?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 67664.7
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 67664.7
Total number of Buildings |  |  |  |  | 21 Wings
Approval Detail : Plan approval
Layout Approval No |  | M.Gov./LN&1/B/512-375/2013 Maharashtra Govt./LNA-1/PK160/2014 |  |  |  | Dated | 26/08/2014. 07/11/2015.
Building plan approval No |  | M.Gov./LN&1/B/512-375/2013 Maharashtra Govt./LNA-1/PK160/2014 |  |  |  | Dated | 26/08/2014. 07/11/2015.
C.certificate No |  | Maharashtra Govt./LNA-1/PK160/2014 |  |  |  | Dated | 07/11/2015.
O. Certificate No.: Approved upto |  | MSHA/L.N.1(B)/OC-37/2018 A1, A2, A3, A4, B1, B2, B3 = G + 1st to 4th Floor |  |  | Date of approval: | Dated | 04/06/2019. | Expiry date: NA
Commencement date of construction |  |  | 07/11/2015. |  | Expected Completion |  | Phase I & II - Completed Phase III - 31/12/2028
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 67664.7 |  | Approved no of units residential |  |  | Flat = 40
Approved no of Floors Type A |  | Bldg No.1 (Wing A & B) & Bldg No.2 (Wing A & B) = G + 1st to 4th Floor Bldg No.3 (Wing A & B ) & Bldg No.4 (Wing A & B) = G + 1st to 4th Floor
Type B |  | Bldg No.5 (Wing A & B) & Bldg No.13 (Wing A & B)= G + 1st to 4th Floor Bldg No.14 (Wing A & B) = G +1st to 4th Floor
Type C |  | Wing C-1, C-2, C-3, C-5, C-6, C-7, C-8 = G + 1st to 7th Floor
Proposed no of Floors Type A |  | Bldg No.1 (Wing A & B) & Bldg No.2 (Wing A & B) = G + 1st to 4th Floor Bldg No.3 (Wing A & B ) & Bldg No.4 (Wing A & B) = G + 1st to 4th Floor
Type B |  | Bldg No.5 (Wing A & B) & Bldg No.13 (Wing A & B)= G + 1st to 4th Floor Bldg No.14 (Wing A & B) = G +1st to 4th Floor
Type C |  | Wing C-1, C-2, C-3, C-5, C-6, C-7, C-8 = G + 1st to 7th Floor
Proposed no of Floors |  | Type A = Bldg No.1 (Wing A & B) = G + 1st to 4th Floor Type A = Bldg No.2 (Wing A & B) = G + 1st to 4th Floor Type A = Bldg No.3 (Wing A & B ) = G + 1st to 4th Floor Type A = Bldg No.4 (A & B Wing) = G + 1st to 4th Floor Type B = Bldg No.5 (Wing A & B) = G + 1st to 4th Floor Type B = Bldg No.13 (Wing A & B) = G + 1st to 4th Floor Type B = Bldg No.14 (Wing A & B) = G +1st to 4th Floor Type C = Wing C-1, C-2, C-3, C-5, C-6, C-7, C-8 = G + 1st to 7th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years after completion
Material laying at Site: :Brick, sand etc.
Construction details: Type A |  | Bldg No. 1 (Wing A & B) = Gr + 1st to 4th Floor Bldg No.2 (Wing A & B) = Gr + 1st to 4th Floor Bldg No.3 (Wing A & B ) = Gr + 1st to 4th Floor Bldg. No. 4 (A & B Wing) = Gr + 1st to 4th Floor Bldg No. 5 (Wing A & B) = Gr + 1st to 4th Floor Bldg No.13 (Wing A & B) = Gr + 1st to 4th Floor Bldg No.14 (Wing A & B) = Gr + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Construction details: |  | Wing C1 & C2 = Gr + 1st to 7th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7 | #REF!
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth in process | 5.25
Possession |  | 7 | 100% | [5 empty] | Plinth completed | 7
Construction details: |  | Wing C3 = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 5 Floor, Flooring upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 5 Floor, Flooring upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 76.43% |  | 90.71% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 42.86% | [5 empty] | Basement 3 | 0 | 37
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Wing C4 = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 7 Slab, Brickwork upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab, Brickwork upto 4 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 49.29% |  | 74.11% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 7 | 87.5% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 4 | 57.14% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Wing C5 = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Wing C6 = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 0% |  | 20% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Wing C7 & C8 = Gr + 1st to 7th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan :Under construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 3600
Development Charges | [5 empty] | 2,50,000/-
Club Charges | [5 empty] | 50,000/-
Legal Charges | [5 empty] | 10,000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 2880
Building details Floor Wise
Details of Flats in Building
Flat No. | Description (As per Approved plan) | Description (As per Sale plan) | Gross Carpet area |  | Attached Otla/ Terrace area | Saleable area | Floor
Type A = Building No.1 (Wing A)
Ground Floor for Residential
1 | 1BHK | 2BHK | 471.7861 |  | 57.399 | 853 | Ground Floor for Residential
2 | 1BHK | 2BHK | 471.7861 |  | 82.1993 | 886
3 | 1BHK | 2BHK | 471.7861 |  | 62.5819 | 883
4 | 1BHK | 2BHK | 471.7861 |  | 37.7816 | 849
1st to 3rd Floor
1 | 1BHK | 2BHK | 531.3649 |  | 0 | 853 | 1st to 3rd Floor
2 | 1BHK | 2BHK | 556.1651 |  | 0 | 886
3 | 1BHK | 2BHK | 556.1651 |  | 0 | 883
4 | 1BHK | 2BHK | 531.3649 |  | 0 | 849
4th Floor
1 | 1BHK | 2BHK | 531.3649 |  | 0 | 853 | 4th Floor
2 | 1BHK | 2BHK | 556.1651 |  | 0 | 886
3 | 1BHK | 2BHK | 556.1651 |  | 0 | 883
4 | 1RK | 1BHK | 413.6605 |  | 87.4306 | 725
Type A = Building No.1 (Wing B)
Ground Floor for Residential
1 | 1BHK | 2BHK | 471.7861 |  | 37.7816 | 849 | Ground Floor for Residential
2 | 1BHK | 2BHK | 471.7861 |  | 62.5819 | 883
3 | 1BHK | 2BHK | 471.7861 |  | 82.1993 | 886
4 | 1BHK | 2BHK | 471.7861 |  | 57.399 | 853
1st to 3rd Floor
1 | 1BHK | 2BHK | 531.3649 |  | 0 | 849 | 1st to 3rd Floor |  | 1.5978
2 | 1BHK | 2BHK | 556.1651 |  | 0 | 883
3 | 1BHK | 2BHK | 556.1651 |  | 0 | 886
4 | 1BHK | 2BHK | 531.3649 |  | 0 | 853
4th Floor
1 | 1RK | 1BHK | 413.6605 |  | 87.4306 | 725 | 4th Floor
2 | 1BHK | 2BHK | 556.1651 |  | 0 | 883
3 | 1BHK | 2BHK | 556.1651 |  | 0 | 886
4 | 1BHK | 2BHK | 531.3649 |  | 0 | 853
Remarks: 1. A & B Type = All work completed. OC Received. C1 & C2 Type = All work completed. Please provide OC. C3 & C4 = Construction work was stopped. Work is same as last visit (08/11/2023). C5 & C6 = Construction work was same as visit (03/03/2021). C7 & C8 = Work not yet Started. 2. We have given rate verify by market inquire. 3. We have considered Other charges from cost sheet. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 6. We update approved plans & CC of Type A = Building No. 1 (A & B Wings) (on 04/03/2021) 7. All 1BHK of approved plan are converted into 2BHK on site.(Area will remain same) 8. On site we met Mr. Nikhil Naik - 7719888644. 9. As per RERA, completion period of project Olympeo Riverside is expired on Date 29/06/2024 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  |  | Report By: |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Olympeo Riverside
Google Map :
C1
C2
C3
C4
C5
C1
C2
C3
C4

## C1, C2
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 7 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 7 | 100% |  | Panvel |  | 300000/-
Wood & painting | 7 | 7 | 100% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 7 | 100% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 5 | 5
Finishing | 5 | 5
total | 95% | 100% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C3
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 4 | 57.14% |  | Palghar |  | 100000/-
plaster | 7 | 1 | 14.29% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 8.5714 | 1.4286 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 8.5714 | 1.4286 | 0 | 0 | 0
Bricks | 8.5714 | 8.5714
Plaster | 1.4286 | 1.4286
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 60% | 70% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C5
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C6
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B
Basement | Podium | Ground | Upper Floor
2 | 6 | 1 | 34
Particulars | total floor | 34
plinth | 10 | 10 | 100%
slab | 43 | 39 | 90.7% |  | Parking |  | Rate
Bricks | 34 | 27 | 79.41% |  | Palghar |  | 100000/-
plaster | 34 | 13.5 | 39.71% |  | Ulwe, karanjade |  | 200000/-
Flooring | 34 | 16 | 47.06% |  | Panvel |  | 300000/-
Wood & painting | 34 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 34 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 36.2791 | 11.9118 | 3.9706 | 4.7059 | 0 | 0
RCC | 36.2791 | 27.2093 |  | Recommended |  | 30 | 27.2093 | 11.9118 | 3.9706 | 2.3529 | 0 | 0
Bricks | 11.9118 | 11.9118
Plaster | 3.9706 | 3.9706
Flooring | 4.7059 | 2.3529
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 66.87% | 75.44% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0