## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | M/s.Provident Housing Limited
Name of the builder company |  |  |  | M/s.Provident Housing Limited
Name of the Project |  |  |  | Provident Palmvista
Contact Details ( Name & Contact No.) |  |  |  | 7349659300
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Rupesh : 8976779733
Name / No of the Building |  |  |  | 8 Wings
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | B1 - P51700025841 B2 - P51700025839 C1 - P51700025840 C2 - P51700025864 |  | D1 - P51700025844 D2 - P51700025854 D3 - P51700025849 D4 - P51700025842
Project location details |  | Provident Palmvista, Plot No.88/4, 89, 90/1, 90/2/4, 90/2/5, 90/4/2, 101/1/B, 101/2, 101/3, near Puravankara Shilphata, Kalyan Shilphata Road, Daighar, Diva East, Thane, Thane.
Plot No |  | 88/4, 89, 90/1, 90/2/4, 90/2/5, 90/4/2, 101/1/B, 101/2, 101/3
Road |  | Kalyan Shilphata Road |  | Locality/Village |  | Daighar
City |  | Diva East |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 421204
Nearby Landmark |  | Puravankara Shilphata |  | Distance from city centre: |  | 7 KM from Diva Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | NA
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Puravankara Shilphata |  |  | -0.75
North | NA | NA |  |  | Kalyan Shilphata Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.146693,73.052259
Location Link |  | https://goo.gl/maps/zgZdfY3zk2rsaXhr8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 20425.53
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.7714
Total FSI availaible for the project |  |  |  | 4.8714
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 99501.93
Total number of Buildings |  |  |  | 8 Wings
Approval Detail : Plan approval
Layout Approval No |  | V.P.S11/0181/18/TMC/TDD/3961/22 |  |  | Dated | 2022-02-11
Approved Floor plan No. |  | V.P.S11/0181/18/TMC/TDD/3961/22 |  |  | Dated | 2022-02-11
Commencement Certificate No. |  | V.P.S11/0181/18/TMC/TDD/3252/19 |  |  | Dated | 2019-11-15
Valid Up to: Building B1 & B2 = G/St + 1st to 18th Floor Building C1 & C2 = G/St + 1st to 6th Floor Building D1 = B + G/St + P + 1st to 5th Floor Building D3 = B + G/St + P + 1st to 6th Floor Building D4 = B + G/St + P + 1st to 30th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 99501.93
Approved no of units |  |  | Sale Shop - 35, Sale Flat - 1194 , Mhada Flat - 78
Approved no of Floors |  |  | Building B1 & B2 = G/St + 1st to 30th Floor Building C1 & C2 = G/St + 1st to 25th Floor Building D1 to D4 = B + G/St + P + 1st to 30th Floor
Proposed no of Floors |  |  | Building B1 & B2= G/St + 1st to 30th Floor
Building C1 & C2 = G/St + 1st to 25th Floor
Building D1 to D4 = B + G/St + P + 1st to 30th Floor
Expected Completion |  |  | As per RERA - 30/06/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building B1 = G/St + 1st to 30th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 12.6 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 12.6 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 46.59% |  | 70.74% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 19 | 61.29% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 18 | 60% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 13.5 | 45% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12.6 | 42% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building B2 = G/St + 1st to 30th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 17.25 Floor, External Plaster upto 16.1 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 17.25 Floor, External Plaster upto 16.1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 56.4% |  | 77.62% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 24 | 77.42% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 23 | 76.67% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 17.25 | 57.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.1 | 53.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building C1 = G/St + 1st to 25th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 11.54% |  | 46.15% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 1 | 3.846% |  |  |  |  | Footing in Process | 6.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 12.5 | In previous report given stage of rcc is high
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0 | so the stage of Building C1 is not increased.
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25
Construction details: |  | Building C2 = G/St + 1st to 25th Floor | [5 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 10% |  | 45% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 6.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 12.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25
Construction details: |  | Building D1 = B + G/St + P + 1st to 30th Floor | [5 empty] | Excavation work Completed. Plinth work is process
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 15
Plinth |  | 22.5 | 75% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building D2 = B + G/St + P + 1st to 30th Floor | [5 empty] | Excavation work Completed. Plinth work completed
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 10% |  | 45% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building D3 = B + G/St + P + 1st to 30th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 26 Slab, Brickwork upto 24 Floor, Internal Plaster upto 16.8 Floor, External Plaster upto 16.8 Floor Completed
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 26 Slab, Brickwork upto 24 Floor, Internal Plaster upto 16.8 Floor, External Plaster upto 16.8 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 58.3% |  | 78.97% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 26 | 81.25% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 24 | 80% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 16.8 | 56% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.8 | 56% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building D4 = B + G/St + P + 1st to 30th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 23 Floor, Internal Plaster upto 16.1 Floor, External Plaster upto 16.1 Floor Completed
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 23 Floor, Internal Plaster upto 16.1 Floor, External Plaster upto 16.1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 56.39% |  | 77.64% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 25 | 78.12% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 23 | 76.67% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 16.1 | 53.67% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.1 | 53.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7500 |  |  |  | Rate 7500 & FR 30 Smith Verbal On 10/07/2024
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 11000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft (from 1st Floor) |  |  |  |  | 30/-
Club Charges |  |  |  |  | 275000
Premium Location Charges |  |  |  |  | 400000
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 6000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building-B1 | Sale Shop | 14 |  | 4144.14 |  | 6630.624
Building-B2 |  | 7 |  | 2165.9321 |  | 3465.4913
Building-C1 |  | 14 |  | 4453.2821 |  | 7125.2513
Total |  | 35 |  | 10763.3542 |  | 17221.3667
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building-B1 | Sale Flat | 295 |  | 105537.0588 |  | 158935.1725
Building-B2 | Sale Flat | 93 |  | 33004.6844 |  | 49507.0267
| Mhada Flat | 78 |  | 27661.5985 |  | 41748.1674
Building-C1 | Sale Flat | 289 |  | 102437.8707 |  | 154134.107
Building-D1 | Sale Flat | 169 |  | 59976.2545 |  | 89964.3818
Building-D2 | Sale Flat | 116 |  | 76625.9021 |  | 114938.8531
Building-D3 | Sale Flat | 116 |  | 76625.9021 |  | 114938.8531
Building-D4 | Sale Flat | 116 |  | 76625.9021 |  | 114938.8531
Total |  | 1272 |  | 558495.1732 |  | 839105.4146
Grand Total |  | 1307 |  | 569258.5274 |  | 856326.7813
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Sale / Mhada Unit | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Building - B1
Ground Floor for Commercial & Parking
22 | Sale | Shop | 245.8498 | 0 | 393.3596 | Ground Floor for Commercial & Parking
23 | Sale | Shop | 445.9525 | 0 | 713.524 | Ground Floor for Commercial & Parking
24 | Sale | Shop | 327.3332 | 0 | 523.7332 | Ground Floor for Commercial & Parking
25 | Sale | Shop | 272.975 | 0 | 436.7601 | Ground Floor for Commercial & Parking
26 | Sale | Shop | 274.3744 | 0 | 438.999 | Ground Floor for Commercial & Parking
27 | Sale | Shop | 298.1628 | 0 | 477.0605 | Ground Floor for Commercial & Parking
28 | Sale | Shop | 298.1628 | 0 | 477.0605 | Ground Floor for Commercial & Parking
29 | Sale | Shop | 274.3744 | 0 | 438.999 | Ground Floor for Commercial & Parking
30 | Sale | Shop | 274.3744 | 0 | 438.999 | Ground Floor for Commercial & Parking
31 | Sale | Shop | 298.1628 | 0 | 477.0605 | Ground Floor for Commercial & Parking
32 | Sale | Shop | 298.1628 | 0 | 477.0605 | Ground Floor for Commercial & Parking
33 | Sale | Shop | 270.1764 | 0 | 432.2822 | Ground Floor for Commercial & Parking
34 | Sale | Shop | 270.1764 | 0 | 432.2822 | Ground Floor for Commercial & Parking
35 | Sale | Shop | 295.9024 | 0 | 473.4438 | Ground Floor for Commercial & Parking
Building - B2
Ground Floor for Commercial & Parking
15 | Sale | Shop | 290.5204 | 0 | 464.8326 | Ground Floor for Commercial & Parking
16 | Sale | Shop | 307.7428 | 0 | 492.3884 | Ground Floor for Commercial & Parking
17 | Sale | Shop | 361.8857 | 0 | 579.0171 | Ground Floor for Commercial & Parking
18 | Sale | Shop | 312.4789 | 0 | 499.9663 | Ground Floor for Commercial & Parking
19 | Sale | Shop | 285.7842 | 0 | 457.2547 | Ground Floor for Commercial & Parking
20 | Sale | Shop | 285.7842 | 0 | 457.2547 | Ground Floor for Commercial & Parking
21 | Sale | Shop | 321.736 | 0 | 514.7775 | Ground Floor for Commercial & Parking
Building - C1
Ground Floor for Commercial & Parking
1 | Sale | Shop | 312.4789 | 0 | 499.9663 | Ground Floor for Commercial & Parking
2 | Sale | Shop | 288.1523 | 0 | 461.0436 | Ground Floor for Commercial & Parking
3 | Sale | Shop | 288.1523 | 0 | 461.0436 | Ground Floor for Commercial & Parking
4 | Sale | Shop | 312.4789 | 0 | 499.9663 | Ground Floor for Commercial & Parking
5 | Sale | Shop | 390.8408 | 0 | 625.3453 | Ground Floor for Commercial & Parking
6 | Sale | Shop | 312.4789 | 0 | 499.9663 | Ground Floor for Commercial & Parking
7 | Sale | Shop | 285.7842 | 0 | 457.2547 | Ground Floor for Commercial & Parking
8 | Sale | Shop | 285.7842 | 0 | 457.2547 | Ground Floor for Commercial & Parking
9 | Sale | Shop | 312.4789 | 0 | 499.9663 | Ground Floor for Commercial & Parking
10 | Sale | Shop | 458.7617 | 0 | 734.0187 | Ground Floor for Commercial & Parking
11 | Sale | Shop | 312.4789 | 0 | 499.9663 | Ground Floor for Commercial & Parking
12 | Sale | Shop | 285.7842 | 0 | 457.2547 | Ground Floor for Commercial & Parking
13 | Sale | Shop | 285.7842 | 0 | 457.2547 | Ground Floor for Commercial & Parking
14 | Sale | Shop | 321.8436 | 0 | 514.9498 | Ground Floor for Commercial & Parking
Flat No. (Approved Plan) | Sale / Rehab / Mhada Unit | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building - B1
1st Floor for Residential
1 | Sale | 1BHK | 360.101 | 35.7903 | 575.9418 | 1st Floor for Residential
2 | Sale | 1BHK | 374.4171 | 0 | 561.6257 | 1st Floor for Residential
3 | Sale | 1BHK | 385.4395 | 0 | 578.1592 | 1st Floor for Residential |  | 6918.5097
4 | Sale | 1BHK | 349.9721 | 83.9786 | 608.9367 | 1st Floor for Residential
5 | Sale | 1BHK | 326.6788 | 95.4767 | 585.4949 | 1st Floor for Residential
6 | Sale | 1BHK | 326.6788 | 95.4767 | 585.4949 | 1st Floor for Residential
7 | Sale | 1BHK | 326.6788 | 111.2459 | 545.6412 | 1st Floor for Residential
8 | Sale | 1BHK | 344.3317 | 93.593 | 610.0906 | 1st Floor for Residential
9 | Sale | 1BHK | 344.3317 | 168.8172 | 600.9062 | 1st Floor for Residential
10 | Sale | 1BHK | 318.5735 | 170.4749 | 563.0977 | 1st Floor for Residential
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2701,..,3001 | 2701 | 3001
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2702,..,3002 | 2702 | 3002
3 | Sale | 1BHK | 371.0351 | 0 | 556.5526 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2703,..,3003 | 2703 | 3003
4 | Sale | 1BHK | 371.0351 | 0 | 556.5526 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2704,..,3004 | 2704 | 3004
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2705,..,3005 | 2705 | 3005
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2706,..,3006 | 2706 | 3006
7 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2707,..,3007 | 2707 | 3007
8 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2708,..,3008 | 2708 | 3008
9 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2709,..,3009 | 2709 | 3009
10 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 2710,..,3010 | 2710 | 3010
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 801,..,2801 | 801 | 2801
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 802,..,2802 | 802 | 2802
3 | Sale | 1BHK | 371.0351 | 0 | 556.5526 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 803,..,2803 | 803 | 2803
4 | Sale | 1BHK | 371.0351 | 0 | 556.5526 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 804,..,2804 | 804 | 2804
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 805,..,2805 | 805 | 2805
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 806,..,2806 | 806 | 2806
7 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 807,..,2807 | 807 | 2807
8 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 808,..,2808 | 808 | 2808
9 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 809,..,2809 | 809 | 2809
10 | - | Refuge Area |  |  |  | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 810,..,2810 | 810 | 2810
Building - B2
1st Floor for Residential
1 | Mhada | 1BHK | 326.0329 | 260.7364 | 575.9615 | 1st Floor for Residential
2 | Mhada | 1BHK | 377.1619 | 0 | 565.7429 | 1st Floor for Residential
3 | Mhada | 1BHK | 377.1619 | 0 | 565.7429 | 1st Floor for Residential
4 | Mhada | 1BHK | 377.1619 | 0 | 565.7429 | 1st Floor for Residential
5 | Mhada | 1BHK | 326.0329 | 147.7144 | 562.9066 | 1st Floor for Residential
6 | Mhada | 1BHK | 326.0329 | 380.0015 | 584.0498 | 1st Floor for Residential
2nd to 7th, 9th to 12th, 13th & 14th Floor
1 | Mhada | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 13th & 14th Floor |  |  |  |  | 201,..,1401 | 201 | 1401
2 | Mhada | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 13th & 14th Floor |  |  |  |  | 202,..,1402 | 202 | 1402
3 | Mhada | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 13th & 14th Floor |  |  |  |  | 203,..,1403 | 203 | 1403
4 | Mhada | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 13th & 14th Floor |  |  |  |  | 204,..,1404 | 204 | 1404
5 | Mhada | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 13th & 14th Floor |  |  |  |  | 205,..,1405 | 205 | 1405
6 | Mhada | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 13th & 14th Floor |  |  |  |  | 206,..,1406 | 206 | 1406
15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 15101,..,3001 | 15101 | 3001
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 15102,..,3002 | 15102 | 3002
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 15103,..,3003 | 15103 | 3003
4 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 15104,..,3004 | 15104 | 3004
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 15105,..,3005 | 15105 | 3005
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 15th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor |  |  |  |  | 15106,..,3006 | 15106 | 3006
18th, 23rd & 28th Floor (Part Refuge Area)
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 1801,..,2801 | 1801 | 2801
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 1802,..,2802 | 1802 | 2802
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 1803,..,2803 | 1803 | 2803
4 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 1804,..,2804 | 1804 | 2804
5 | - | Refuge Area |  |  |  | 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 1805,..,2805 | 1805 | 2805
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 1806,..,2806 | 1806 | 2806
Building - C1
1st Floor for Residential
1 | Sale | 1BHK | 362.2269 | 0 | 543.3403 | 1st Floor for Residential
2 | Sale | 1BHK | 362.2269 | 0 | 543.3403 | 1st Floor for Residential
3 | Sale | 1BHK | 362.2269 | 0 | 543.3403 | 1st Floor for Residential
4 | Sale | 1BHK | 362.2269 | 0 | 543.3403 | 1st Floor for Residential
5 | Sale | 1BHK | 362.2269 | 0 | 543.3403 | 1st Floor for Residential
6 | Sale | 1BHK | 362.2269 | 0 | 543.3403 | 1st Floor for Residential
7 | Sale | 1BHK | 326.7057 | 102.4195 | 541.2683 | 1st Floor for Residential
8 | Sale | 1BHK | 326.7057 | 295.827 | 588.6676 | 1st Floor for Residential
9 | Sale | 1BHK | 326.7057 | 289.5301 | 586.5686 | 1st Floor for Residential
10 | Sale | 1BHK | 326.7057 | 289.5301 | 586.5686 | 1st Floor for Residential
11 | Sale | 1BHK | 326.7057 | 249.7571 | 573.3109 | 1st Floor for Residential
12 | Sale | 1BHK | 326.7057 | 102.4195 | 541.2683 | 1st Floor for Residential
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
4 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
7 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
8 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
9 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
10 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
11 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
12 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th Floor
8th, 13th, 18th, 23rd Floor (Part Refuge Area)
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
4 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
7 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
8 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
9 | - | Refuge Area |  |  |  | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
10 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
11 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
12 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
25th Floor (Part Terrace Area)
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 25th Floor (Part Terrace Area)
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 25th Floor (Part Terrace Area)
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 25th Floor (Part Terrace Area)
4 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 25th Floor (Part Terrace Area)
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 25th Floor (Part Terrace Area)
6 | - | Terrace Area |  |  |  | 25th Floor (Part Terrace Area)
7 | - |  |  |  |  | 25th Floor (Part Terrace Area)
8 | - |  |  |  |  | 25th Floor (Part Terrace Area)
9 | - | Terrace Area |  |  |  | 25th Floor (Part Terrace Area)
10 | - |  |  |  |  | 25th Floor (Part Terrace Area)
11 | - |  |  |  |  | 25th Floor (Part Terrace Area)
12 | - |  |  |  |  | 25th Floor (Part Terrace Area)
Building - D1
Basement Floor for Parking
Ground Floor for Parking
Podium Floor for Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
4 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
1 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
2 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
3 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
4 | - | Refuge Area |  |  |  | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
5 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
6 | Sale | 1BHK | 354.8891 | 0 | 532.3336 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
Building - D2
Basement Floor for Parking
Ground Floor for Parking
Podium Floor for Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
1 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  | 7801.87 |  |  | 15701 to 3001 | 15701 | 3001
2 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15702 to 3002 | 15702 | 3002
3 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15703 to 3003 | 15703 | 3003
4 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15704 to 3004 | 15704 | 3004
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
1 | Sale | 2BHK | 597.6173 | 0 | 896.4259 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6101 to 2601 | 6101 | 2601
2 | Sale | 2BHK | 597.6173 | 0 | 896.4259 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6102 to 2602 | 6102 | 2602
3 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6103 to 2603 | 6103 | 2603
4 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6104 to 2604 | 6104 | 2604
Building - D3
Basement Floor for Parking
Ground Floor for Parking
Podium Floor for Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
1 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15701 to 3001 | 15701 | 3001
2 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15702 to 3002 | 15702 | 3002
3 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15703 to 3003 | 15703 | 3003
4 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15704 to 3004 | 15704 | 3004
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
1 | Sale | 2BHK | 597.6173 | 0 | 896.4259 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6101 to 2601 | 6101 | 2601
2 | Sale | 2BHK | 597.6173 | 0 | 896.4259 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6102 to 2602 | 6102 | 2602
3 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6103 to 2603 | 6103 | 2603
4 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6104 to 2604 | 6104 | 2604
Building - D4
Basement Floor for Parking
Ground Floor for Parking
Podium Floor for Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor
1 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15701 to 3001 | 15701 | 3001
2 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15702 to 3002 | 15702 | 3002
3 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15703 to 3003 | 15703 | 3003
4 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th & 28th to 30th Floor |  |  |  |  | 15704 to 3004 | 15704 | 3004
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area)
1 | Sale | 2BHK | 597.6173 | 0 | 896.4259 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6101 to 2601 | 6101 | 2601
2 | Sale | 2BHK | 597.6173 | 0 | 896.4259 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6102 to 2602 | 6102 | 2602
3 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  |  |  |  | 6103 to 2603 | 6103 | 2603
4 | Sale | 2.5BHK | 666.5069 | 0 | 999.7603 | 6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  | 7357.7825 | 23.5043 |  | 6104 to 2604 | 6104 | 2604
Remarks:
* | Bldg B1, B2, D1 to D4 = Construction work is in Process at the time of visit. Bldg C1 & C2 = Work is in process at the time of visit (Slow Speed).
* | We considered Saleable area as per our calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Please provide approved floor plans of Following buildings : Building C2 = All Floor Plans Building B2 = 8th Floor Building D1, D2, D3, D4 = 27th Floor
* | Please provide C.C of Building D2.
* | As per site person Mr. Krushna (9607007059) Piling work is in process in Buildings B1, B2 & D4 Excavation work is in process in Building D3.
* | On Site, we meet Mr. Krishna - 9607007059. Provided plans doesn't consists dimensions and are not in scale. So please provide approved plans which are in scale and proper dimensions.
* | Recommended Rates / Other charges of the Property have been revised on 10/07/2024.
* | Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram Lambore |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Provident Palmvista
Google Map :
Formulas:
Daighar = [Daighar, row above]
Building C1 & C2
Building D1 & D2
Building D3 & D4
Building B1 & B2
Building C1 & C2
Building D1 & D2
Building D3 & D4
Building D4
Building B1 & B2
Building C1
D2
D1
C2
C1
D3

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
asmi | palas | 2022-10-06