## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Sammaan Capital | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | SCL Kalyan
CPC Name: |  |  |  | Axis Badlapur | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-09-07 | [6 empty] | Axis Sanpada |  |  | SCL Vashi
Name of the builder group |  |  |  | Regency Nirman Ltd | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | Regency Nirman Ltd | [9 empty] | SCL Thane
Name of the Project |  |  |  | Regency Anantam Nxt Phase I | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | NA | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | Ms. Aarti 9107171020 |  |  |  | Miss. Geeta : 9107171050 | [5 empty] | SCL Virar
Name / No of the Building |  |  |  | Building No. 1, 2, 7 & 8
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700055848 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Regency Anantam Nxt Phase I, Survey No.64, 65/3,4,5, 66/1, 67/4B, 102/5A,5B,7,9,10, near Aster - Tower Regency Anantam, Regency Anantam Rd, Davdi, Davdi, Dombivali East, Kalyan, Thane - 421306. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 64, 65/3,4,5, 66/1, 67/4B, 102/5A,5B,7,9,10 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Davdi | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Regency Anantam Rd |  | Locality/Village |  | Davdi | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Dombivali East |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kalyan |  | Pin Code |  | 421306 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Aster - Tower Regency Anantam |  | Distance from city centre: |  | 5.7 KM from Dombivali Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Open Plot
West | NA | 24 M W Road |  |  | Road
North | NA | 24 M W Road |  |  | Road
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.1991311,73.1217787
Location Link |  | https://maps.app.goo.gl/pjpTReZWBG3Ho7iz6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 54438
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.0344
Total FSI availaible for the project |  |  |  | 2.1344
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 116190.74
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan Dombivli Municipal Corporation (KDMC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | KDMC/TPD/BP/27Village/2024-25/01 |  |  | Dated | 2024-04-02 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | KDMC/TPD/BP/27Village/2024-25/01 |  |  | Dated | 2024-04-02 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/27Village/2024-25/01 |  |  | Dated | 2024-04-02 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KDMC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Building No. 1 & 2 = St + 2P + E Deck + 1st to 28th Floors Building No. 7 & 8 = St + 2P + E Deck + 1st to 24th Floor | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Building No. 1 & 2 = St + 2P + E Deck + 1st to 28th Floors Building No. 7 & 8 = St + 2P + E Deck + 1st to 24th Floor |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | KDMC/TPD/4894 |  |  | Dated | 2023-11-30 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | Survey No. 64, 65/3, 65/4, 65/5, 66/1, 66/2, 67/4B, 102/5A, 102/5B, 102/7, 102/9, 102/10, 102/4 | [15 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | Survey No. 64, 65/3, 65/4, 65/5, 66/1, 66/2, 67/4B, 102/5A, 102/5B, 102/7, 102/9, 102/10, 102/4 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 67842.3 |  |  |  |  | 67842.3
Approved no of units |  |  | Flats - 800 |  |  |  |  | Total Flat = 832
Approved no of Floors |  |  | Building No. 1 & 2 = St + 2P + E Deck + 1st to 28th Floor Building No. 7 & 8 = St + 2P + E Deck + 1st to 24th Floor
Proposed no of Floors |  |  | Building No. 1 & 2 = St + 2P + E Deck + 1st to 28th Floor
Building No. 7 & 8 = St + 2P + E Deck + 1st to 24th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion | [6 empty] | 32
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Cafeteria With Library, Meditation Room, 3D Video Parlor, Mini Theatre, Salon, Jogging Track, Buiseness Center, Multipurpose Hall, Spa Room, Swimming Pool, Senior Citizen Zone, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 1 & 2 = St + 2P + E Deck + 1st to 28th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 28 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 14
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Construction details: |  | Building No. 7 & 8 = St + 2P + E Deck + 1st to 24th Floor | [5 empty] | Excavation Completed
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 24 | Excavation
Stage of construction: |  | Excavation Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 0% |  | 20% |  | Excavation in process | 12
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Construction details: |  | 0 | [5 empty] | #DIV/0!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 0 | #DIV/0! | Work not yet Started.
Stage of construction: |  | #DIV/0! | [5 empty] | #DIV/0!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0
Excavation |  | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! |  | Excavation in process | 0
Plinth |  | 0 | #DIV/0! |  |  |  |  | Excavation Completed | 0
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0
Brickwork | Brickwork & Internal Plaster | 0 | #DIV/0! |  |  |  |  | Footing Completed | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | #DIV/0! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #DIV/0! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #DIV/0! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #DIV/0! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #DIV/0! |  |  |  |  | Plinth in process | 0
Possession |  | 0 | #DIV/0! |  |  |  |  | Plinth completed | 0
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6800 |  |  |  | Rate 6800 Smith Cost sheet |  | 2024-11-18 | [5 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [16 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 300000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 5440 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 |  | 216 |  | 109903.8845 |  | 159360.6325
Building No. 2 |  | 216 |  | 109903.8845 |  | 159360.6325
Building No. 7 |  | 184 |  | 138877.9891 |  | 201373.0842
Building No. 8 |  | 184 |  | 138877.9891 |  | 201373.0842
Total |  | 800 |  | 497563.7472 |  | 721467.4334
Grand Total |  | 800 |  | 497563.7472 |  | 721467.4334
Building details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Building No. 1
Ground Floor For Meter Room & Parking | [9 empty] | 10.764
1st & 2nd Podium For Parking
E Deck Floor For Society Office & Parking
1st, 2nd, 4th, 5th, 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 26th & 28th Floor
1 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
2 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807 | 37.0555 | 7.4575
3 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
4 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
5 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
6 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
7 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
8 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
3rd, 8th, 13th, 18th, 23rd & 27th Floor (Part Refuge Area)
1 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
2 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
3 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807 |  | 5421.6652
4 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
5 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
6 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
7 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
8 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
Building No. 2
Ground Floor For Meter Room & Parking
1st & 2nd Podium For Parking
E Deck Floor For Society Office & Parking
1st, 2nd, 4th, 5th, 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 26th & 28th Floor
1 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
2 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
3 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
4 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
5 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
6 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
7 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
8 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
3rd, 8th, 13th, 18th, 23rd & 27th Floor (Part Refuge Area)
1 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
2 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
3 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
4 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
5 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
6 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
7 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
8 |  | 1BHK | 428.1919 | 80.6224 | 508.8143 | 0 | 737.7807
Building No. 7
Ground Floor, 1st & 2nd Podium For Parking
E Deck Floor For Society Office & Parking
1st, 2nd, 4th, 5th, 7th, 9th to 12th, 14th to 17th, 19th to 22nd & 24th Floor
1 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
2 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189 | 55.1277 | 10.2125
3 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
4 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
5 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
6 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
7 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
8 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
3rd, 8th, 13th, 18th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
2 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
3 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
4 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
5 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
6 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
7 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
8 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
Building No. 8
Ground Floor, 1st & 2nd Podium For Parking
E Deck Floor For Society Office & Parking
1st, 2nd, 4th, 5th, 7th, 9th to 12th, 14th to 17th, 19th to 22nd & 24th Floor
1 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
2 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
3 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
4 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
5 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
6 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
7 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
8 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
3rd, 8th, 13th, 18th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
2 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
3 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
4 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
5 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
6 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
7 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
8 |  | 2BHK | 641.5344 | 113.2373 | 754.7717 | 0 | 1094.4189
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Bldg No.1 & 2 = Work Not yet Started. Bldg No.7 & 8 = Construction work is stop. Work is same as last vsit dtd. 04/12/2024.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | In Approved plans 6th Floor Plan is missing in Building No. 1, 2, 7 & 8. Please Provide approved floor plan for 6th floor.
* | Please check for Fire Noc & Environmental Clearance .
* | Recommended Rates/Other Charges of the Property have been revised on 18/11/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Gangaram Lambore |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Regency Anantam Nxt Phase I
Layout :
Google Map :
Formulas:
Davdi = [Davdi, row above]
Bldg No.1
Bldg No.8
Bldg No.7
Bldg No.2
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F122: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H154: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0