## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-16
Name of the builder group |  |  |  |  | M/S. Shree Siddhivinayak Classic Construction Pvt. Ltd.
Name of the builder company |  |  |  |  | M/S. Shree Siddhivinayak Classic Construction Pvt. Ltd.
Name of the Project |  |  |  |  | Ruparel Pride
Name of the Wings |  |  |  |  | Wing A & B
Contect Details ( Name & Contect No.) |  |  |  |  | 8369069448
RERA No. |  |  |  |  | P51800020602
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | Ruparel Pride, C.T.S No.6 (pt), Near Sheth Nanji Bhai Kimji Bhai Tanae Sabhagruh, Mother Dairy Road, Nehru Nagar, Kurla (E), Villlage Kurla-III, Dist. Mumbai 400024
CTS No |  | 6 (pt) |  |  | Locality |  | Kurla
Road |  | Mother Dairy Road |  |  | District |  | Mumbai
City |  | Kurla |  |  | Pin Code |  | 400 024
Near by Landmark |  | Nehru Nagar Shanti Bhuvan CHS Ltd |  |  | Distance from city centre: |  | About 3.3Km Distance From Kurla Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Upper class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Road |  | Building |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.0626241,72.8824203
Location Link |  | https://goo.gl/maps/nH9zW5gChsggc4vn7
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 931.87
Permissible FSI |  |  |  |  | Not Given
Permissible TDR/Paid FSI |  |  |  |  | Not Given
Total FSI availaible for the project |  |  |  |  | -
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 4525.67
Total number of Buildings |  |  |  |  | 02 wings
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  |  | Dated | NA
Building plan approval No |  | EE/BP Cell GM/Mhada-22/229/2019 |  |  |  | Dated | 08/03/2019.
C.certificate No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-22/229/2022/ FCC/1/Amend |  |  |  | Dated | 06/04/2022.
|  | This Full CC is now re-endorsed and further extended from 6th to 16th floors for building consisting of Wing A and Wing B i.e. ht. 50.90 AGL as per approved plans dtd. 11/06/2021. |  |  |  | Valid Date Upto | 15/04/2022.
O. Certificate No.: |  | NA |  |  |  | Date of approval: |  | NA
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 4525.67
Approved no of units residential |  |  | NA
Approved no of Floors |  |  | Wing A & B = Stilt(Pt) + Gr(Pt) + 16th Floors
Proposed no of Floors |  |  | Wing A & B = Stilt + 1st to 16th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure: |  |  | 60 Years After Completion
Proposed Amenities |  |  | Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, Landscaping & Garden, etc.
Quality of construction: |  |  | Good
Material laying at Site: : |  |  | Bricks, Cement & Steel etc.
Violations Observed if any : |  |  | NA
Wheather the construction is as per approved Building plan : |  |  | Under Construction
Construction details: |  | Wing A & B = Stilt + 16th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 16
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% |  | 90.94% |  | 94.69% |  | Excavation in process | 8
Plinth |  | 16 | 100% | [5 empty] | Excavation Completed | 16
RCC (Including podiums) |  | 17 | 100% | [5 empty] | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 93.75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 14 | 87.5% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 43.75% | [5 empty] | Plinth in process | 12
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 16
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 18000
Club Hous Charges | [5 empty] | 1,00,000/-
Development Charges | [5 empty] | 1,00,000/-
Electric/Water Charges | [5 empty] | 40,000/-
MGL Connection | [5 empty] | 10,000/-
Society Formation Charges | [5 empty] | 25,000/-
Recommended rate of Parking | [5 empty] | 600000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 14400
Remarks: 1. Construction work is in process at the time of visit. Internal photographs was not allowed. 2. We considered given rate verify by market inquire. 3. Car parking is subjected to authentic documentation. 4. We have release report on the basis of other vendor report. 5. We have updated revised approved CC from MHADA site dtd on 11/03/2023. 6. As per our observation, the construction work of ruparel projects (Ruparel Jewel, Ruparel Regalia, Ruparel Millennia, etc.) seems to be on a slow speed since year 2023. 7. Please provide revised Approved Plan. 1. Construction work was stopped. Work is same as last visit(09/06/2023). 5. On site, we meet Mr. Prathmesh - 7719883028.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ruparel Pride
Google Map :

## A
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 22
Particulars | total floor | 22
plinth | 10 | 10 | 100%
slab | 23 | 2 | 8.696% |  | Parking |  | Rate
Bricks | 22 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 22 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 22 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 22 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 22 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 3.4783 | 0 | 0 | 0 | 0 | 0
RCC | 3.4783 | 2.6087 |  | Recommended |  | 30 | 2.6087 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 13.48% | 32.61% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2021-02-23 | Pratiksha

## B
Basement | Podium | Ground | Upper Floor
2 | 6 | 1 | 34
Particulars | total floor | 34
plinth | 10 | 10 | 100%
slab | 43 | 39 | 90.7% |  | Parking |  | Rate
Bricks | 34 | 27 | 79.41% |  | Palghar |  | 100000/-
plaster | 34 | 13.5 | 39.71% |  | Ulwe, karanjade |  | 200000/-
Flooring | 34 | 16 | 47.06% |  | Panvel |  | 300000/-
Wood & painting | 34 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 34 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 36.2791 | 11.9118 | 3.9706 | 4.7059 | 0 | 0
RCC | 36.2791 | 27.2093 |  | Recommended |  | 30 | 27.2093 | 11.9118 | 3.9706 | 2.3529 | 0 | 0
Bricks | 11.9118 | 11.9118
Plaster | 3.9706 | 3.9706
Flooring | 4.7059 | 2.3529
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 66.87% | 75.44% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0