## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-13
Name of the builder group |  |  |  |  | M/s. Jai Mata Di Home Construction Pvt Ltd
Name of the builder company |  |  |  |  | M/s. Jai Mata Di Home Construction Pvt Ltd
Name of the Project |  |  |  |  | Safal Trademark
Contect Details ( Name & Contect No.) |  |  |  |  | 2225555444
Name / No of the Building |  |  |  |  | 01 Building (Tower 1, Tower 2, Tower 3 & Tower 4)
Docouments Verified |  |  |  |  | Approved plans, CC
RERA No. |  |  |  |  | P51800003754
Project location details |  | Safal Trademark, CTS No.303, 303/1 to 303/45, Lal Dongar Road, Chembur, Kurla, Mumbai - 400071.
CTS No |  | 303, 303/1 to 303/45
Road |  | Lal Dongar Road |  |  | Locality/Village |  | Chembur
City |  | Chembur |  |  | District |  | Mumbai
Taluka |  | Kurla |  |  | Pin Code |  | 400071
Near by Landmark |  | Anand Nagar Society |  |  | Distance from city centre: |  | About 1.9 Km from Tilaknagar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Jakh Dada Mandir |  | Anand Nagar Society |  | Slum |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.0514011,72.8889536
Location Link |  | https://goo.gl/maps/MtUhptNjgmS74wsF9
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
[5 empty] | Non-Slum Plot |  | Non-Slum Plot
Total land area of the project in Sq. Mt. |  |  |  |  | 2904.08 |  | 2904.08
Permissible FSI |  |  |  |  | 1 |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 1.3124
Total FSI availaible for the project |  |  |  |  | 2.3124 |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 6715.52 |  | 6715.52
Total number of Buildings |  |  |  |  | 04 Towers
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/3897/MW/PL/AP |  |  |  | Dated | 16/09/2019.
Approved Floor plan No. |  | SRA/ENG/3897/MW/PL/AP |  |  |  | Dated | 16/09/2019.
Commencement Certificate No. |  | SRA/ENG/3897/MW/PL/AP Valid Up to: Tower 1 & 2 = G + 1st Podium + 2nd Podium + 1st to 10th Floors as per Approved amended plans dtd 30/08/2018. |  |  |  | Dated | 19/03/2019. | Valid upto date: One year from date of issue
Commencement Certificate No. |  | SRA/ENG/3897/MW/PL/AP Valid Up to: Tower 3 & 4 = Upto plinth |  |  |  | Dated | 27/04/2017. | Valid upto date: One year from date of issue
Commencement Certificate No. |  | SRA/ENG/3897/MW/PL/AP Valid Up to: This furher C.C is granted for 11th to 16th upper floors including OHWT & LMR for Tower '1' & '2' for sale bldg and also granted for 1st to 15th upper floors for full work & 16th upper floor for RCC framework including OHWT & LMR for Tower '3' & '4' for sale bldg as per approved amended plans dtd 22/07/2021. |  |  |  | Dated | 2021-07-22 | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  |  | Dated | NA
Commencement date of construction |  |  | 19/03/2019. |  | Expected Completion |  | As per RERA=31/12/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 6715.52 |  | Approved no of units |  | Flats = 166
Approved no of Floors |  | Tower 1 & 2 = G + 1st Podium + 2nd Podium + 1st to 12th Floors Tower 3 & 4 = G + 1st Podium + 2nd Podium + 1st to 11th Floors + 12th Floor (Refuge Floor)
Proposed no of Floors |  | Tower 1 & 2 = G + 1st Podium + 2nd Podium + 1st to 16th Floor Tower 3 & 4 = G + 1st Podium + 2nd Podium + 1st to 16th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc
Construction details: Tower 1 & 2 = G + 1st Podium + 2nd Podium + 1st to 16th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 16 Floor completed, External Plaster upto 16 Floor completed, Flooring upto 14 Floor completed, Painting upto 12 Floor completed
Ground |  | 1 | Podium |  | 2 |  | Floors | 16 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 16 Floor completed, External Plaster upto 16 Floor completed, Flooring upto 14 Floor completed, Painting upto 12 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 16 | 100% |  | 87.5% |  | 94.38%
Plinth |  | 16 | 100%
RCC |  | 19 | 100% | [5 empty] | Excavation in process | 8
Brickwork | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Excavation Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 16 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% | [5 empty] | Footing in Process | 4
Flooring & Fitting | Flooring & Fitting | 14 | 87.5% | [5 empty] | Footing Completed | 8
Painting & Wooden |  | 12 | 75% | [5 empty] | Plinth in process | 12
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 16
Possession |  | 0 | 0%
Construction details: Tower 3 = G + 1st Podium + 2nd Podium + 1st to 16th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 16 Floor completed, External Plaster upto 16 Floor completed, Flooring upto 14 Floor completed, Painting upto 10 Floor completed
Ground |  | 1 | Podium |  | 2 |  | Floors | 16 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 16 Floor completed, External Plaster upto 16 Floor completed, Flooring upto 14 Floor completed, Painting upto 10 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 16 | 100% |  | 86.88% |  | 94.38%
Plinth |  | 16 | 100%
RCC |  | 19 | 100% | [5 empty] | Excavation in process | 8
Brickwork | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Excavation Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 16 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% | [5 empty] | Footing in Process | 4
Flooring & Fitting | Flooring & Fitting | 14 | 87.5% | [5 empty] | Footing Completed | 8
Painting & Wooden |  | 10 | 62.5% | [5 empty] | Plinth in process | 12
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 16
Possession |  | 0 | 0%
Construction details: Tower 4 = G + 1st Podium + 2nd Podium + 1st to 16th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 16 Floor completed, External Plaster upto 16 Floor completed, Flooring upto 11 Floor completed
Ground |  | 1 | Podium |  | 2 |  | Floors | 16 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 19 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 16 Floor completed, External Plaster upto 16 Floor completed, Flooring upto 11 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 16 | 100% |  | 81.88% |  | 93.44%
Plinth |  | 16 | 100%
RCC |  | 19 | 100% | [5 empty] | Excavation in process | 8
Brickwork | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Excavation Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 16 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% | [5 empty] | Footing in Process | 4
Flooring & Fitting | Flooring & Fitting | 11 | 68.75% | [5 empty] | Footing Completed | 8
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process | 12
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 16
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 16600
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area)
Floor rise rate Per Sq. Ft. from 1st floor ( on Saleable area) | [5 empty] | 55/-
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 500000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 13280
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
A
B
C
Total |  | 0 | 0 |  |  | 0
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
A
B
C
Total |  | 0 | 0 |  |  | 0
Building details Floor Wise
Details of Flats in Building
Flat No. (As per Sale Plan) | Flat No. (As per Approved Plan) | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
N
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Tower No.1 |  | 46 | 40354.4513 |  |  | 64567.122
Tower No.2 |  | 46 | 37199.7382 |  |  | 59519.5811
Tower No.3 |  | 32 | 26053.078 |  |  | 41684.9247
Tower No.4 |  | 42 | 29763.3209 |  |  | 47621.3135
Total |  | 166 | 133370.5883 |  |  | 213392.9413
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Tower No.1
Ground Floor is Parking
1st Level Podium (Parking)
2nd Level Podium (Fitness Centre & Parking)
1st Floor
1 |  | 2 BHK | 744.0077 |  | 0 | 1190.4123 | N | 1st Floor | 1.6
2 |  | 3 BHK | 1048.0907 |  | 0 | 1676.9451 | N
3 |  | 3 BHK | 1040.5559 |  | 0 | 1664.8894 | N
4 |  | 2 BHK | 636.26 |  | 0 | 1018.0161 | N
2nd to 4th Floor & 6th to 11th Floor
1 |  | 2 BHK | 744.0077 |  | 0 | 1190.4123 | N | 2nd to 4th Floor & 6th to 11th Floor
2 |  | 3 BHK | 1048.0907 |  | 0 | 1676.9451 | N
3 |  | 3 BHK | 1040.5559 |  | 0 | 1664.8894 | N
4 |  | 2 BHK | 636.26 |  | 0 | 1018.0161 | N
5th Floor
1 |  | 2 BHK | 744.0077 |  | 0 | 1190.4123 | N | 5th Floor
2 |  | 3 BHK | 1048.0907 |  | 0 | 1676.9451 | N
3 |  | 3 BHK | 1040.5559 |  | 0 | 1664.8894 | N
4 |  | Refuge Area |  |  |  |  | N
12th Floor
1 |  | 2 BHK | 744.0077 |  | 0 | 1190.4123 | N | 12th Floor
2 |  | 3 BHK | 1048.0907 |  | 0 | 1676.9451 | N
3 |  | 3 BHK | 1040.5559 |  | 0 | 1664.8894 | N
4 |  | Refuge Area |  |  |  |  | N
Tower No.2
Ground Floor is Parking
1st Level Podium (Parking)
2nd Level Podium (Fitness Centre & Parking)
1st Floor
1 |  | 2 BHK | 735.3965 |  | 0 | 1176.6344 | N | 1st Floor
2 |  | 3 BHK | 1044.2156 |  | 0 | 1670.745 | N
3 |  | 2 BHK | 696.3232 |  | 0 | 1114.1171 | N
4 |  | 2 BHK | 748.8515 |  | 0 | 1198.1624 | N
2nd to 4th Floor & 6th to 11th Floor
1 |  | 2 BHK | 735.3965 |  | 0 | 1176.6344 | N | 2nd to 4th Floor & 6th to 11th Floor
2 |  | 3 BHK | 1044.2156 |  | 0 | 1670.745 | N
3 |  | 2 BHK | 696.3232 |  | 0 | 1114.1171 | N
4 |  | 2 BHK | 748.8515 |  | 0 | 1198.1624 | N
5th Floor
1 |  | 2 BHK | 735.3965 |  | 0 | 1176.6344 | N | 5th Floor
2 |  | 3 BHK | 1044.2156 |  | 0 | 1670.745 | N
3 |  | 2 BHK | 696.3232 |  | 0 | 1114.1171 | N | 5th Floor
4 |  | Refuge Area |  |  |  |  | N
12th Floor
1 |  | 2 BHK | 735.3965 |  | 0 | 1176.6344 | N | 12th Floor
2 |  | 3 BHK | 1044.2156 |  | 0 | 1670.745 | N
3 |  | 2 BHK | 696.3232 |  | 0 | 1114.1171 | N
4 |  | Refuge Area |  |  |  |  | N
Tower No.3
Ground Floor is Parking
1st Level Podium (Parking)
2nd Level Podium (Fitness Centre & Parking)
1st Floor
1 |  | 3 BHK | 991.472 |  | 0 | 1586.3553 | N | 1st Floor
2 |  | 2 BHK | 696.2155 |  | 0 | 1113.9448 | N
3 |  | 2 BHK | 748.8515 |  | 0 | 1198.1624 | N
2nd to 4th Floor & 6th to 11th Floor
1 |  | 3 BHK | 991.472 |  | 0 | 1586.3553 | N | 2nd to 4th Floor & 6th to 11th Floor
2 |  | 2 BHK | 696.2155 |  | 0 | 1113.9448 | N
3 |  | 2 BHK | 748.8515 |  | 0 | 1198.1624 | N
5th Floor
1 |  | 3 BHK | 991.472 |  | 0 | 1586.3553 | N | 5th Floor
2 |  | 2 BHK | 696.2155 |  | 0 | 1113.9448 | N
3 |  | Refuge Area |  |  |  |  | N
12th Floor (Refuge Area)
Tower No.4
Ground Floor is Parking
1st Level Podium (Parking)
2nd Level Podium (Fitness Centre & Parking)
1st Floor
1 |  | 2 BHK | 636.4753 |  | 0 | 1018.3605 | N | 1st Floor
2 |  | 2 BHK | 628.0792 |  | 0 | 1004.9267 | N
3 |  | 4.5 BHK | 1511.3732 |  | 0 | 2418.1972 | N
2nd to 4th Floor & 6th to 11th Floor
1 |  | 2 BHK | 636.4753 |  | 0 | 1018.3605 | N | 2nd to 4th Floor & 6th to 11th Floor
2 |  | 2 BHK | 635.3989 |  | 0 | 1016.6383 | N
3 |  | 2 BHK | 750.3584 |  | 0 | 1200.5735 | N
4 |  | 2 BHK | 751.5425 |  | 0 | 1202.468 | N
5th Floor
1 |  | 3 BHK | 636.4753 |  | 0 | 1018.3605 | N | 5th Floor
2 |  | 2 BHK | 635.3989 |  | 0 | 1016.6383 | N
3 |  | Refuge Area |  |  |  |  | N
4 |  | 2 BHK | 751.5425 |  | 0 | 1202.468 | N
12th Floor (Refuge Area)
Remarks:
1. Tower 1 to 4 = Construction work is the same as last visit (dtd.10/03/2025), but work is in process at the time of the visit. (Slow Speed) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet. 5. We considered Flat rate as per Market Inquire. 6. Car parking is subjected to authentic documentation. 7. As per Brochure, Phase 1 is comprised of tower 1 & 2 and Phase 2 is comprised of tower 3 & 4. 8. We have refer latest CC from RERA site. 9. We have given construction percentage as per proposed no of Floors because construction work goes beyound approved no of Floors. 10. Since the project has received first CC on 17/01/2019, but still project is under construction. 11. Please provide revised approved CC & plans . 12. As per RERA, completion period of project Safal Trademark is expired on 31/08/2024 but still project is under construction. 11. On site, we meet Mr.Jugnu - 8451099951..
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Aakash Chaure |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY :
Google Map :
T2

## Note
2020-01-13 | Pratiksha

## Valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Safal Trademark | 2BHK | 0 | 1203 | 16541.9784 | 19900000
99 Acres | Safal Trademark | 3BHK | 0 | 1665 | 17477.4775 | 29100000
99 Acres | Safal Trademark | 5BHK | 3469 | 5550.4 | 17836.5523 | 99000000
99 Acres | Safal Trademark | 5BHK | 1792 | 2867.2 | 17403.7388 | 49900000
99 Acres | Safal Trademark | 4BHK | 1445 | 2312 | 17214.5329 | 39800000
99 Acres | Safal Trademark | 3BHK | 991 | 1585.6 | 17154.3895 | 27200000
Average | Safal Trademark |  |  |  | 17271.4449
Valuation Adopted |  |  |  |  | 17200