## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-06-06
Name of the builder group |  |  |  |  | M/s.Vikaasha Housing
Name of the builder company |  |  |  |  | M/s.Vikaasha Housing
Name of the Project |  |  |  |  | Space World
Contect Details ( Name & Contect No.) |  |  |  |  | 02532511686
Name / No of the Building |  |  |  |  | Building No. 1 (A, B, C, D, E, F, G Wings) Building No.2 (A,B,C Wings)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | Buiding No.1 |  | A Wing | P52000011751
[7 empty] | B Wing | P52000011043
[7 empty] | C Wing | P52000007711
[7 empty] | D Wing | P52000007375
[7 empty] | E Wing | P52000009794
[7 empty] | F Wing | P52000006851
[7 empty] | G Wing | P52000012225
[5 empty] | Building No.2 |  | A Wing | P52000007986
[7 empty] | B Wing | P52000008029
[7 empty] | C Wing | P52000006165
Project location details |  | Space World, Survey No.17/1 Part, Karjat-Murbad Road, Anjap, Neral, Karjat, Raigad.
Survey No |  | 17/1 Part
Road |  | Karjat-Murbad Road |  |  | Locality/Village |  | Anjap
City |  | Neral |  |  | District |  | Raigad
Taluka |  | Karjat |  |  | Pin Code |  | 410101
Near by Landmark |  | SBW Logistics |  |  | Distance from city centre: |  | About 7.2Km from Neral Junction Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Land |  | Building |  | Road |  | Open Land
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.008684, 73.375557
Location Link |  | https://goo.gl/maps/ybk6tzzcCmC7r4z3A
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 11814.8
Permissible FSI |  |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  |  | 0.13021
Total FSI availaible for the project |  |  |  |  | 1.3302
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 15716.16
Total number of Buildings |  |  |  |  | 02 Buildings (10 Wings)
Approval Detail : Plan approval
Layout Approval No |  | MS/LNA1/SR/117/2014 |  |  |  | Dated | 25/07/2016.
Approved Floor plan No. |  | MS/LNA1/SR/117/2014 |  |  |  | Dated | 25/07/2016.
Commencement Certificate No. |  | MS/LNA1(B)/SR.117/2014 Valid Up to: Building No. 1 (A, B, C, D, E, F, G Wings) & Building No.2 (A, B &C Wings) = G +1st to 7th Floor |  |  |  | Dated | 25/07/2016. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 25/07/2016. |  | Expected Completion |  | As per RERA: Building No.1 Wing( A, B, C, D, E, F & G ) = 30/12/2024 Building No. 2 Wing (A, B & C) = 31/12/2023 Bldg 1- C Wing = 31/12/2023 Bldg 1- D Wing = 31/12/2023 Bldg 1- E Wing = 31/12/2023 Bldg 1- F Wing = 31/12/2023 Bldg 1- G Wing = 31/12/2023 Bldg 2- A Wing = 31/12/2021 Bldg 2- B Wing = 31/12/2021 Bldg 2- C Wing = 31/12/2021
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 15716.16 |  | Approved no of units |  | Flats = 448
Approved no of Floors |  | Building No. 1 (A, B, C, D, E, F, G Wings) & Building No.2 (A, B & C Wings) = G +1st to 7th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Building No.1 (A & B Wings) = G + 1st to 7th Floor | [6 empty] | Excavation work completed,
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 0% |  | 20% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.1 (C Wing) = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Footing work Completed
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Footing work Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 5% |  | 32.5% |  | Excavation in process | 3.5
Plinth |  | 3.5 | 50% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.1 (D, E, F Wings) = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.1 (G Wing) = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 1 Slab completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 15% |  | 48.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 1 | 12.5% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.2 (A Wing) = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 76.43% |  | 90.71% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 28.57% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.2 (B Wing) = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 73.93% |  | 89.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 28.57% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.2 (C Wing) = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 6 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 73.93% |  | 89.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 28.57% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3350 |  |  | 100/- - Akash
Recommended rate of Parking | [5 empty] | 100000/-
Development + Infra charges | [5 empty] | 2,00,000/-
Distressed valuation of the Property | [5 empty] | 2680
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Blg No.1 - A Wing |  | 42 | 14666.1868 |  |  | 22372
Blg No.1 - B Wing |  | 42 | 14513.0985 |  |  | 22358
Blg No.1 - C Wing |  | 56 | 19299.2977 |  |  | 29806
Blg No.1 - D Wing |  | 42 | 14666.1868 |  |  | 22372
Blg No.1 - E Wing |  | 56 | 22304.0629 |  |  | 34692
Blg No.1 - F Wing |  | 42 | 20797.1884 |  |  | 33656
Blg No.1 - G Wing |  | 28 | 14218.6385 |  |  | 23184
Blg No.2 - A Wing |  | 56 | 14304.8178 |  |  | 21805
Blg No.2 - B Wing |  | 28 | 9301.6805 |  |  | 14756
Blg No.2 - C Wing |  | 56 | 14359.0684 |  |  | 21840
Total |  | 448 | 158430.2262 |  |  | 246841
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.1
Ground Floor is for Parking
A Wing
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 1 BHK | 352.8466 |  | 0 | 533 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | 186550
2 |  | 1 BHK | 352.8466 |  | 0 | 533 | N |  | 186550
3 |  | 1 BHK | 352.8466 |  | 0 | 533 | N |  | 186550
4 |  | 1 BHK | 352.8466 |  | 0 | 533 | N |  | 186550
5 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
6 |  | 1 BHK | 341.8915 |  | 0 | 532 | N
B Wing
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 1 BHK | 341.8915 |  | 0 | 532 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | 186200
2 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
3 |  | 1 BHK | 352.887 |  | 0 | 533 | N |  | 186550
4 |  | 1 BHK | 352.8466 |  | 0 | 533 | N |  | 186550
5 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
6 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
C Wing | [8 empty] | 0
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 1 BHK | 341.8915 |  | 0 | 532 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
2 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  |  | 1.556
3 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
4 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
5 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
6 |  | 1 BHK | 341.8915 |  | 0 | 532 | N |  | 186200
7 |  | 1 BHK | 352.8466 |  | 0 | 533 | N |  | 186550
8 |  | 1 BHK | 352.8466 |  | 0 | 533 | N
D Wing
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 1 BHK | 352.8466 |  | 0 | 533 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
2 |  | 1 BHK | 352.8466 |  | 0 | 533 | N
3 |  | 1 BHK | 341.8915 |  | 0 | 532 | N
4 |  | 1 BHK | 341.8915 |  | 0 | 532 | N
5 |  | 1 BHK | 352.8466 |  | 0 | 533 | N
6 |  | 1 BHK | 352.8466 |  | 0 | 533 | N
E Wing
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 1 BHK | 399.962 |  | 0 | 621 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | 217350
2 |  | 1 BHK | 399.962 |  | 0 | 621 | N |  | 217350
3 |  | 1 BHK | 397.7285 |  | 0 | 619 | N |  | 216650
4 |  | 1 BHK | 397.7285 |  | 0 | 619 | N |  | 216650
5 |  | 1 BHK | 397.7285 |  | 0 | 619 | N |  | 216650
6 |  | 1 BHK | 397.7285 |  | 0 | 619 | N |  | 216650
7 |  | 1 BHK | 397.7285 |  | 0 | 619 | N |  | 216650
8 |  | 1 BHK | 397.7285 |  | 0 | 619 | N
F Wing
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | [8 empty] | 0
1 |  | 2 BHK | 494.9891 |  | 0 | 795 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | 278250
2 |  | 2 BHK | 494.9891 |  | 0 | 795 | N |  | 278250
3 |  | 2 BHK | 508.3696 |  | 0 | 861 | N |  | 301350
4 |  | 2 BHK | 482.7007 |  | 0 | 767 | N |  | 268450
5 |  | 2 BHK | 494.9891 |  | 0 | 795 | N |  | 278250
6 |  | 2 BHK | 494.9891 |  | 0 | 795 | N |  | 278250
G Wing | [8 empty] | 0
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 2 BHK | 499.4725 |  | 0 | 795 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
2 |  | 2 BHK | 499.4725 |  | 0 | 795 | N |  | 278250
3 |  | 2 BHK | 516.1446 |  | 0 | 861 | N |  | 301350
4 |  | 2 BHK | 516.1446 |  | 0 | 861 | N |  | 301350
Building No.2 | [8 empty] | 0
Ground Floor is for Parking | [8 empty] | 0
A Wing | [8 empty] | 0
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | [8 empty] | 0
1 |  | 1 RK | 228.2506 |  | 0 | 365 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | 127750
2 |  | 1 RK | 236.0007 |  | 0 | 370 | N |  | c
3 |  | 1 RK | 236.0007 |  | 0 | 370 | N
4 |  | 1 RK | 236.0007 |  | 0 | 370 | N
5 |  | 1 BHK | 317.6456 |  | 0 | 450 | N
6 |  | 1 BHK | 317.6456 |  | 0 | 450 | N
7 |  | 1 RK | 236.0007 |  | 0 | 370 | N
8 |  | 1 RK | 236.0007 |  | 0 | 370 | N
B Wing
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
1 |  | 1 BHK | 332.2029 |  | 0 | 527 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor
2 |  | 1 BHK | 332.2029 |  | 0 | 527 | N
3 |  | 1 BHK | 332.2029 |  | 0 | 527 | N
4 |  | 1 BHK | 332.2029 |  | 0 | 527 | N
C Wing | [8 empty] | 0
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | [8 empty] | 0
1 |  | 1 RK | 236.0007 |  | 0 | 370 | N | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor | 129500
2 |  | 1 RK | 236.0007 |  | 0 | 370 | N |  | 129500
3 |  | 1 BHK | 317.6456 |  | 0 | 450 | N |  | 157500
4 |  | 1 BHK | 317.6456 |  | 0 | 450 | N |  | 157500
5 |  | 1 RK | 236.0007 |  | 0 | 370 | N |  | 129500
6 |  | 1 RK | 236.0007 |  | 0 | 370 | N |  | 129500
7 |  | 1 RK | 236.0007 |  | 0 | 370 | N |  | 129500
8 |  | 1 RK | 236.0007 |  | 0 | 370 | N |  | 129500
Remarks:
1. Bldg No.1 (Wing A to F) |  |  |  |  | Construction work was stopped. Work is same as last visit(21/04/2021).
Bldg No.1 (Wing G) |  |  |  |  | Construction work was stopped. Work is same as last visit(06/12/2023).
Bldg No.2(Wing A) |  |  |  |  | Construction work is same as last visit (08/03/2025).
Bldg No.2(Wing B & C) |  |  |  |  | Construction work was stopped. Work is same as last visit(06/06/2025)
2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose, Open balcony + C.B Area + W.S Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. As per RERA, completion period of Space World (Bldg No.1 & 2) is expired on 30/12/2024 & 31/12/2023 but still project is under construction. 9. Since the project has received first CC on 25/07/2016., But construction work of Building No. 1 & 2 is under construction. 10. The project (Space World : Building No.2) is not available on RERA site ( Checked on 10/06/2025 ) 11. On site we met Mr. Yadav : 9572846324. 8. On Site We Meet With Mr. Chandrakant : 9371606180.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nayanesh Lovanshi |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Space World
Google Map :
Buiding No.1
Wing G
Building No.2
Wing A, B & C
Bldg No.1
Bldg No.1
2A
2B
2A
2B
2C
2A
2B
2C

## 1C
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 5 | 50%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 5 | 25 |  | Progress |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 5% | 25% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
B1 | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 1D
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
B1 | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 1G
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
B1 | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2A
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 65% | 75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2B
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 4 | 57.14% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 8.5714 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 8.5714 | 0 | 0 | 0 | 0
Bricks | 8.5714 | 8.5714
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 58.57% | 68.57% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2C
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 1 | 14.29% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 2.1429 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 2.1429 | 0 | 0 | 0 | 0
Bricks | 2.1429 | 2.1429
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 52.14% | 62.14% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-01-13 | Pratiksha | bldg 1 A rcc com brickwork 5 this floor com B rcc com brickwork 4th floor com C rcc com brickwork 1 st floor com bldg 2 A&B footing only C,D,E,F bldg plint com G 1 st slap progress

## Valuation
2020-01-13 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing |  |  |  |  | #DIV/0!
| Proptiger |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| 99 Acres |  |  |  |  | #DIV/0!
| 99 Acres |  |  |  |  | #DIV/0!
| Average |  |  |  |  | #DIV/0!
| Valuation Adopted |  |  |  |  | 32000

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.25 | 2.75 | 8.9375 | Balcony | 1.225 | 2.75 | 3.3688 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.85 | 2.075 | 3.8388 | CB | 0.6 | 0.45 | 0.27 |  |  | 0
|  |  |  | 0 | WS | 2.45 | 0.75 | 1.8375 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 1.5 | 2.3 | 3.45 | CB | 1.5 | 0.45 | 0.675 |  |  | 0
|  |  |  | 0 | Balcony | 2.3 | 1.475 | 3.3925 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.075 | 1.37 | 1.4728 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.825 | 1.2 | 2.19 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.05 | 0.15 | 0.1575 |  |  |  | 0 |  |  | 0
| passage2 | 1.1 | 2.9 | 3.19 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 250.1177 | 23.2365 |  |  | 102.7289 | 9.5437 |  | 0 | 0
|  |  | 352.8466 | 32.7803