## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group |  |  |  |  | M/s.RRD Heights & Builders Pvt. Ltd.
Name of the builder company |  |  |  |  | M/s.RRD Heights & Builders Pvt. Ltd.
Name of the Project |  |  |  |  | The Elite
Contact Number |  |  |  |  | Mr. Chetan/Ms. Kavita - 9769791479, 8767170288, 9082417289
Name & No of Buildings |  |  |  |  | Wing A & B
Docouments Provided |  |  |  |  | Refer Data
RERA No. |  |  |  |  | P51800005901
Project location details |  | The Elite, Proposed Sale Building On Plot Bearing CTS No. 555(pt) Of Village - Mulund, Sarvodaya Nagar, Jain Mandir Road, Nahur Road, Purushottam Kheraj Road, Near Sarvodaya Heights, Nahur, Mulund (W), Mumbai 400080.
CTS No |  | 555(pt) |  |  | Locality |  | Mulund
Road |  | Nahur Road |  |  | District |  | Mumbai
City |  | Mulund |  |  | Pin Code |  | 400080
Near by Landmark |  | Sarvodaya Heights |  |  | Distance from city centre: |  | About 1.5Km from Mulund Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Irsha Chaya CHS |  | Building |  | Road |  | St. Mary Convent School
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.1649625,72.9437923
Location Link |  | https://goo.gl/maps/eBV8WAVxNvFEvLu38
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 16111.01
Permissible FSI |  |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  |  | NA
Total approved built-up area |  |  |  |  | 3677.1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 27958.14
Total number of Buildings |  |  |  |  | 2 Wings
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/2595/T/MML/AP |  |  |  | Dated | 2022-07-14
Building plan approval No |  | SRA/ENG/2595/T/MML/AP |  |  |  | Dated | 2022-07-14 | Expiry date:NA
C.certificate No |  | SRA/ENG/2595/T/MHL/AP Valid Up to: This C.C. is re-endorsed as per approved amended plans dated 14/07/2022. |  |  |  | Dated | 2022-07-14
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 27958.14
Approved no of units |  |  | 213
Approved no of Floors |  |  | Wing A & B - Stilt/Ground + 1st to 3rd Podium + 4th to 45th Floor.
Proposed no of Floors |  |  | Wing A & B - Stilt/Ground + 1st to 3rd Podium + 4th to 45th Floor.
Commencement date of construction |  |  | 2022-07-14
Expected Completion |  |  | As per Rera - 31/12/2025
Quality of construction: |  |  | Good
Projected life: |  |  | 60 Years After Completion
Material laying at Site: |  |  | Bricks, Cement & Steel etc.
Construction details: |  | Wing A & B - Stilt/Ground + 1st to 3rd Podium + 4th to 45th Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 43 Floor, Internal Plaster upto 40 Floor, External Plaster upto 38 Floor, Flooring upto 23 Floor, Painting upto 16 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 45
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 43 Floor, Internal Plaster upto 40 Floor, External Plaster upto 38 Floor, Flooring upto 23 Floor, Painting upto 16 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 11.25
Excavation |  | 45 | 100% |  | 79.17% |  | 91% |  | Excavation in process | 22.5
Plinth |  | 45 | 100% | [5 empty] | Excavation Completed | 45
RCC (Including podiums) |  | 46 | 100% | [5 empty] | Footing in Process | 11.25
Brickwork | Brickwork & Internal Plaster | 43 | 95.56% | [5 empty] | Footing Completed | 22.5
Internal Plaster | Brickwork & Internal Plaster | 40 | 88.89% | [5 empty] | Basement 1 | 0 | 155
Ext. Plaster & Plumbing | External Plaster & Plumbing | 38 | 84.44% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 23 | 51.11% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 16 | 35.56% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 33.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 45
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 15000
Floor rise rate Per Sq. Ft. | [5 empty] | 50/-
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 800000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 12000
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 107 |  | 145028.8961 |  | 232046.2337
Wing B |  | 106 |  | 143154.2884 |  | 223011.5409
Total |  | 213 |  | 288183.1845 |  | 455057.7747
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0
3 |  |  |  | 0 | 0
4 |  |  |  | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A
Ground Floor for Parking
1st & 2nd Podium Floor for Parking
3rd Floor for Amenities
4th to 6th, 8th to 13th, 15th to 19th, 21st, 23rd to 28th, 30th to 34th Floor for Residential
1 |  | 2BHK | 988.8887 | 0 | 1582.2219 | 4th to 6th, 8th to 13th, 15th to 19th, 21st, 23rd to 28th, 30th to 34th Floor for Residential |  |  |  |  | 92.3628
2 |  | 2BHK | 988.8887 | 0 | 1582.2219
3 |  | 3BHK | 1405.3478 | 0 | 2248.5565
20th Service Floor
7th, 14th, 22nd, 29th Floor (Part Refuge Area)
1 |  | 2BHK | 988.8887 | 0 | 1582.2219 | 7th, 14th, 22nd, 29th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 3BHK | 1405.3478 | 0 | 2248.5565 | [5 empty] | 15565.5414 | 30580368.9984 | 112427.8272
35th Floor | [11 empty] | 30692796.8256
1 |  | 5BHK | 3107.5668 | 0 | 4972.1069 | 35th Floor
2 |  | 4BHK | 1903.9363 | 0 | 3046.2981
36th Floor (Part Refuge Area)
1 |  | 2BHK | 1851.4252 | 0 | 2962.2804 | 36th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 4BHK | 1828.5883 | 0 | 2925.7413
37th to 42nd Floor
1 |  | 5BHK | 3138.2442 | 0 | 5021.1907 | 37th to 42nd Floor
2 |  | 3BHK | 1405.3478 | 0 | 2248.5565
43rd Floor (Part Refuge Area)
1 |  | 2BHK | 1851.4252 | 0 | 2962.2804 | 43rd Floor (Part Refuge Area)
2 |  | 3BHK | 1405.3478 | 0 | 2248.5565
44th Floor (Duplex with 45th Floor)
1 |  | 7BHK (Duplex with 45th Floor) | 5470.1572 | 0 | 8752.2515 | 44th Floor (Duplex with 45th Floor)
2 |  | 3BHK | 1405.3478 | 0 | 2248.5565
45th Floor
1 |  | 7BHK (Duplex with 44th Floor) |  |  |  | 45th Floor
2 |  | 3BHK | 1405.3478 | 0 | 2248.5565
Wing B
Ground Floor for Parking
1st & 2nd Podium Floor for Parking
3rd Floor for Amenities
4th, 6th, 8th to 13th, 15th to 19th, 21st, 23rd to 28th, 30th to 34th Floor for Residential
1 |  | 2BHK | 988.8887 | 0 | 1582.2219 | 4th, 6th, 8th to 13th, 15th to 19th, 21st, 23rd to 28th, 30th to 34th Floor for Residential
2 |  | 2BHK | 988.8887 | 0 | 1582.2219
3 |  | 3BHK | 1405.3478 | 0 | 2248.5565
20th Service Floor
7th, 14th, 22nd, 29th Floor (Part Refuge Area)
1 |  | 2BHK | 988.8887 | 0 | 1582.2219 | 7th, 14th, 22nd, 29th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 3BHK | 1405.3478 | 0 | 2248.5565
35th Floor
1 |  | 5BHK | 3138.2442 | 0 | 5021.1907 | 35th Floor
2 |  | 3BHK (Duplex with 36th Floor) | 1892.1573 | 0 | 3027.4516
36th Floor (Part Refuge Area)
1 |  | 2BHK | 1851.4252 | 0 | 2962.2804 | 36th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | Lower Duplex with 35th Floor
37th to 42nd Floor
1 |  | 5BHK | 3138.2442 | 0 | 5021.1907 | 37th to 42nd Floor
2 |  | 3BHK | 1405.3478 | 0 | 1405.3478
43rd Floor (Part Refuge Area)
1 |  | 2BHK | 1851.4252 | 0 | 1851.4252 | 43rd Floor (Part Refuge Area)
2 |  | 3BHK | 1405.3478 | 0 | 2248.5565
44th Floor (Duplex with 45th Floor)
1 |  | 7BHK (Duplex with 45th Floor) | 5470.1572 | 0 | 8752.2515 | 44th Floor (Duplex with 45th Floor)
2 |  | 3BHK | 1372.889 | 134.7868 | 2264.0158
45th Floor
1 |  | Lower Duplex with 44th Floor |  |  |  | 45th Floor
2 |  | 3BHK | 1372.889 | 134.7868 | 2264.0158
Remarks: 1. Construction work is Same as last visit dtd. 17/03/2025. 2. Car parking is subjected to authentic documentation. 3. We have considered rate by verifying it from market inquire. 4. On site, we meet Mr Sontosh Kumar (site engineer) - 9029409221. 5. We update CC from Rera (On 06/04/2023). 6. We have updated approved floor plans (On 03/07/2023). 7. As per RERA, completion period of project is expired on 29/12/2024 but still project is under construction. 7. Construction work goes beyond approved CC. Please provide revised approved CC. | [9 empty] | 1. Construction work is Same as last visit (12/09/2023).
Authorized Signatory Name & Seal of the agency
Photographs of Property : |  |  | The Elite
Google Map :
Formulas:
Mulund = [Mulund, row above]

## C %
Particulars | totaL floor | 42
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 88.3721 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 43 | 38 | 88.0952 | Progress |  |  | 10 | 35.3488 | 13.2143 | 7.619 | 0.2381 | 0 | 0
Bricks | Total Floor | completed Floor | 76.1905 | Recommended |  |  | 30 | 26.5116 | 13.2143 | 7.619 | 0.11905 | 0 | 0
| 42 | 37 | 2.381
plaster | Total Floor | completed Floor | 0
| 42 | 32 | 0
Flooring | Total Floor | completed Floor
| 42 | 1 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 42 | 0 |  | RCC | 35.3488 | 26.5116
Finishing | Total Floor | completed Floor |  | Bricks | 13.2143 | 13.2143
| 42 | 0 |  | Plaster | 7.619 | 7.619
|  |  |  | Flooring | 0.2381 | 0.11905
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 66.4203 | 77.464

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0