## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Sammaan Capital | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | SCL Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-06-06 | [6 empty] | Axis Sanpada | PNB Panvel |  | SCL Vashi
Name of the builder group |  |  |  | Tigon Reality Private Limited | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | Tigon Reality Private Limited | [9 empty] | SCL Thane
Name of the Project |  |  |  | Tigon Elite | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 7715072480 / 9967511196 | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA | [9 empty] | SCL Virar
Name / No of the Building As per Approved Plan |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | Bldg No.46, Subhash Nagar Sagar CHS LTD | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Sale Plans, Airport Noc, Fire Noc | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800047212 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Tigon Elite, CTS No.828/84 to 828/93, Redevelopement of " Bldg No. 46, Subhash Nagar Sagar CHS Ltd. ", near Satra Harmony, Principal Mandalecha Street, Subhash Nagar, Chembur, Chembur East, Kurla, Mumbai - 400071. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 828/84 to 828/93, Redevelopement of " Bldg No. 46, Subhash Nagar Sagar CHS Ltd. " | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Subhash Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Principal Mandalecha Street |  | Locality/Village |  | Chembur | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Chembur East |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400071 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Satra Harmony |  | Distance from city centre: |  | 0.80KM from Chembur Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Podar Spraha Diamond
West | NA | 10.90MTS Wide Existing Road |  |  | Principal Mandalecha Road
North | NA | 12.00MTS Wide Existing Road |  |  | Internal Road
South | NA | Other Plot |  |  | Bldg No. 45 Subhash Nagar
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.057010,72.904664
Location Link |  | https://maps.app.goo.gl/4wuL6AptfB9LLszq9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 891.45
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 4.6082
Total FSI availaible for the project |  |  |  | 7.6082
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6782.33
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority(MHADA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | MH/EE/(BP)/GM/MHADA-29/1131/2024/IOA/1/Amend |  |  | Dated | 2024-10-31 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | MH/EE/(BP)/GM/MHADA-29/1131/2024/IOA/1/Amend |  |  | Dated | 2024-10-31 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-29/1131/2024/FCC/3/Amend |  |  | Dated Valid Upto Date | 04/11/2024 29/08/2025 |  | NO REMARK | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. Re-endorsed upto top of 9th floor & Further extended upto top of 14th floor of i.e. Basement (pt.) for Pump Room + Ground (Pt.) for Shops + Stilt for parking +1st to 14th upper floor along with parking tower as per approved amended plan dtd. 31.10.2024. Note:-That the guidelines for reduction of Air Pollution issued by Chief Engineer (D.P.) BMC dt. 15/09/2023,Hon’ble Municipal Commissioner (BMC) dt. 25/10/2023 and MHADA circular vide No. ET-321, dtd. 25.10.2023 shall be strictly followed on site | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA) | Palghar Muncipal Council
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-29/1131/ 2025/FCC/4/Amend |  |  | Dated Valid Upto Date | 07/02/2025 29/08/2025 |  | #VALUE! | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. further extended upto top of 16th (Pt.) floor (including LMR/OHT) along with parking tower as per approved amended plans dtd. 31.10.2024. | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA) | Palghar Muncipal Council
Fire Noc No Valid Up to: |  | FB/R-V/HR/13 |  |  | Dated | 2022-06-14 |  |  |  | #VALUE! | NO REMARK | [5 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Stilt + 1st to 16th Floor (Height = 50.80m) | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | Stilt + 1st to 16th Floor (Height = 50.80m) |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up for: |  | SNCR/WEST/B/090121/573141 |  |  | Dated | 2021-10-22 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
|  | Site Elevation = 4.58M Permissible Top Elevation = 57.13M |  |  | Valid upto Dated | 2029-10-21 | [11 empty] | Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 6782.33
Approved no of units |  |  | Flats - 104, Shops - 05
Approved no of Floors |  |  | Wing A & B = G + 1st to 16th Floor
Proposed no of Floors |  |  | Wing A & B = G + 1st to 16th Floor
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | World Class Gym, Library, Business Center, Private Mini Theatre, Kids Play Area, Indoor Games etc. |  |  |  |  | https://www.99acres.com/tigon-elite-subhash-nagar-central-mumbai-npxid-r399442?nn_source=Performance&nn_account=google_cmt_projects&nn_campaign=13742860051_124430417716_614690945708&nn_medium=13742860051_124430417716_614690945708&nn_adtype=g_&nn_keyword=&nn_placement=&gad_source=1&gclid=EAIaIQobChMI1cnb7N2kigMVKQ97Bx2AbzQLEAAYASAAEgL6UfD_BwE#showModal
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A & B = G + 1st to 16th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 13 Floor, Flooring upto 2 Floor Completed | , External Plaster upto 13 Floor, Flooring upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 13 Floor, Flooring upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 74.38% |  | 89.69% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 81.25% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 12.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Construction details: |  | B Wing = 1B + G + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 17500 |  |  |  | Rate 17500 Sanjay verbal 31/01/2025 | [7 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 25000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 800000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 14000 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A + B |  | 5 |  | 1276.8924 |  | 1915.3386
Total |  | 5 |  | 1276.8924 |  | 1915.3386
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 57 |  | 32539.9509 |  | 48809.9263
Wing B |  | 47 |  | 30458.9984 |  | 45688.4977
Total |  | 104 |  | 62998.9493 |  | 94498.424 |  | 104
Grand Total |  | 109 |  | 64275.8417 |  | 96413.7626
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading : | 10.764
50%
Wing A + B
Ground Floor For Entrance Lobby, Commercial, Meter Room, Society Office & Parking
1 |  | Shop | 201.4892 | 0 | 201.4892 | 0 | 302.2337
2 |  | Shop | 118.8432 | 0 | 118.8432 | 0 | 178.2648
3 |  | Shop | 628.4938 | 0 | 628.4938 | 0 | 942.7407
4 |  | Shop | 135.4714 | 0 | 135.4714 | 0 | 203.2071
5 |  | Shop | 192.5949 | 0 | 192.5949 | 0 | 288.8923
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Balcony Area + Dry Yard Area | Gross Carpet area | Attached Terrace area | Saleable area Loading : | 10.764
50%
Wing A
1st Floor For Residential
1 |  | 2BHK | 704.0732 | 64.3687 | 768.442 | 0 | 1152.6629
2 |  | 1BHK | 443.2615 | 0 | 443.2615 | 0 | 664.8923
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | 2BHK | 668.1215 | 24.2922 | 692.4137 | 0 | 1038.6205
2nd to 5th, 7th, 9th & 10th Floor
1 |  | 2BHK | 704.0732 | 64.3687 | 768.442 | 0 | 1152.6629
2 |  | 1BHK | 443.2615 | 0 | 443.2615 | 0 | 664.8923
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | 2BHK | 668.1215 | 24.2922 | 692.4137 | 0 | 1038.6205
6th Floor
1 |  | 2BHK | 704.0732 | 64.3687 | 768.442 | 0 | 1152.6629
2 |  | 1BHK | 443.2615 | 0 | 443.2615 | 0 | 664.8923
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | 2BHK | 668.1215 | 24.2922 | 692.4137 | 0 | 1038.6205
8th Floor (Part Refuge Area)
1 |  | Refuge Area
2 |  | 1BHK | 443.2615 | 0 | 443.2615 | 0 | 664.8923
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | Refuge Area
11th & 12th Floor
1 |  | 2BHK | 704.0732 | 64.3687 | 768.442 | 0 | 1152.6629
2 |  | 1BHK | 443.2615 | 0 | 443.2615 | 0 | 664.8923
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | 2BHK | 668.1215 | 24.2922 | 692.4137 | 0 | 1038.6205
13th Floor
1 |  | 3BHK | 960.687 | 64.3687 | 1025.0557 | 0 | 1537.5836
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | 2BHK | 668.1215 | 24.2922 | 692.4137 | 0 | 1038.6205
14th to 15th Floor
1 |  | 3BHK | 960.687 | 64.3687 | 1025.0557 | 0 | 1537.5836
6 |  | 1BHK | 319.1526 | 0 | 319.1526 | 0 | 478.7289
7 |  | 2BHK | 668.1215 | 24.2922 | 692.4137 | 0 | 1038.6205
16th Floor
1 |  | 2BHK | 704.0732 | 64.3687 | 768.442 | 0 | 1152.6629
2 |  | 1BHK | 443.2615 | 0 | 443.2615 | 0 | 664.8923
6 |  | Fitness Center
7
Wing B
Ground Floor For Entrance Lobby, Meter Room, Society Office & Parking
1st Floor For Residential & Parking Tower
3 |  | Entrance Lobby Below
4 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
5 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
2nd to 5th, 7th, 9th & 10th Floor
3 |  | 2BHK | 629.2634 | 0 | 629.2634 | 0 | 943.8952
4 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
5 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
6th Floor
3 |  | 2BHK | 629.2634 | 0 | 629.2634 | 0 | 943.8952
4 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
5 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
8th Floor
3 |  | 2BHK | 597.0791 | 89.8794 | 686.9585 | 0 | 1030.4377
4 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
5 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
11th & 12th Floor
3 |  | 2BHK | 620.437 | 24.8648 | 645.3018 | 0 | 967.9527
4 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
5 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
13th Floor
3 |  | 3BHK | 792.7686 | 58.6638 | 851.4324 | 0 | 1277.1486
4 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
5 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
14th to 15th Floor
3 |  | 3BHK | 792.7686 | 58.6638 | 851.4324 | 0 | 1277.1486
4 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
5 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
16th Floor
3 |  | 1BHK | 475.123 | 24.8648 | 499.9878 | 0 | 749.9817
4 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
5 |  | 2BHK | 690.403 | 32.1844 | 722.5873 | 0 | 1083.881
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | 0 | 0
7 |  |  |  | 0 | 0 | 0 | 0
Ground Floor
3 |  | Entrance Lobby Below
4 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
5 |  | 2BHK | 586.0998 | 0 | 586.0998 | 0 | 879.1497
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Construction work is in process at the time of Visit. Internal visit was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area + Dry Yard Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Fire NOC & Airport NOC.
* | We have given Valuation for Sale Flats and Shops only.
* | NO REMARK FOR CC
* | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
* | We have referred Approved Plan and Approved CC from MHADA Site.
* | We have referred Wing bifurcation from Approved Plan Sheet No. 7 out of 7.
* | Recommended Rates / Other charges of the Property have been revised on 31/01/2025.
* | We have updated CC from MCGM site on 18/09/2025.
* | Validity of CC is expired on 29/08/2025. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tigon Elite
Layout :
Google Map :
Formulas:
Chembur = [Chembur, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C57: SACHIN: Floor with height
Note on C59: SACHIN: Survey Nos.
Note on C61: SACHIN: Height from AMSL
Note on D64: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F124: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H156: SACHIN: Give loading of 50% for A Category
Wing A
Wing B
Parking Tower
A Wing
B Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34 | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
35 | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0