## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 08/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-07
Name of the builder group |  |  |  | Green Park Residency
Name of the builder company |  |  |  | Green Park Residency
Name of the Project |  |  |  | Green Park Residency
Provided Contact Details ( Name & Contact No.) |  |  |  | 9967777400/ 9607319777
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr.Yadav - 9323036886 & Mr. Anil 9607319777
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51700018080
Project location details |  | Green Park Residency, Survey No.141/2/A/2, near Platinum Decor India, Bhiwandi Wada Road, Koliwali, Kawad Khurd, Bhiwandi East, Bhiwandi, Thane - 421302.
Survey No |  | 141/2/A/2
Locality |  | Koliwali
Road |  | Bhiwandi Wada Road |  | Locality/Village |  | Kawad Khurd
City |  | Bhiwandi East |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421302
Nearby Landmark |  | Platinum Decor India |  | Distance from city centre: |  | 10KM from Bhiwandi Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Bhiwandi Wada Road
North | NA | NA |  |  | Kumavat Farm House
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.3463 |  | Longitude |  | 73.0713
Location Link |  | https://goo.gl/maps/78Z1AqnAuRm5ecaW8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4440
Permissible FSI |  |  |  | 1.55 |  |  |  | or 1.95
Permissible TDR/Paid FSI |  |  |  | -0.0019122
Total FSI availaible for the project |  |  |  | 1.5481
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6873.51
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mumbai Metropolitan Region Development Authority
Layout Approval No |  | SROT/BSNA/2501/BP/CC/Kawad Khurd-04/339/2022 |  |  | Dated | 2022-03-11
Approved Floor plan No. |  | SROT/BSNA/2501/BP/CC/Kawad Khurd-04/339/2022 |  |  | Dated | 2022-03-11
Commencement-CC No Valid Up to: |  | SROT/BSNA/2501/BP/CC/Kawad Khurd-04/339/2022 |  |  | Dated | 2022-03-11
G + 1st to 12th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 6873.51
Approved no of units |  |  | Flats - 147, Shops - 16, Offices - 8
Approved no of Floors |  |  | G + 1st to 12th Floor
Proposed no of Floors |  |  | G + 1st to 16th Floor
Expected Completion |  |  | As per RERA - 30/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | GYM, Jogging Track & Club
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | G + 1st to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.5 Floor Completed | , RCC upto 4 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Part 1 (Flat No.1) | Part 2 (Flat No.2 to 4) | Slab/Floor Average of Part 1 & 2 | Complition % | Progress % | Disbursement % | Piling Work in process | 4
Excavation |  | 16 | 16 | 16 | 100% | 21.05% | 53.15% | Excavation in process | 8
Plinth |  | 16 | 16 | 16 | 100% |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 7 | 1 | 4 | 23.53% |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 4 | 0 | 2 | 12.5% |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 3 | 0 | 1.5 | 9.375% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0 | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0 | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0 | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0 | 0 | 0% |  |  | Plinth in process | 12
Possession |  | 0 | 0 | 0 | 0% |  |  | Plinth completed | 16
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3800
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6500
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 5500
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3040
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 18 |  | 6151.1416 |  | 9534.2695
Offices |  | 6 |  | 6392.3629 |  | 9908.1624
Total |  | 24 |  | 12543.5045 |  | 19442.4319
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 102740.6335 | 67447.3047
Flats |  | 147 |  | 54903.8002 |  | 83298.2016
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Ground Floor For Commercial & Part Parking | [8 empty] | 10.764
1 |  | Shop | 361.8319 | 0 | 560.8394 | Ground Floor For Commercial & Part Parking
2 |  | Shop | 301.5265 | 0 | 467.3662
3 |  | Shop | 361.8319 | 0 | 560.8394
4 |  | Shop | 361.8319 | 0 | 560.8394
5 |  | Shop | 301.5265 | 0 | 467.3662
6 |  | Shop | 361.8319 | 0 | 560.8394
7 |  | Shop | 361.8319 | 0 | 560.8394
8 |  | Shop | 301.5265 | 0 | 467.3662
9 |  | Shop | 361.8319 | 0 | 560.8394
10 |  | Shop | 361.8319 | 0 | 560.8394
11 |  | Shop | 301.5265 | 0 | 467.3662
12 |  | Shop | 361.8319 | 0 | 560.8394
13 |  | Shop | 361.8319 | 0 | 560.8394
14 |  | Shop | 301.5265 | 0 | 467.3662
15 |  | Shop | 361.8319 | 0 | 560.8394
16 |  | Shop | 361.8319 | 0 | 560.8394
17 |  | Shop | 301.5265 | 0 | 467.3662
18 |  | Shop | 361.8319 | 0 | 560.8394
1st Floor For Part Commercial & Part Amenities
1 |  | Office | 1065.3938 | 0 | 1651.3604 | 1st Floor For Part Commercial & Part Amenities
2 |  | Office | 1065.3938 | 0 | 1651.3604
3 |  | Office | 1065.3938 | 0 | 1651.3604
4 |  | Office | 1065.3938 | 0 | 1651.3604
5 |  | Office | 1065.3938 | 0 | 1651.3604
6 |  | Office | 1065.3938 | 0 | 1651.3604
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
1st Floor For Part Residential
1 |  | 1 | 385.6741 | 0 | 578.5112 | 1st Floor For Part Residential |  |  | 39.381
2 |  | 2 | 498.7499 | 0 | 748.1249 |  |  |  | 5.715
3 |  | 2 | 498.7499 | 0 | 748.1249
4 |  | 1 | 385.6741 | 0 | 578.5112
2nd Floor
1 |  | 1 | 385.6741 | 0 | 578.5112 | 2nd Floor
2 |  | 2 | 498.7499 | 0 | 748.1249
3 |  | 0 | 247.0607 | 0 | 370.5911
4 |  | 0 | 266.7588 | 0 | 400.1382 |  |  |  | 8.134
5 |  | 0 | 266.7588 | 0 | 400.1382 |  |  |  | 0.64912
6 |  | 0 | 247.0607 | 0 | 370.5911 |  |  |  | 1.5405 | 3912.6685 | 4560.2826
7 |  | 2 | 498.7499 | 0 | 748.1249 |  |  |  | 10.626
8 |  | 1 | 385.6741 | 0 | 578.5112 |  |  |  | 7.546
9 |  | 1 | 405.0224 | 599.2588 | 757.3483 |  |  |  | 6.93
10 |  | 1 | 405.0224 | 599.2588 | 757.3483 |  |  |  |  | 4.95
11 |  | 1 | 397.7567 | 686.4849 | 768.2563
12 |  | 1 | 397.7567 | 686.4849 | 768.2563
13 |  | 1 | 405.0224 | 599.2588 | 757.3483
14 |  | 1 | 405.0224 | 599.2588 | 757.3483
3rd to 7th, 9th to 11th Floor
1 |  | 1 | 385.6741 | 0 | 578.5112 | 3rd to 7th, 9th to 11th Floor |  |  | 3802.8651 | 2198342.484
2 |  | 2 | 498.7499 | 0 | 748.1249 |  |  |  | 3675.8567 | 2768062.167
3 |  | 0 | 247.0607 | 0 | 370.5911 |  |  |  | 3912.6685 | 1371186.9405
4 |  | 0 | 266.7588 | 0 | 400.1382 |  |  |  |  | 1480511.5065
5 |  | 0 | 266.7588 | 0 | 400.1382 |  |  |  | 4243.5334 | 1480511.5065
6 |  | 0 | 247.0607 | 0 | 370.5911 |  |  |  |  | 1371186.9405
7 |  | 2 | 498.7499 | 0 | 748.1249 |  |  |  | 4138.3464 | 2768062.167
8 |  | 1 | 385.6741 | 0 | 578.5112 |  |  |  |  | 2140491.366
9 |  | 1 | 405.0224 | 0 | 607.5336 |  |  |  |  | 2247874.3755
10 |  | 1 | 405.0224 | 0 | 607.5336 |  |  |  |  | 2247874.3755
11 |  | 1 | 389.2801 | 0 | 583.9201 |  |  |  |  | 2160504.333
12 |  | 1 | 389.2801 | 0 | 583.9201 |  |  |  |  | 2160504.333
13 |  | 1 | 405.0224 | 0 | 607.5336 |  |  |  |  | 2247874.3755
14 |  | 1 | 405.0224 | 0 | 607.5336 |  |  |  |  | 2247874.3755
8th Floor (Part Refuge Area)
1 |  | 1 | 385.6741 | 0 | 578.5112 | 8th Floor (Part Refuge Area)
2 |  | 2 | 498.7499 | 0 | 748.1249 |  |  | 3542.1892 |  | 4000
3 |  | 0 | 247.0607 | 0 | 370.5911 | [5 empty] | 147
4 |  | 0 | 266.7588 | 0 | 400.1382
5 |  | 0 | 266.7588 | 0 | 400.1382
6 |  | 0 | 247.0607 | 0 | 370.5911
7 |  | 2 | 498.7499 | 0 | 748.1249
8 |  | 1 | 385.6741 | 0 | 578.5112 |  |  | 3802.8651
9 |  | Refuge Area
10 |  | 1 | 405.0224 | 0 | 607.5336
11 |  | 1 | 389.2801 | 0 | 583.9201
12 |  | 1 | 389.2801 | 0 | 583.9201
13 |  | 1 | 405.0224 | 0 | 607.5336
14 |  | 1 | 405.0224 | 0 | 607.5336
12th Floor (Part Terrace Area)
1 |  | 1 | 389.2801 | 0 | 583.9201 | 12th Floor (Part Terrace Area)
2 |  | 1 | 389.2801 | 0 | 583.9201
3 |  | 1 | 396.5458 | 0 | 594.8186
4 |  | 1 | 396.5458 | 0 | 594.8186
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Part I = Construction work is in process at the time of visit (Very Slow Speed). Part II = Construction work is same as last visit (11/03/2025). Phase II = Work is in process at the time of visit (Very Slow Speed).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Green Park Residency
Layout :
Google Map :
Formulas:
Kawad Khurd = [Kawad Khurd, row above]
PART 1
PART 2
Phase II
Part I
Part I
Part II
Part I
Part 2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted